## IAM+PAM+Support (hidden)
S.No | Department | Resource | Location | Customer Name | Project Name | Role | Engagement Type | Allocated Billed Days | Utilized Billed Days(Project plan ) | Remaining Billed Days(Project plan ) | Utilized Billed hrs (Zoho) | Utilized Billed days (Zoho) | Remaining Billed Days (Zoho) | Project Start Date | Project End Date | Revised End Date | Comments
1 | Identity | Karthikeyan Subramanian | UAE | DOHA Bank | SailPoint | Architect | Professional Services | 119.5 | 45 | 74.5 | 246.3 | 30.7875 | 88.7125 | 2024-02-22 | 2024-10-30 | TBD
2 | Identity | Prathmesh | India | DOHA Bank | SailPoint | Engineer | Professional Services | 5 | 5 | 0 | 27 | 3.375 | 1.625
3 | Identity | Rakesh Vadnala | UAE | DOHA Bank | SailPoint | Engineer | Professional Services | 47.5 | 13 | 34.5 | 209 | 26.125 | 21.375
4 | Identity | Vaishnavi Makarand | India | DOHA Bank | SailPoint | Engineer | Professional Services | 14 | 0 | 14 | 0 | 0 | 14
5 | Identity | Kanchan Mishra | UAE | NIJordan_Sept_2023 | SailPoint | Architect | Professional Services | 22 | 22 | 0 | 198.3 | 24.7875 | -2.7875 | 2023-10-19 | 2024-07-30 | 2024-12-24 | Full Payment Completed
6 | Identity | Srikant Bavandla | UAE | NIJordan_Sept_2023 | SailPoint | Architect | Professional Services | 1 | 1 | 0 | 0 | 0 | 1
7 | Identity | Vaishnavi Makarand | India | NIJordan_Sept_2023 | SailPoint | Engineer | Professional Services | 17 | 17 | 0 | 143 | 17.875 | -0.875
8 | Identity | Swapnil Deka | UAE | NIJordan_Sept_2023 | SailPoint | Engineer | Professional Services | 35 | 30 | 5 | 259 | 32.375 | 2.625
9 | Identity | Saurabh Bharadwaj | UAE | NI SouthAfrica_Sept_2023 | SailPoint | Architect | Professional Services | 26 | 26 | 0 | 225.3 | 28.1625 | -2.1625 | 2023-11-01 | 2024-04-22 | 2024-12-02 | Signed off
10 | Identity | Prathmesh | India | NI SouthAfrica_Sept_2023 | SailPoint | Engineer | Professional Services | 5 | 5 | 0 | 40 | 5 | 0
11 | Identity | Rakesh Vadnala | UAE | NI SouthAfrica_Sept_2023 | SailPoint | Engineer | Professional Services | 48.5 | 48.5 | 0 | 372.3 | 46.5375 | 1.9625
12 | Identity | Vaishnavi Makarand | India | NI SouthAfrica_Sept_2023 | SailPoint | Engineer | Professional Services | 5.5 | 5.5 | 0 | 32 | 4 | 1.5
13 | Identity | Vamshi | UAE | NI Egypt_Phase 2 | SailPoint | Architect | Professional Services | 50.25 | 45.5 | 4.75 | 394 | 49.25 | 1 | 2023-12-26 | 2024-05-30 | Project officially closed
14 | Identity | Srikant Bavandla | UAE | NI Egypt_Phase 2 | SailPoint | Architect | Professional Services | 10.5 | 5.5 | 5 | 39 | 4.875 | 5.625
15 | Identity | Niraj Joshi | UAE | NI Egypt_Phase 2 | SailPoint | Engineer | Professional Services | 48.25 | 11.5 | 36.75 | 88 | 11 | 37.25
16 | Identity | Rakesh Vadnala | UAE | NI Egypt_Phase 2 | SailPoint | Engineer | Professional Services | 2 | 2 | 0 | 16 | 2 | 0
17 | Identity | Swapnil Deka | UAE | NI Egypt_Phase 2 | SailPoint | Engineer | Professional Services | 4 | 4 | 0 | 32 | 4 | 0
18 | Identity | Karthik NSP | UAE | Airtel - Phase 2 | IIQ | Architect | Professional Services | 120 | 120 | 0 | 1007 | 125.875 | -5.875 | 2023-12-11 | 2024-09-10 | 2024-10-05 | project signed Off
19 | Identity | Amala Sunny | UAE | Airtel - Phase 2 | IIQ/Forgerock | Engineer | Professional Services | 92 | 92 | 0 | 793.18 | 99.1475 | -7.1475
20 | Identity | Preshit Ghode | India | Airtel - Phase 2 | IIQ | Engineer | Professional Services | 91 | 94.5 | -3.5 | 652 | 81.5 | 9.5
21 | Identity | Niraj Joshi | UAE | Airtel - Phase 2 | IIQ | Engineer | Professional Services | 18 | 18 | 0 | 248 | 31 | -13 |  |  |  |  | no chnges made
22 | Identity | Rakesh Vadnala | UAE | Airtel - Phase 2 | IIQ | Engineer | Professional Services | 41 | 41 | 0 | 232 | 29 | 12
23 | Identity | Aishwary Kumar | UAE | Airtel - Phase 2 | IIQ | Engineer | Professional Services | 37 | 46 | -9 | 328 | 41 | -4
24 | Identity | Kanchan Mishra | UAE | Airtel - Phase 2 | Forgerock/SMS OTP | Architect | Professional Services | 146 | 150.95 | -4.95 | 1221 | 152.625 | -6.625
25 | Identity | Shandeep Srinivas | UAE | Airtel - Phase 2 | Forgerock/SMS OTP | Engineer | Professional Services | 90 | 90 | 0 | 790.3 | 98.7875 | -8.7875
26 | Identity | Shandeep Srinivas | UAE | Airtel Phase 2A - Multisite Installation | Forgerock | Engineer | Professional Services | 45 | 17 | 28 | 0 | 0 | 45 | 2024-07-10 | TBD
27 | Identity | Kanchan Mishra | UAE | Airtel Phase 2A - Multisite Installation | Forgerock | Architect | Professional Services | 2 | 2 | 0 | 0 | 0 | 2
28 | Identity | Karthik NSP | UAE | Airtel - Phase 3 | IIQ | Architect | Professional Services | 24 | 0 | 24 | 0 | 0 | 24 | 2025-01-13 | 2028-03-02
29 | Identity | Karthikeyan Subramanian | UAE | Airtel - Phase 3 | IIQ | Architect | Professional Services | 80 | 0 | 80 | 0 | 0 | 80
30 | Identity | Karthik NSP | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 140 | 0 | 140 | 0 | 0 | 140
31 | Identity | Amala Sunny | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 90 | 0 | 90 | 0 | 0 | 90
32 | Identity | Rakesh Vadnala | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 30 | 0 | 30 | 0 | 0 | 30
33 | Identity | Swapnil Deka | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 50 | 0 | 50 | 0 | 0 | 50
34 | Identity | Shilpi | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 129 | 0 | 129 | 0 | 0 | 129
35 | Identity | New Resources 1 | India | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 155 | 0 | 155 | 0 | 0 | 155
36 | Identity | New Resources 2 | India | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 155 | 0 | 155 | 0 | 0 | 155
37 | Identity | Shandeep Srinivas | UAE | Airtel - Phase 3 | IIQ - RBAC | Engineer | Professional Services | 90 | 0 | 90 | 0 | 0 | 90
38 | Identity | Hrushikesh Ubale | India | Airtel - Phase 3 | FAM | Engineer | Professional Services | 22 | 0 | 22 | 0 | 0 | 22 | 2025-01-13 | 2025-02-11
39 | Identity | Kanchan Mishra | UAE | Airtel - Phase 3 | Forgerock | Architect | Professional Services | 90 | 0 | 90 | 0 | 0 | 90 | 2025-01-13 | 2026-05-15
40 | Identity | Kanchan Mishra | UAE | Airtel - Phase 3 | Forgerock | Engineer | Professional Services | 10 | 0 | 10 | 0 | 0 | 10
41 | Identity | Shandeep Srinivas | UAE | Airtel - Phase 3 | Forgerock | Engineer | Professional Services | 90 | 0 | 90 | 0 | 0 | 90
42 | Identity | Amala Sunny | UAE | Airtel - Phase 3 | Forgerock | Engineer | Professional Services | 100 | 0 | 100 | 0 | 0 | 100
43 | Identity | Chaitanya Kulkarni | India | Airtel - Phase 3 | Forgerock | Engineer | Professional Services | 90 | 0 | 90 | 0 | 0 | 90
44 | Identity | Karthikeyan Subramanian | UAE | DMT | Sailpoint | Architect | Professional Services | 143 | 140 | 3 | 721 | 90.125 | 52.875 |  | 2023-10-13 | 2024-11-30 | Received Complete payment
45 | Identity | Infant Ujval Rex | UAE | DMT | Sailpoint | Engineer | Professional Services | 88.75 | 80 | 8.75 | 399.45 | 49.9312 | 38.8188
46 | Identity | Aishwary Kumar | UAE | DMT | Sailpoint | Engineer | Professional Services | 11.25 | 11.25 | 0 | 98 | 12.25 | -1
47 | Identity | Rakesh Vadnala | UAE | DMT | Sailpoint | Engineer | Professional Services | 3 | 3 | 0 | 24 | 3 | 0
48 | Identity | Karthik NSP | UAE | Intigral - Phase 2 | Sailpoint | Architect | Professional Services | 31 | 10 | 21 | 81 | 10.125 | 20.875 | 2024-02-17 | 2024-12-31 | TBD
49 | Identity | Aishwary Kumar | UAE | Intigral - Phase 2 | Sailpoint | Engineer | Professional Services | 49 | 17 | 32 | 139.45 | 17.4312 | 31.5688
50 | Identity | Rushikesh Chaudhari | UAE | Intigral - Phase 2 | SailPoint | Engineer | Professional Services | 32 | 0 | 32 | 32 | 4 | 28
51 | Identity | Saurabh Bharadwaj | UAE | DIB | Sailpoint | Architect | Professional Services | 73 | 87.6 | -14.6 | 519.15 | 64.8937 | 8.1063 | 2022-01-17 | 2022-06-19 | 2024-11-14 | Signed Off
52 | Identity | Swapnil Deka | UAE | DIB | Sailpoint | Engineer | Professional Services | 62 | 59 | 3 | 754.3 | 94.2875 | -32.2875
53 | Identity | Aishwary Kumar | UAE | DIB | Sailpoint | Engineer | Professional Services | 65 | 65 | 0 | 662 | 82.75 | -17.75
54 | Identity | Srikant Bavandla | UAE | Abu Dhabi Media Company | SailPoint | Architect | Professional Services | 74.5 | 54.6 | 19.9 | 1183 | 147.875 | -73.375 | 2023-09-06 | 2024-08-19 | 2024-12-24
55 | Identity | Infant Ujval Rex | UAE | Abu Dhabi Media Company | SailPoint | Engineer | Professional Services | 136.5 | 143.47 | -6.97 | 962.3 | 120.2875 | 16.2125
56 | Identity | Rushikesh Chaudhari | UAE | Abu Dhabi Media Company | SailPoint | Engineer | Professional Services | 139 | 100.9 | 38.1 | 827 | 103.375 | 35.625
57 | Identity | Karthikeyan Subramanian | UAE | Abu Dhabi Media Company | SailPoint | Architect | Professional Services | 51 | 30.6 | 20.4 | 521 | 65.125 | -14.125
58 | Identity | Shandeep Srinivas | UAE | Abu Dhabi Media Company | SailPoint | Engineer | Professional Services | 10 | 11.1 | -1.1 | 87.3 | 10.9125 | -0.9125
59 | Identity | Aishwary Kumar | UAE | Abu Dhabi Media Company | SailPoint | Engineer | Professional Services | 19 | 22 | -3 | 0 | 0 | 19
60 | Identity | Karthik NSP | UAE | Mashreq Phase 2 | SailPoint | Architect | Professional Services | 26 | 17 | 9 | 348.3 | 43.5375 | -17.5375 | 2023-10-15 | 2024-02-26 | TBD | Received Complete payment
61 | Identity | Shandeep Srinivas | UAE | Mashreq Phase 2 | SailPoint | Engineer | Professional Services | 29 | 29 | 0 | 332.3 | 41.5375 | -12.5375
62 | Identity | Amala Sunny | UAE | Mashreq Phase 2 | SailPoint | Engineer | Professional Services | 9 | 3 | 6 | 42 | 5.25 | 3.75
63 | Identity | Shilpi | UAE | Mashreq Phase 2 | SailPoint | Engineer | Professional Services | 22 | 8 | 14 | 176 | 22 | 0
64 | Identity | Vaishnavi Makarand | India | Mashreq Phase 2 | SailPoint | Engineer | Professional Services | 14 | 14 | 0 | 56 | 7 | 7
65 | Identity | Sandeep Dwivedi | UAE | AXA_Gulf Insurance Group | SailPoint | Architect | Professional Services | 0 | 0 | 0 | 15 | 1.875 | -1.875 | Signed off |  |  | Received Complete payment
66 | Identity | Karthik NSP | UAE | AXA_Gulf Insurance Group | SailPoint | Engineer | Professional Services | 8 | 0.5 | 7.5 | 0 | 0 | 8
67 | Identity | Rushikesh Chaudhari | UAE | AXA_Gulf Insurance Group | SailPoint | Engineer | Professional Services | 2 | 2 | 0 | 242.15 | 30.2688 | -28.2688
68 | Identity | Vamshi | UAE | AXA_Gulf Insurance Group – Upgrade | SailPoint | Architect | Professional Services | 10 | 10 | 0 | 120 | 15 | -5 | Signed off |  |  | Received Complete payment
69 | Identity | Rushikesh Chaudhari | UAE | AXA_Gulf Insurance Group – Upgrade | SailPoint | Engineer | Professional Services | 10 | 8 | 2 | 242.15 | 30.2688 | -20.2688
70 | Identity | Preshit Ghode | India | AXA_Gulf Insurance Group – Upgrade | SailPoint | Engineer | Professional Services | 13 | 13 | 0 | 140.3 | 17.5375 | -4.5375
71 | Identity | Vamshi | UAE | Azaq_kalaam | SailPoint | Architect | Professional Services | 83 | 41.6 | 41.4 | 560 | 70 | 13 | 2024-04-29 | 2025-02-04 | 2025-06-05
72 | Identity | Niraj Joshi | UAE | Azaq_kalaam | SailPoint | Engineer | Professional Services | 65 | 79.7 | -14.7 | 288 | 36 | 29
73 | Identity | Rakesh Vadnala | UAE | Azaq_kalaam | SailPoint | Engineer | Professional Services | 3 | 3 | 0 | 24 | 3 | 0
74 | Identity | Shandeep Srinivas | UAE | Azaq_kalaam | SailPoint | Engineer | Professional Services | 5 | 5 | 0 | 81 | 10.125 | -5.125
75 | Identity | Sandeep Dwivedi | UAE | Ni UAE FAM Upgrade | SailPoint | Technical Manager | Professional Services | 2 | 0 | 2 | 14 | 1.75 | 0.25 | 2024-07-03 | 2024-07-30
76 | Identity | Karthik NSP | UAE | Ni UAE FAM Upgrade | SailPoint | Sr Consultant | Professional Services | 2 | 0 | 2 | 24 | 3 | -1
77 | Identity | Preshit Ghode | India | Ni UAE FAM Upgrade | SailPoint | Engineer | Professional Services | 17 | 15 | 2 | 138 | 17.25 | -0.25
78 | Identity | Karthikeyan Subramanian | UAE | Mashreq Phase 3 | SailPoint | Architect | Professional Services | 6 | 4 | 2 | 46 | 5.75 | 0.25 | 2024-07-08 | 2025-01-17
79 | Identity | Shilpi | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 54 | 54 | 0 | 461 | 57.625 | -3.625
80 | Identity | Swapnil Deka | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 48 | 48 | 0 | 200 | 25 | 23
81 | Identity | Shandeep Srinivas | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 32 | 37 | -5 | 336 | 42 | -10
82 | Identity | Amala Sunny | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 54 | 54 | 0 | 312 | 39 | 15
83 | Identity | Karthik NSP | UAE | Mashreq Phase 3 | SailPoint | Architect | Professional Services | 22 | 22 | 0 | 352 | 44 | -22
84 | Identity | Saurabh Bharadwaj | UAE | Mashreq Phase 3 | SailPoint | Architect | Professional Services | 11 | 3 | 8 | 0 | 0 | 11
85 | Identity | Karthik NSP | UAE | Mashreq Phase 3 | SailPoint | Sr Consultant | Professional Services | 73 | 40 | 33 | 352 | 44 | 29 |  |  |  |  | 41 - 30 required , rest can be transferred----(Mashreq Phase3a -Fieldglass)
86 | Identity | Harsh Aru | India | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 17 | 17 | 0 | 0 | 0 | 17
87 | Identity | Rakesh Vadnala | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 40 | 10 | 30 | 144 | 18 | 22
88 | Identity | Preshit Ghode | India | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 11 | 8 | 3 | 64 | 8 | 3
89 | Identity | Shruti C | India | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 17 | 17 | 0 | 0 | 0 | 17
90 | Identity | Karthik NSP | UAE | Mashreq Fieldglass | SailPoint | Architect | Professional Services | 13 | 13 | 0 | 0 | 0 | 13 | 2024-11-25 | 2025-01-17
91 | Identity | Srikant Bavandla | UAE | Mashreq Fieldglass | sailpoint | Engineer | Professional Services | 10 | 10 | 0 | 0 | 0 | 10
92 | Identity | Shandeep Srinivas | UAE | Mashreq Fieldglass | SailPoint | Engineer | Professional Services | 15 | 15 | 0 | 0 | 0 | 15
93 | Identity | Srikant Bavandla | UAE | Tawazun | SailPoint | Architect | Professional Services | 41.5 | 39.6 | 1.9 | 324 | 40.5 | 1 | 2024-07-15 | 2025-01-27 |  | 2nd Milestone Completed
94 | Identity | Niraj Joshi | UAE | Tawazun | SailPoint | Engineer | Professional Services | 14 | 7.7 | 6.3 | 48 | 6 | 8
95 | Identity | Vaishnavi Makarand | India | Tawazun | SailPoint | Engineer | Professional Services | 64 | 61 | 3 | 303 | 37.875 | 26.125
96 | Identity | Saurabh Bharadwaj | UAE | ADCB Phase 2 | SailPoint | Architect | Professional Services | 69 | 1 | 68 | 0 | 1 | 68 | 2024-07-15
97 | Identity | Shilpi | UAE | ADCB Phase 2 | SailPoint | Engineer | Professional Services | 50 | 1 | 49 | 0 | 1 | 49
98 | Identity | Rushikesh Chaudhari | UAE | ADCB Phase 2 | SailPoint | Engineer | Professional Services | 30 | 0 | 30 | 0 | 0 | 30
99 | Identity | Swapnil Deka | UAE | ADCB Phase 2 | SailPoint | Engineer | Professional Services | 21 | 0 | 21 | 0 | 0 | 21
100 | Identity | Saurabh Bharadwaj | UAE | EDC | SailPoint | Architect | Professional Services | 50 | 50 | 0 | 0 | 35 | 15 | Signed off |  | Received complete payment
101 | Identity | Shilpi | UAE | EDC | SailPoint | Engineer | Professional Services | 83.5 | 80 | 3.5 | 0 | 46 | 37.5
102 | Identity | Niraj Joshi | UAE | EDC | SailPoint | Engineer | Professional Services | 17.5 | 17.5 | 0 | 0 | 41 | -23.5
103 | Identity | Vamshi | UAE | SIB | IIQ- Upgrade 8.1 to 8.4 P | Architect | Professional Services | 11 | 4 | 7 | 0 | 0 | 11 | 2024-10-03 | 2025-01-10 |  | Kick-off Done
104 | Identity | Niraj Joshi | UAE | SIB | IIQ- Upgrade 8.1 to 8.4 P | Engineer | Professional Services | 11 | 4 | 7 | 0 | 0 | 11
105 | Identity | Preshit Ghode | UAE | SIB | IIQ- Upgrade 8.1 to 8.4 P | Engineer | Professional Services | 17 | 0.5 | 16.5 | 0 | 0 | 17
106 | Identity | Sandeep Dwivedi | UAE | SIB | FAM - Upgrade | Architect | Professional Services | 4 | 2 | 2 | 0 | 0 | 4
107 | Identity | Vamshi | UAE | ZAND Bank | ZAND - SailPoint Enhancement | Technical Consultant | Professional Services | 13 | 13 | 0 | 104 | 13 | 0 | 2024-09-30 | 2024-11-01 |  | signed off
108 | Identity | Vamshi | UAE | ZAND Bank | ZAND - SailPoint Enhancement | Architect | Professional Services | 5 | 5 | 0 | 40 | 5 | 0
109 | Identity | Karthikeyan Subramanian | UAE | QIB | QIB Phase 3 SailPoint | Architect | Professional Services | 33 | 8.1 | 24.9 | 128 | 16 | 17 | 2023-04-01 | 2023-07-30 |  | On Hold
110 | Identity | Rakesh Vadnala | UAE | QIB | QIB Phase 3 SailPoint | Engineer | Professional Services | 2 | 0 | 2 | 0 | 0 | 2
111 | Identity | Shilpi | UAE | QIB | QIB Phase 3 SailPoint | Engineer | Professional Services | 45 | 12 | 33 | 113 | 14.125 | 30.875
112 | Identity | Saurabh Bharadwaj | UAE | ADCB - SAPsuccessfactor and CR | SAP Success Factor Enhancement | Architect | Professional Services | 25 | 25 | 0 | 320 | 40 | -15 | 2024-09-04 | 2024-10-30 | 2024-12-30
113 | Identity | Rakesh Vadnala | UAE | ADCB - SAPsuccessfactor and CR | SAP Success Factor Enhancement | Engineer | Professional Services | 25 | 25 | 0 | 316.02 | 39.5025 | -14.5025
114 | Identity | Rushikesh Chaudhari | UAE | ADCB - SAPsuccessfactor and CR | SAP Success Factor Enhancement | Engineer | Professional Services | 5 | 5 | 0 | 317 | 39.625 | -34.625
115 | Identity | Kavin | UAE | Presidential Flights | PF Cyberark | Sr. Technical Consultant | Professional Services | 2 | 2 | 0 |  |  |  | 2024-10-07 | 2024-12-11 | Signed off
116 | Identity | Shashant | India | Presidential Flights | PF Cyberark | Sr. Technical Consultant | Professional Services | 2 | 2 | 0
117 | Identity | Rakesh Vadnala | UAE | Katim | Katim LLC | Technical Consultant | Professional Services | 15 | 15 | 0
118 | Identity | Sandeep Dwivedi | UAE | SIB FAM | SailPoint | Tech-ops Manager | Professional Services | 19 | 3 | 16 |  |  |  | 2024-06-21 | 2025-06-20
119 | Identity | Preshit ghode | India | SIB FAM | SailPoint | Consultant | Professional Services | 2 | 0 | 2 |  |  |  | 2024-06-21 | 2025-06-20
120 | Identity | Vaishnavi Makarand | India | DIB Support | SailPoint | Consultant | Support | 10 | 5 | 5 |  |  |  | 2024-12-31 | 2025-12-30
121 | Identity | Sandeep Dwivedi | UAE | DIB Support | SailPoint | Tech-ops Manager | Support | 5 | 4 | 1 |  |  |  | 2024-12-31 | 2025-12-30
122 | Identity | Hrushikesh Ubale | India | SIB Support | SailPoint | Consultant | Support | 17 | 14 | 3 |  |  |  | 2024-06-21 | 2025-06-20
123 | Identity | Sandeep Dwivedi | UAE | SIB Support | SailPoint | Tech-ops Manager | Support | 8 | 6 | 2 |  |  |  | 2024-06-21 | 2025-06-20
124 | Identity | Preshit Ghode | India | AXA Support | SailPoint | Consultant | Support | 8 | 8 | 0 |  |  |  | 2024-11-05 | 2025-11-04
125 | Identity | Sandeep Dwivedi | UAE | AXA Support | SailPoint | Tech-ops Manager | Support | 27 | 9 | 18 |  |  |  | 2024-11-05 | 2025-11-04
126 | Identity | Rushikesh Chaudhari | UAE | AXA Support | SailPoint | Consultant | Support | 2 | 2 | 0 |  |  |  | 2024-11-05 | 2025-11-04
127 | Identity | Sandeep Dwivedi | UAE | Tawazun Support | SailPoint | Tech-ops Manager | Support | 1 | 0 | 1 |  |  |  | 2024-09-30 | 2025-09-29
128 | Identity | Niraj Joshi | UAE | Tawazun Support | SailPoint | Consultant | Support | 2 | 1 | 1 |  |  |  | 2024-09-30 | 2025-09-29
129 | Identity | Rakesh Vadnala | UAE | Tawazun Support | SailPoint | Consultant | Support | 2 | 2 | 0 |  |  |  | 2024-09-30 | 2025-09-29
130 | Identity | Vaishnavi Makarand | India | Tawazun Support | SailPoint | Consultant | Support | 2 | 2 | 0 |  |  |  | 2024-09-30 | 2025-09-29
131 | Identity | Srikant Bavandla | UAE | Tawazun Support | SailPoint | Architect | Support | 1 | 1 | 0 |  |  |  | 2024-09-30 | 2025-09-29
132 | Identity | Sandeep Dwivedi | UAE | NI Egypt- Log movement | SailPoint | Tech-ops Manager | Support | 1 | 1 | 0
133 | Identity | Preshit Ghode | India | NI Egypt- Log movement | SailPoint | Consultant | Support | 5 | 5 | 0
134 | Identity | Hrushikesh Ubale | India | PHCC Support | SailPoint | Consultant | Support | 15 | 8 | 7 |  |  |  | 2023-03-02 | 2026-03-02
135 | Identity | Sandeep Dwivedi | UAE | PHCC Support | SailPoint | Tech-ops Manager | Support | 4 | 0 | 4 |  |  |  | 2023-03-02 | 2026-03-02
136 | Identity | Shashant | UAE | Sukoon Insurance (24-25) | Cyberark | Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 2024-11-24 | 2025-11-24
137 | Identity | Kavin | UAE | Sukoon Insurance (24-25) | Cyberark | Sr. Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 2024-11-24 | 2025-11-24
138 | Identity | Sandeep Dwivedi | UAE | ADJD | Cyberark | Tech-ops Manager | Support | 1 | 0 | 1 |  |  |  | 2023-09-12 | 2024-09-11
139 | Identity | Niraj Joshi | UAE | ADMC Support | SailPoint | Technical Consultant | Support | 208 | 0 | 208 |  |  |  | Not Started | Not Started
140 | Identity | Sandeep Dwivedi | UAE | DMT Support | SailPoint | Tech-ops Manager | Support | 5 | 0 | 5 |  |  |  | 2024-11-01 | 2025-10-31
141 | Identity | Rushikesh Chaudhari | UAE | DMT Support | SailPoint | Engineer | Support | 14 | 0 | 14 |  |  |  | 2024-11-01 | 2025-10-31
142 | Identity | Rushikesh Chaudhari | UAE | ADCB Phase 2 Support | ADCB | Engineer | Support | 30 | 17 | 13 |  |  |  | 2024-11-01 | 2024-10-31
143 | Identity | Kavin | UAE | OQ trading Support | OQ Trading CyberArk | Sr. Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 10-Aug-24 | 9-Aug-25
144 | Identity | Shashant | India | OQ trading Support | OQ Trading CyberArk | Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 10-Aug-24 | 9-Aug-25
145 | Identity | Kavin | UAE | OQ trading Support | OQ Trading CyberArk | Sr. Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 2024-11-24 | 2025-11-23
146 | Identity | Shashant | India | OQ trading Support | OQ Trading CyberArk | Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 2024-11-24 | 2025-11-23
147 | Identity | Kavin | UAE | Adek Support (Unlimited tickets) | ADEK CyberArk | Sr. Technical Consultant | Support | 14 | 0 | 14
148 | Identity | Shashant | India | Adek Support (Unlimited tickets) | ADEK CyberArk | Technical Consultant | Support | 50 | 0 | 50
149 | Identity |  |  | Intigral SailPoint Support | Intigral |  | Support | 6 | 0 | 6
150 | Identity | Shilpi | UAE | Mashreq Support - 5 month | Sailpoint | Engineer | Support | 7 | 7 | 0 | [6 empty] | Started in November 2024
151 | Identity | Amala Sunny | UAE | Mashreq Support - 5 month | Sailpoint | Engineer | Support | 8 | 8 | 0
152 | Identity | Preshit Ghode | India | Mashreq Support - 5 month | SailPoint | Engineer | Support | 95 | 0 | 95 | [6 empty] | Started in November 2024
153 | Identity | Kavin | UAE | Presidential Flights | PF Cyberark | Technical Consultant | Support | 10 | 0 | 10 |  |  |  | 2024-12-11 | 2025-12-10
154 | Identity | Kavin | UAE | Sukoon Insurance | Sukoon Insurance CyberArk (23-24) | Sr. Technical Consultant | Support | 8 | 3.4 | 4.6 |  |  |  | 2023-11-24 | 2024-11-23
155 | Identity | Shashant | India | Sukoon Insurance | Sukoon Insurance CyberArk (23-24) | Technical Consultant | Support | 8 | 3.8 | 4.2 |  |  |  | 2023-11-24 | 2024-11-23
156 | Identity | Kavin | UAE | Damac | Damac CyberArk | Sr. Technical Consultant | Support | 15 | 0.5 | 14.5 |  |  |  | 2023-05-12 | 2025-05-11
157 | Identity | Shashant | India | Damac | Damac CyberArk | Technical Consultant | Support | 15 | 6.3 | 8.7 |  |  |  | 2023-05-12 | 2025-05-11
158 | Identity | Shashant | India | ADJD | ADJD CyberArk | Technical Consultant | Support | 3 | 1.3 | 1.7 |  |  |  | 2023-09-11 | 2024-09-11
159 | Identity | Kavin | UAE | ADJD | ADJD CyberArk | Sr. Technical Consultant | Support | 3 | 0.7 | 2.3 |  |  |  | 2023-09-11 | 2024-09-11
160 | Identity | Sandeep Dwivedi | UAE | Carrefour (24-25) | SailPoint | Tech-ops Manager | Support | 4 | 4 | 0
161 | Identity | Rakesh Vadnala | UAE | Carrefour (24-25) | SailPoint | Consultant | Support | 7 | 7 | 0
162 | Identity | Hrushikesh Ubale | India | Carrefour (24-25) | SailPoint | Consultant | Support | 7 | 7 | 0
163 | Identity | Sandeep Dwivedi | UAE | NI Support | SailPoint | Tech-ops Manager | Support | 4 | 4 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
164 | Identity | Kanchan Mishra | UAE | NI Support | SailPoint | Senior Architect | Support | 6 | 6 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
165 | Identity | Swapnil Deka | UAE | NI Support | SailPoint | Consultant | Support | 54 | 54 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
166 | Identity | Saurabh Bharadwaj | UAE | NI Support | SailPoint | Consultant | Support | 0.5 | 0.5 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
167 | Identity | Rakesh Vadnala | UAE | NI Support | SailPoint | Consultant | Support | 0.5 | 0.5 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
168 | Identity | Shilpi | UAE | EDC | SailPoint | Technical Consultant | Support | 10 | 0 | 10 | [6 empty] | 1 Year = Remote Shared Managed Support (8/5). The Assigned resource should be handling min 2 similar customer's.
169 | Identity | Rushikesh Chaudhari | UAE | AXA CR Support | SailPoint | Consultant | Support | 2 | 2 | 0
170 | Identity | Karthik NSP | UAE | AXA CR Support | SailPoint | Consultant | Support | 8 | 8 | 0
171 | Identity | Hrushikesh Ubale | India | Aldar Support | SailPoint | Consultant | Support | 80 | 7 | 73 |  |  |  | 2024-07-13 | 2025-07-30
172 | Identity | Sandeep Dwivedi | UAE | Aldar Support | SailPoint | Tech-ops Manager | Support | 16 | 4 | 12
173 | Identity | Hrushikesh Ubale | India | Aldar Support 200 hours Support | SailPoint | Consultant | Support | 25 | 25 | 0
174 | Identity | Sandeep Dwivedi | UAE | NI -UAE FAM Upgrade | SailPoint | Tech-ops Manager | Support | 5 | 5 | 0
175 | Identity | Karthik NSP | UAE | NI -UAE FAM Upgrade | SailPoint | Tech-ops Manager | Support | 5 | 5 | 0
176 | Identity | Preshit Ghode | India | NI -UAE FAM Upgrade | SailPoint | Consultant | Support | 12 | 12 | 0
177 | Identity | Kavin | UAE | ADNEC | ADNEC Cyberark | Sr. Technical Consultant | Support | 2 | 2 | 0
178 | Identity | Shashant | UAE | ADNEC | ADNEC Cyberark | Technical Consultant | Support | 2 | 2 | 0
179 | Identity | Preshit Ghode | India | AXA CR | SailPoint | Consultant | Professional Services | 2 | 2 | 0
180 | Identity | Sandeep Dwivedi | UAE | AXA CR | SailPoint | Tech-ops Manager | Professional Services | 1 | 1 | 0
181 | Identity | Rushikesh Chaudhari | UAE | AXA CR | SailPoint | Consultant | Professional Services | 30 | 30 | 0
182 | Identity | Karthik NSP | UAE | AXA CR | SailPoint | Senior Consultant | Professional Services | 35 | 35 | 0
183 | Identity | Kavin | UAE | ADEK PAM | ADEK CyberArk | Sr. Technical Consultant | Professional Services | 9.2 | 10 | -0.8 |  | 7.25 | 1.95 |  |  | 2024-12-13
184 | Identity | Shashant | India | ADEK PAM | ADEK CyberArk | Technical Consultant | Professional Services | 25.8 | 31.2 | -5.4 |  | 26.46 | -0.66
185 | Identity | Kavin | UAE | OQ Trading PAM | OQ Trading CyberArk | Sr. Technical Consultant | Professional Services | 6 | 1.5 | 4.5 |  | 1 | 5 |  |  | Received conditional sign off
186 | Identity | Shashant | India | OQ Trading PAM | OQ Trading CyberArk | Technical Consultant | Professional Services | 14 | 6.5 | 7.5 |  | 5 | 9
187 | Identity | Kavin | UAE | ADNEC PAM | ADNEC CyberArk | Sr. Technical Consultant | Professional Services | 7 | 24 | -17 |  | 24.31 | -17.31 |  |  | Signed off
188 | Identity | Shashant | India | ADNEC PAM | ADNEC CyberArk | Technical Consultant | Professional Services | 7 | 21 | -14 |  | 19.31 | -12.31
189 | Identity | Kavin | UAE | ADNEC PAM | ADNEC CyberArk 3 months onsite engagement | Sr. Technical Consultant | Professional Services | 66 | 66 | 0 |  | 53.87 | 12.13
190 | Identity | Kavin | UAE | DOH PAM | DOH CyberArk | Sr. Technical Consultant | Professional Services | 15 | 15 | 0 |  | 2.75 | 12.25 |  |  | Signed off
191 | Identity | Shashant | India | DOH PAM | DOH CyberArk | Technical Consultant | Professional Services | 23 | 21 | 2 |  | 15.5 | 7.5
192 | Identity | Shashant | India | ZMI PAM | ZMI - P Cloud | Technical Consultant | Professional Services | 17.5 | 17.5 | 0 |  | 9.8 | 7.7 |  |  | Signed off
193 | Identity | Kavin | UAE | ZMI PAM | ZMI - P Cloud | Sr. Technical Consultant | Professional Services | 2.5 | 2.5 | 0 |  | 0 | 2.5
194 | Identity | Shashant | India | Nextcare PAM | Nextcare - BT | Technical Consultant | Professional Services | 10 | 0.05 | 9.95 |  | 0 | 10
195 | Identity | Kavin | UAE | Nextcare PAM | Nextcare - BT | Sr. Technical Consultant | Professional Services | 19 | 0.05 | 18.95 |  | 0 | 19
196 | Identity | Kavin | UAE | Presidential Flights | PF Cyberark | Sr. Technical Consultant | Professional Services | 2 | 2 | 0 |  |  |  | 2024-10-07 | 2024-12-11 | Signed off
197 | Identity | Shashant | India | Presidential Flights | PF Cyberark | Sr. Technical Consultant | Professional Services | 2 | 2 | 0
Note on I45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requirement for onboarding 3rd party datasouce (Bayanty) Reply: Added 12 days
Note on I137: Bhushan Sisode: IAM & PAM - 16 hrs NOT IAM & AXA - 8 hrs
Note on I138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to Discuss
Note on I140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 Year (2 days in a week onsite )
Note on F144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AMC started after PS conditional sign off
Note on F146: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AMC new renewal which came in Nov 2024

## Resource Analysis
Row Labels | Sum of Allocated Billed Days 2025 | Sum of Utilized Billed Days 2025(Project plan) | Sum of Remaining Billed Days 2025 (Project plan)
<Noida_l2_2 | 264 | 0 | 264
<Noida_L3_1> | 152 | 0 | 152
<Noida_L3_2> | 132 | 0 | 132
Ajit Rathod | 264 | 44 | 227
Amala Sunny | 110 | 74 | 36
Bharath | 5 | 3 | 2
Chaitanya Kulkarni | 323.42 | 80.5 | 242.92
Harsh Aru | 0 | 0 | 0
Hitesh Sindhi | 120 | 17.5 | 102.5
Hrushikesh Ubale | 247 | 86 | 161
Infant Ujval Rex | 14 | 7 | 7
Kanchan Mishra | 141.25 | 32 | 109.25
Karina Singh | 154 | 0 | 154
Karthik NSP | 282 | 44 | 238
Karthikeyan Subramanian | 259.4 | 80.4875 | 178.9125
Kavin | 101.45 | 9 | 92.45
Mahipal Jadhav | 264 | 44 | 227
New Resources 2 | 155 | 0 | 155
Niraj Joshi | 137.8 | 48.8 | 89
Preshit Ghode | 80 | 78 | 2
Priyanka Jagnade | 264 | 44 | 227
Rakesh Vadnala | 224.5 | 39.125 | 185.375
Resource | 12 | 0.2 | 11.8
Rushikesh | 0.5 | 0.5
Rushikesh Chaudhari | 155.5 | 20 | 135.5
Rushikesh Jadhav | 209 | 79 | 336
Sandeep | 2 | 2 | 0
Sandeep D | 12 | 12 | 0
Sandeep Dwivedi | 6 | 6 | 0
Saurabh Bharadwaj | 89 | 6.2 | 82.8
Shandeep Srinivas | 208.525 | 33 | 402.525
Shashant | 215 | 34 | 181
Shilpi | 301 | 63 | 238
Shruti C | 199 | 39 | 160
Srikant Bavandla | 29.75 | 27 | 2.75
Suraj Kalamkar | 264 | 44 | 227
Swapnil Deka | 125 | 19.5 | 105.5
Vaishnavi Makarand | 192 | 5 | 187
Vamshi | 61 | 11.05 | 49.95
Vendor (Shifra) | 0 | 0 | 0
Vinod | 232 | 76 | 156
(blank)
Grand Total | 6008.095 | 1208.8625 | 5260.2325

## Sheet1 (hidden)
Row Labels | Sum of Remaining Billed Days 2025 (Project plan)
<Noida_l2_2 | 264
<Noida_L3_1> | 152
<Noida_L3_2> | 132
Ajit Rathod | 227
Amala Sunny | 36
Bharath | 2
Chaitanya Kulkarni | 242.92
Harsh Aru | 0
Hitesh Sindhi | 102.5
Hrushikesh Ubale | 161
Infant Ujval Rex | 7
Kanchan Mishra | 109.25
Karina Singh | 154
Karthik NSP | 238
Karthikeyan Subramanian | 178.9125
Kavin | 26
Kavin | 66.45
Mahipal Jadhav | 227
New Resources 2 | 155
Niraj Joshi | 89
Preshit Ghode | 2
Priyanka Jagnade | 227
Rakesh Vadnala | 185.375
Resource | 11.8
Rushikesh
Rushikesh Chaudhari | 135.5
Rushikesh Jadhav | 336
Sandeep | 0
Sandeep D | 0
Sandeep Dwivedi | 0
Saurabh Bharadwaj | 82.8
Shandeep Srinivas | 402.525
Shashant | 181
Shilpi | 238
Shruti C | 160
Srikant Bavandla | 2.75
Suraj Kalamkar | 227
Swapnil Deka | 105.5
Vaishnavi Makarand | 187
Vamshi | 49.95
Vendor (Shifra) | 0
Vinod | 156
(blank)
Grand Total | 5260.2325

## Sheet2 (hidden)
Row Labels | Sum of Remaining Billed Days 2025 (Project plan)
<Noida_l2_2 | 264
<Noida_L3_1> | 152
<Noida_L3_2> | 132
Ajit Rathod | 227
Amala Sunny | 36
Bharath | 2
Chaitanya Kulkarni | 242.92
Harsh Aru | 0
Hitesh Sindhi | 102.5
Hrushikesh Ubale | 161
Infant Ujval Rex | 7
Kanchan Mishra | 109.25
Karina Singh | 154
Karthik NSP | 238
Karthikeyan Subramanian | 178.9125
Kavin | 26
Kavin | 66.45
Mahipal Jadhav | 227
New Resources 2 | 155
Niraj Joshi | 89
Preshit Ghode | 2
Priyanka Jagnade | 227
Rakesh Vadnala | 185.375
Resource | 11.8
Rushikesh
Rushikesh Chaudhari | 135.5
Rushikesh Jadhav | 336
Sandeep | 0
Sandeep D | 0
Sandeep Dwivedi | 0
Saurabh Bharadwaj | 82.8
Shandeep Srinivas | 402.525
Shashant | 181
Shilpi | 238
Shruti C | 160
Srikant Bavandla | 2.75
Suraj Kalamkar | 227
Swapnil Deka | 105.5
Vaishnavi Makarand | 187
Vamshi | 49.95
Vendor (Shifra) | 0
Vinod | 156
(blank)
Grand Total | 5260.2325

## Resource Analysis_Extra (hidden)
Row Labels | Sum of Utilized Billed Days(Project plan)2025
Karthik NSP | 5
Preshit Ghode | 8
Sandeep Dwivedi | 6
Grand Total | 19

## Billed_2025
Department | Resource | Location | Customer Name | Billing Status | Project Name | Role | Engagement Type | Allocated Billed Days | Utilized Billed Days 2024(Project plan) | Allocated Billed Days 2025 | Utilize Days 2025(PP Cal) | Utilized Billed Days 2025(Project plan) | Remaining Billed Days 2025 (Project plan) | Utilized Billed hrs (Zoho) | Utilized Billed days 2025 (Zoho) | Remaining Billed Days 2025 (Zoho) | Project Start Date | Project End Date | Revised End Date | Comments
Identity | Karthikeyan Subramanian | UAE | DOHA Bank | Hold | SailPoint | Architect | Professional Services | 109.5 | 0 | 109.5 | 246.3 | 30.7875 | 78.7125 | 24 | 3 | 106.5 | 2024-02-22 | 2024-10-30 | TBD
Identity | Rakesh Vadnala | UAE | DOHA Bank | Hold | SailPoint | Engineer | Professional Services | 34.5 | 0 | 34.5 | 209 | 26.125 | 8.375 | 0 | 0 | 34.5 | 2024-02-22 | 2024-10-30 |  | Full Payment Completed
Identity | Vaishnavi Makarand | India | DOHA Bank | Hold | SailPoint | Engineer | Professional Services | 14 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 14 | 2024-02-22 | 2024-10-30
Identity | Kanchan Mishra | UAE | NIJordan_Sept_2023 | Active | SailPoint | Architect | Professional Services | 22 | 22 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2023-10-19 | 2024-07-30
Identity | Srikant Bavandla | UAE | NIJordan_Sept_2023 | Active | SailPoint | Architect | Professional Services | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2023-10-19 | TBD
Identity | Vaishnavi Makarand | India | NIJordan_Sept_2023 | Active | SailPoint | Engineer | Professional Services | 17 | 17 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2023-10-19
Identity | Swapnil Deka | UAE | NIJordan_Sept_2023 | Active | SailPoint | Engineer | Professional Services | 35 | 31 | 4 |  | 1.5 | 2.5 | 32 | 4 | 0 | 2023-10-19 | TBD
Identity | Shandeep Srinivas | UAE | Airtel Phase 2A - Multisite Installation | Active | Forgerock | Engineer | Professional Services | 26 | 1.975 | 23.025 |  | 9 | 14.025 | 264 | 33 | -9.975 | 2025-01-13 | 2028-03-02
Identity | Chaitanya Kulkarni | India | Airtel Phase 2A - Multisite Installation | Active | Forgerock | Engineer | Professional Services | 10 | 10 | 2 |  | 2 | 0 | 4 | 0.5 | 1.5 | 2025-01-13 | 2028-03-02
Identity | Kanchan Mishra | UAE | Airtel Phase 2A - Multisite Installation | Active | Forgerock | Architect | Professional Services | 11 | 1.25 | 8.75 |  | 4.5 | 4.25 | 8 | 1 | 7.75 | 2025-01-13 | 2028-03-02
Identity | Karthik NSP | UAE | Airtel - Phase 3 | Active | IIQ | Architect | Professional Services | 24 | 0 | 24 |  | 24 | 0 | 192 | 24 | 0 | 2025-01-13 | 2028-03-02
Identity | Karthikeyan Subramanian | UAE | Airtel - Phase 3 | Active | IIQ | Architect | Professional Services | 80 | 0 | 80 |  | 8 | 72 | 8 | 1 | 79 | 2025-01-13 | 2028-03-02
Identity | Karthik NSP | UAE | Airtel - Phase 3 | Active | IIQ | Engineer | Professional Services | 140 | 0 | 140 |  | 10 | 130 | 0 | 0 | 140 | 2025-01-13 | 2028-03-02
Identity | Rakesh Vadnala | UAE | Airtel - Phase 3 | Active | IIQ | Engineer | Professional Services | 90 | 0 | 120 |  | 5 | 115 | 34 | 4.25 | 115.75 | 2025-01-13 | 2028-03-02 |  |  | IIQ - 515
Identity | Swapnil Deka | UAE | NIJordan_Sept_2023 | Active | SailPoint | Technical Consultant | Support |  |  | 40 |  | 5 | 35 | 0 |  |  |  | 2028-03-02
Identity | Swapnil Deka | UAE | Airtel - Phase 3 | Active | IIQ | Engineer | Professional Services | 50 | 0 | 50 |  | 3 | 47 | 24 | 3 | 47 | 2025-01-13 | 2028-03-02
Identity | Shilpi | UAE | Airtel - Phase 3 | Active | IIQ | Engineer | Professional Services | 129 | 0 | 129 |  | 3 | 126 | 0 | 0 | 129 | 2025-01-13 | 2028-03-02
Identity | Vaishnavi Makarand | India | Airtel - Phase 3 | Active | IIQ | Engineer | Professional Services | 155 | 0 | 155 |  | 4 | 151 | 0 | 0 | 155 | 2025-01-13 | 2028-03-02
Identity | New Resources 2 | India | Airtel - Phase 3 | Active | IIQ | Engineer | Professional Services | 155 | 0 | 155 |  | 0 | 155 | 0 | 0 | 155 | 2025-01-13 | 2028-03-02
Identity | Shandeep Srinivas | UAE | Airtel - Phase 3 | Active | IIQ - RBAC | Engineer | Professional Services | 90 | 0 | 90 |  | 8 | 82 | 0 | 0 | 90 | 2025-01-13 | 2028-03-02
Identity | Hrushikesh Ubale | India | Airtel - Phase 3 | Active | FAM | Engineer | Professional Services | 22 | 0 | 22 |  | 0 | 22 | 0 | 0 | 22 | 2025-01-13 | 2028-03-02
Identity | Kanchan Mishra | UAE | Airtel - Phase 3 | Active | Forgerock | Architect | Professional Services | 90 | 3 | 87 |  | 21 | 66 | 133 | 16.625 | 70.375 | 2025-01-13 | 2028-03-02
Identity | Kanchan Mishra | UAE | Airtel - Phase 3 | Active | Forgerock | Engineer | Professional Services | 10 | 0 | 10 |  | 5 | 5 | 0 | 0 | 10 | 2025-01-13 | 2028-03-02
Identity | Shandeep Srinivas | UAE | Airtel - Phase 3 | Active | Forgerock | Engineer | Professional Services | 90 | 6 | 84 |  | 6 | 78 | 136 | 17 | 67 | 2025-01-13 | 2024-11-30
Identity | Chaitanya Kulkarni | UAE | Airtel - Phase 3 | Active | Forgerock | Engineer | Professional Services | 100 | 0 | 189.42 |  | 4.5 | 184.92 | 20 | 2.5 | 186.92 | 2025-01-13 | 2024-11-30
Identity | Karthikeyan Subramanian | UAE | DMT | Active | Sailpoint | Architect | Professional Services | 143 | 143 | 0 |  | 0 | 0 | 85 | 10.625 | -10.625 | 2023-10-13 | 2024-12-31 | TBD
Identity | Infant Ujval Rex | UAE | DMT | Active | Sailpoint | Engineer | Professional Services | 88.75 | 89 | 5 |  | 5 | 0 | 184 | 23 | -18 | 2023-10-13 | 2024-12-31
Identity | Rakesh Vadnala | UAE | DMT | Active | Sailpoint | Engineer | Professional Services | 3 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2023-10-13 | 2024-08-19 | 2024-12-24
Identity | Karthik NSP | UAE | Intigral - Phase 2 | Active | Sailpoint | Architect | Professional Services | 63 | 10 | 53 |  | 0 | 53 | 0 | 0 | 53 | 2024-02-17 | 2024-08-19
Identity | Rushikesh Chaudhari | India | Intigral - Phase 2 | Active | SailPoint | Engineer | Professional Services | 32 | 0 | 32 |  | 0 | 32 | 0 | 0 | 32 | 2024-02-17 | 2024-08-19
Identity | Srikant Bavandla | UAE | Abu Dhabi Media Company | Active | SailPoint | Architect | Professional Services | 74.5 | 52.3 | 0 | 52.3 | 0 | 0 | 0 | 0 | 0 | 2023-09-06 | 2024-08-19
Identity | Infant Ujval Rex | UAE | Abu Dhabi Media Company | Active | SailPoint | Engineer | Professional Services | 136.5 | 143.5 | 7 | 143.5 | 0 | 7 | 260 | 32.5 | -25.5 | 2023-09-06 | 2024-08-19
Identity | Rushikesh Chaudhari | India | Abu Dhabi Media Company | Active | SailPoint | Engineer | Professional Services | 139 | 95.5 | 33.5 | 102 | 6.5 | 27 | 60 | 7.5 | 26 | 2023-09-06 | 2024-02-26 | TBD | Received Complete payment
Identity | Karthikeyan Subramanian | UAE | Abu Dhabi Media Company | Active | SailPoint | Architect | Professional Services | 51 | 30.6 | 45 | 71.55 | 40.95 | 4.05 | 221 | 27.625 | 17.375 | 2023-09-06 | 2024-02-26
Identity | Shandeep Srinivas | UAE | Abu Dhabi Media Company | Active | SailPoint | Engineer | Professional Services | 10 | 11.5 | 1.5 | 11.5 | 0 | 1.5 | 0 | 0 | 1.5 | 2023-09-06 | 2024-02-26
Identity | Karthik NSP | UAE | Mashreq Phase 2 | Active | SailPoint | Architect | Professional Services | 20 | 10 | 10 |  | 0 | 10 | 0 | 0 | 10 | 2023-10-15 | 2024-02-26
Identity | Shandeep Srinivas | UAE | Mashreq Phase 2 | Active | SailPoint | Engineer | Professional Services | 29 | 29 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2023-10-15 | 2024-02-26
Identity | Rakesh Vadnala | UAE | Mashreq Phase 2 | Active | SailPoint | Engineer | Professional Services | 9 | 3 | 6 |  | 0 | 6 | 0 | 0 | 6 | 2023-10-15 | 2025-03-21
Identity | Shilpi | UAE | Mashreq Phase 2 | Active | SailPoint | Engineer | Professional Services | 22 | 8 | 14 |  | 0 | 14 | 0 | 0 | 14 | 2023-10-15 | 2025-03-21
Identity | Vaishnavi Makarand | India | Mashreq Phase 2 | Active | SailPoint | Engineer | Professional Services | 20 | 14 | 6 |  | 0 | 6 | 0 | 0 | 6 | 2023-10-15 | 2025-03-21
Identity | Rushikesh Chaudhari | India | AXA_Gulf Insurance Group – Upgrade | Active | SailPoint | Engineer | Professional Services | 10 | 8 | 5 |  | 5 | 0 | 40 | 5 | 0 | 2025-02-03 | 2025-02-04 | 2025-06-05
Identity | Srikant Bavandla | UAE | AXA_Gulf Insurance Group – Upgrade | Active | SailPoint | Architect | Professional Services |  |  | 26 |  | 26 | 0 | 205 | 25.625 | 0.375 | 2025-02-03 | 2025-02-04
Identity | Vamshi | UAE | Azaq_kalaam | Active | SailPoint | Architect | Professional Services | 95 | 41 | 54 | 50.05 | 9.05 | 44.95 | 112 | 14 | 40 | 2024-04-29 | 2025-02-04
Identity | Niraj Joshi | UAE | Azaq_kalaam | Active | SailPoint | Engineer | Professional Services | 100 | 79.7 | 20.3 | 105.5 | 25.8 | -5.5 | 72 | 9 | 11.3 | 2024-04-29 | 2025-01-17 | TBD | 41 - 30 required , rest can be transferred----(Mashreq Phase3a -Fieldglass)
Identity | Rakesh Vadnala | UAE | Azaq_kalaam | Active | SailPoint | Engineer | Professional Services | 3 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-04-29 | 2025-01-17
Identity | Shandeep Srinivas | UAE | Azaq_kalaam | Active | SailPoint | Engineer | Professional Services | 5 | 5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-04-29 | 2025-01-17
Identity | Karthikeyan Subramanian | UAE | Mashreq Phase 3 | Active | SailPoint | Architect | Professional Services | 4 | 4 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-07-08 | 2025-01-17
Identity | Shilpi | UAE | Mashreq Phase 3 | Active | SailPoint | Engineer | Professional Services | 54 | 54 | 16 |  | 16 | 0 | 60 | 7.5 | 8.5 | 2024-07-08 | 2025-01-17
Identity | Swapnil Deka | UAE | Mashreq Phase 3 | Active | SailPoint | Engineer | Professional Services | 48 | 48 | 8 |  | 8 | 0 | 64 | 8 | 0 | 2024-07-08 | 2025-01-17
Identity | Shandeep Srinivas | UAE | Mashreq Phase 3 | Active | SailPoint | Engineer | Professional Services | 37 | 37 | 8 |  | 8 | 0 | 64 | 8 | 0 | 2024-07-08 | 2025-01-17
Identity | Rakesh Vadnala | UAE | Mashreq Phase 3 | Active | SailPoint | Engineer | Professional Services | 54 | 54 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-07-08 | 2025-01-17
Identity | Karthik NSP | UAE | Mashreq Phase 3 | Active | SailPoint | Architect | Professional Services | 56 | 22 | 10 |  | 5 | 5 | 0 | 0 | 10 | 2024-07-08 | 2025-01-17
Identity | Saurabh Bharadwaj | UAE | Mashreq Phase 3 | Active | SailPoint | Architect | Professional Services | 9 | 5 | 4 |  | 2 | 2 | 52 | 6.5 | -2.5 | 2024-07-08 | 2025-01-17
Identity | Karthik NSP | UAE | Mashreq Phase 3 | Active | SailPoint | Sr Consultant | Professional Services | 41 | 41 | 0 |  | 0 | 0 | 148 | 18.5 | -18.5 | 2024-07-08 | 2025-01-17
Identity | Harsh Aru | India | Mashreq Phase 3 | Active | SailPoint | Engineer | Professional Services | 17 | 17 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-07-08 | 2025-01-27 |  | 2nd Milestone Completed
Identity | Rakesh Vadnala | UAE | Mashreq Phase 3 | Active | SailPoint | Engineer | Professional Services | 31 | 10 | 13 |  | 0 | 13 | 0 | 0 | 13 | 2024-07-08 | 2025-01-27
Identity | Preshit Ghode | India | Mashreq Phase 3 | Active | SailPoint | Engineer | Professional Services | 17 | 12 | 5 |  | 2 | 3 | 32 | 4 | 1 | 2024-07-08 | 2025-01-27
Identity | Srikant Bavandla | UAE | Tawazun | Active | SailPoint | Architect | Professional Services | 41.5 | 39.75 | 1.75 |  | 0 | 1.75 | 55 | 6.875 | -5.125 | 2024-07-15 | 2025-03-06
Identity | Niraj Joshi | UAE | Tawazun | Active | SailPoint | Engineer | Professional Services | 14 | 10.5 | 3.5 |  | 0 | 3.5 | 0 | 0 | 3.5 | 2024-07-15
Identity | Vaishnavi Makarand | India | Tawazun | Active | SailPoint | Engineer | Professional Services | 64 | 61 | 3 |  | 0 | 3 | 21 | 2.625 | 0.375 | 2024-10-03
Identity | Saurabh Bharadwaj | UAE | ADCB Phase 2 | Hold | SailPoint | Architect | Professional Services | 69 | 1 | 68 |  | 0 | 68 | 0 | 0 | 68 | 2024-07-15 | 2024-07-15
Identity | Shilpi | UAE | ADCB Phase 2 | Hold | SailPoint | Engineer | Professional Services | 50 | 1 | 49 |  | 0 | 49 | 0 | 0 | 49 | 2024-07-15 | 2024-10-03
Identity | Rushikesh Chaudhari | India | ADCB Phase 2 | Hold | SailPoint | Engineer | Professional Services | 30 | 0 | 30 |  | 0 | 30 | 0 | 0 | 30 | 2024-07-15
Identity | Swapnil Deka | UAE | ADCB Phase 2 | Hold | SailPoint | Engineer | Professional Services | 21 | 0 | 21 |  | 0 | 21 | 0 | 0 | 21 | 2024-07-15 | 2024-10-03 |  | On Hold
Identity | Vamshi | UAE | SIB | Active | IIQ- Upgrade 8.1 to 8.4 P | Architect | Professional Services | 11 | 4 | 7 |  | 2 | 5 | 32 | 4 | 3 | 2024-10-03 | 2025-03-21
Identity | Rakesh Vadnala | UAE | SIB | Active | IIQ- Upgrade 8.1 to 8.4 P | Engineer | Professional Services | 9 | 0 | 9 |  | 8 | 1 | 62 | 7.75 | 1.25 | 2023-04-01 | 2025-03-21
Identity | Niraj Joshi | UAE | SIB | Active | IIQ- Upgrade 8.1 to 8.4 P | Engineer | Professional Services | 11 | 3 | 8 |  | 3 | 5 | 32 | 4 | 4 | 2023-04-01 | 2025-03-21
Identity | Preshit Ghode | India | SIB | Active | FAM- Upgrade 8.1 to 8.4 P | Engineer | Professional Services | 7 | 0 | 7 |  | 1 | 6 | 0 | 0 | 7 | 2023-04-01 | 2025-03-31
Identity | Sandeep | UAE | SIB | Active | FAM - Upgrade | Architect | Professional Services | 5 | 3 | 2 |  | 2 | 0 | 15 | 1.875 | 0.125 | 2024-09-04 | 2025-03-31
Identity | Karthikeyan Subramanian | UAE | QIB | Active | QIB Phase 3 SailPoint | Architect | Professional Services | 33 | 8.1 | 24.9 |  | 0.75 | 24.15 | 36 | 4.5 | 20.4 | 2024-09-04 | 2025-12-30
Identity | Rakesh Vadnala | UAE | QIB | Active | QIB Phase 3 SailPoint | Engineer | Professional Services | 2 | 0 | 2 |  | 0 | 2 | 0 | 0 | 2 | 2024-09-04 | 2025-06-20
Identity | Shilpi | UAE | QIB | Active | QIB Phase 3 SailPoint | Engineer | Professional Services | 45 | 12 | 33 |  | 0 | 33 | 0 | 0 | 33 | 2024-12-31 | 2025-06-20
Identity | Saurabh Bharadwaj | UAE | ADCB - SAPsuccessfactor and CR | Active | SAP Success Factor Enhancement | Architect | Professional Services | 25 | 25 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-12-31 | 2025-02-06
Identity | Rakesh Vadnala | UAE | ADCB - SAPsuccessfactor and CR | Active | SAP Success Factor Enhancement | Engineer | Professional Services | 25 | 25 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-06-21 | 2025-02-06
Identity | Rushikesh Chaudhari | India | ADCB - SAPsuccessfactor and CR | Active | SAP Success Factor Enhancement | Engineer | Professional Services | 5 | 5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2024-06-21 | 2025-02-06
Identity | Vaishnavi Makarand | India | DIB Support | Active | SailPoint | Technical Consultant | Support | 10 | 0 | 12 |  | 1 | 11 |  |  |  | 2024-11-05
Identity | Saurabh Bharadwaj | UAE | DIB Support | Active | SailPoint | Technical Consultant | Support | 5 | 0 | 3 |  | 1 | 2 |  |  |  | 2024-11-05
Identity | Hrushikesh Ubale | India | SIB Support | Active | SailPoint | Technical Consultant | Support | 2 | 0 | 25 |  | 0 | 25 |  |  |  | 2024-11-05
| Srikant Bavandla |  | AXA Support |  | SailPoint | Technical Consultant | Support |  |  | 1 |  | 1 | 0
Identity | Rushikesh Chaudhari | India | AXA Support | Active | SailPoint | Technical Consultant | Support | 4 | 4 | 25 |  | 4.625 | 20.375 |  |  |  |  | 2025-09-29
Identity | Vaishnavi Makarand | India | Tawazun Support | Active | SailPoint | Technical Consultant | Support | 1 | 0 | 2 |  | 0 | 2 |  |  |  | 2024-09-30 | 2025-11-24
Identity | Niraj Joshi | UAE | Tawazun Support | Active | SailPoint | Technical Consultant | Support | 2 | 1 | 2 |  | 0 | 2 |  |  |  | 2023-03-02 | 2025-11-24
Identity | Rakesh Vadnala | UAE | Tawazun Support | Active | SailPoint | Technical Consultant | Support | 2 | 2 | 2 |  | 0 | 2 |  |  |  | 2023-03-02 | 2024-09-11
Identity | Srikant Bavandla | UAE | Tawazun Support | Active | SailPoint | Technical Consultant | Support | 1 | 1 | 1 |  | 0 | 1 |  |  |  | 2024-11-24 | 2025-10-31
Identity | Hrushikesh Ubale | India | PHCC Support | Active | SailPoint | Technical Consultant | Support | 15 | 8 | 19 |  | 7 | 12 |  |  |  | 2023-09-12 | 2025-10-31
Identity | Shashant | India | Sukoon Insurance (24-25) | Active | Cyberark | Technical Consultant | Support | 8 | 1 | 4 |  | 1.3 | 2.7 |  |  |  | 2024-11-01 | TBD
Identity | Kavin | UAE | Sukoon Insurance (24-25) | Active | Cyberark | Technical Consultant | Support | 8 | 1 | 4 |  | 3 | 1 |  |  |  | 2024-11-01 | TBD
Identity | Niraj Joshi | UAE | ADMC Support | Active | SailPoint | Technical Consultant | Support | 208 | 0 | 104 |  | 20 | 84 |  |  |  | 2023-12-18 | 2024-10-31
| Infant Ujval Rex |  | DMT Support |  | SailPoint | Technical Consultant | Support | 19 |  | 2 |  | 2 | 0
Identity | Rushikesh Chaudhari | India | DMT Support | Active | SailPoint | Technical Consultant | Support | 2 | 1 | 17 |  | 3.875 | 13.125 |  |  |  | 2024-08-16 | 9-Aug-25
Identity | Kavin | UAE | OQ Trading PAM | Active | OQ Trading CyberArk | Sr. Technical Consultant | Professional Services | 6 | 1.5 | 4.5 |  | 0 | 4.5 | 0 | 0 | 4.5 | 2024-11-01 | 2025-12-09
Identity | Shashant | India | OQ Trading PAM | Active | OQ Trading CyberArk | Technical Consultant | Professional Services | 14 | 6.5 | 7.5 |  | 0.2 | 7.3 | 0 | 0 | 7.5 | 10-Aug-24 | 2025-12-09
Identity | Shashant | India | Nextcare PAM | Active | Nextcare - BT | Technical Consultant | Professional Services | 19 | 0 | 19 |  | 2 | 17 | 14.5 | 1.8125 | 17.1875 | 10-Aug-24 | 2027-12-26
Identity | Kavin | UAE | Nextcare PAM | Active | Nextcare - BT | Sr. Technical Consultant | Professional Services | 10 | 0.05 | 9.95 |  | 0 | 9.95 | 0 | 0 | 9.95 | 2024-12-10 | 2027-12-26
Identity | Rushikesh Chaudhari | India | ADCB Phase 2 Support | Active | ADCB | Technical Consultant | Support | 30 | 17 | 13 |  | 0 | 13 |  |  |  | 2024-12-10
Identity | Kavin | UAE | OQ trading Support | Active | Cyberark | Technical Consultant | Support | 8 | 0 | 4 |  | 0 | 4 |  |  |  | 2024-12-27 |  |  | Started in November 2024
Identity | Shashant | India | OQ trading Support | Active | Cyberark | Technical Consultant | Support | 8 | 0 | 4 |  | 0 | 4 |  |  |  | 2024-12-27
Identity | Kavin | UAE | Adek Support (Unlimited tickets) | Active | Cyberark | Technical Consultant | Support | 36 | 0 | 36 |  | 1 | 35 |  |  |  | 2024-10-09 | 2025-12-10
Identity | Shashant | India | Adek Support (Unlimited tickets) | Active | Cyberark | Technical Consultant | Support | 36 | 0 | 36 |  | 3.75 | 32.25 |  |  |  | 2024-10-09 | 2025-05-11
Identity | Hrushikesh Ubale | India | Intigral SailPoint Support | Active | SailPoint | Technical Consultant | Support | 6 | 0 | 6 |  | 0 | 6 |  |  |  | 2024-12-11 | 2025-05-11
Identity | Shilpi | UAE | Mashreq Support - 5 month | Active | SailPoint | Technical Consultant | MSP | 7 | 7 | 5 |  | 5 | 0 |  |  |  | 2025-03-24 | 2025-03-28
Identity | Amala Sunny | UAE | Mashreq Support - 5 month | Active | SailPoint | Technical Consultant | MSP | 8 | 8 | 0 |  | 0 | 0 |  |  |  | 2024-05-12 | 2025-10-13
Identity | Preshit Ghode | India | Mashreq Support - 5 month | Active | SailPoint | Technical Consultant | MSP | 93 | 44 | 49 |  | 67 | -18 |  |  |  | 2024-10-09 | 2025-03-10
Identity | Kavin | UAE | Presidential Flights | Active | Cyberark | Technical Consultant | Support | 5 | 0 | 5 |  | 0 | 5 |  |  |  | 2024-10-14
Identity | Shashant | India | Presidential Flights | Active | Cyberark | Technical Consultant | Support | 5 | 0 | 5 |  | 1.75 | 3.25 |  |  |  | 2024-10-14
Identity | Kavin | UAE | Damac | Active | Cyberark | Technical Consultant | Support | 6 | 0 | 6 |  | 0 | 6 | [6 empty] | 1 Year = Remote Shared Managed Support (8/5). The Assigned resource should be handling min 2 similar customer's.
Identity | Shashant | India | Damac | Active | Cyberark | Technical Consultant | Support | 6 | 0.5 | 5.5 |  | 0 | 5.5
Identity | Shashant | India | ADJD | Active | Cyberark | Technical Consultant | Support | 2 | 0 | 2 |  | 0 | 2
Identity | Kavin | UAE | ADJD | Active | Cyberark | Technical Consultant | Support | 2 | 0 | 2 |  | 1 | 1
Identity | Rushikesh Jadhav | India | EDC | Active | SailPoint | Technical Consultant | MSP | 132 | 0 | 67 |  | 0 | 67
Identity | Shilpi | India | EDC | Active | SailPoint | Technical Consultant | MSP |  |  | 55 |  | 39 | 16
Identity | Hrushikesh Ubale | India | EDC | Active | SailPoint | Technical Consultant | MSP |  |  | 10 |  | 0 | 10
Identity | Rushikesh Jadhav | India | Aldar Support | Active | SailPoint | Consultant | MSP | 80 | 80 | 77 |  | 35 | 42
Identity | Hrushikesh Ubale | India | Aldar Support | Active | SailPoint | Consultant | MSP |  |  | 55 |  | 35 | 20
Identity | Bharath | India | Aldar Support | Active | SailPoint | Tech-ops Manager | MSP | 16 | 16 | 5 |  | 3 | 2
Identity | Hrushikesh Ubale | India | Aldar Support 200 hours Support | Active | SailPoint | Technical Consultant | Support | 25 | 25 | 0 |  | 0 | 0 |  |  |  | 2024-10-16
Identity | Karthik NSP | UAE | Ni UAE FAM Upgrade | Active | SailPoint | Architect | Professional Services | 2 | 0 | 2 |  | 0 | 2 | 8 | 1 | 1
Identity | Karthik NSP | UAE | Ni UAE FAM Upgrade | Active | SailPoint | Sr Consultant | Professional Services | 2 | 0 | 2 |  | 0 | 2 | 6 | 0.75 | 1.25
Identity | Preshit Ghode | India | Ni UAE FAM Upgrade | Active | SailPoint | Engineer | Professional Services | 17 | 15 | 2 |  | 0 | 2 | 0 | 0 | 2
Identity | Vendor (Shifra) | UAE | Intigral Delinia | Active | PAM | Technical Consultant | Support |  |  | 0 |  | 0 | 0
Identity | Vinod | UAE | Katim | Active | SailPoint | Engineer | Professional Services |  |  | 232 |  | 76 | 156 | 567 | 70.875 | 161.125
Identity | Karthik NSP | UAE | Mashreq SailPoint - Upgrade | Active | SailPoint | Architect | Professional Services |  |  | 12 |  | 0 | 12 | 0 | 0 | 12
Identity | Rakesh Vadnala | UAE | Mashreq SailPoint - Upgrade | Active | SailPoint | Consultant | Professional Services |  |  | 18 |  | 0 | 18 | 0 | 0 | 18
Identity | Hitesh Sindhi | India | Airtel Support Phase3 | Active | SailPoint | Tech-ops Manager | MSP |  |  | 120 |  | 17.5 | 102.5 |  |  | 120 | 2024-08-01 | 2027-08-01
Identity | Kanchan Mishra | UAE | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 24 |  | 0 | 24 |  |  | 24 | 2024-08-01 | 2027-08-01
Identity | Karthik NSP | UAE | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 24 |  | 0 | 24 |  |  | 24 | 2024-08-01 | 2027-08-01
Identity | Sandeep D | India | Airtel Support Phase3 | Active | SailPoint | Tech-ops Manager | MSP | 120 |  | 12 |  | 12 | 0 |  |  | 12 | 2024-08-01 | 2027-08-01
Identity | Chaitanya Kulkarni | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 132 |  | 74 | 58 |  |  | 132 | 2024-08-01 | 2027-08-01
Identity | <Noida_L3_1> | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 152 |  | 0 | 152 |  |  | 152 | 2024-08-01 | 2027-08-01
Identity | Amala Sunny | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 110 |  | 74 | 36 |  |  | 110 | 2024-08-01 | 2027-08-01
Identity | <Noida_L3_2> | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 132 |  | 0 | 132 |  |  | 132 | 2024-08-01 | 2027-08-01
Identity | Karina Singh | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 154 |  | 0 | 154 |  |  | 154 | 2024-08-01 | 2027-08-01
Identity | <Noida_l2_2 | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 264 |  | 0 | 264 |  |  | 264 | 2024-08-01 | 2027-08-01
Identity | Shruti C | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 199 |  | 39 | 160 |  |  | 199 | 2024-08-01 | 2027-08-01
Identity | Hrushikesh Ubale | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 110 |  | 44 | 66 |  |  | 110 | 2024-08-01 | 2027-08-01
Identity | Suraj Kalamkar | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 264 |  | 44 | 227 |  |  | 264 | 2024-08-01 | 2027-08-01
Identity | Mahipal Jadhav | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 264 |  | 44 | 227 |  |  | 264 | 2024-08-01 | 2027-08-01
Identity | Ajit Rathod | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 264 |  | 44 | 227 |  |  | 264 | 2024-08-01 | 2027-08-01
Identity | Priyanka Jagnade | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 264 |  | 44 | 227 |  |  | 264 | 2024-08-01 | 2027-08-01
Identity | Shandeep Srinivas | UAE | Airtel Support Phase3 |  | SailPoint | Consultant | MSP |  |  | 2 |  | 2 | 227 |  |  | 2 | 2024-08-01 | 2027-08-01
Identity | Rushikesh Jadhav | India | Airtel Support Phase3 | Active | SailPoint | Consultant | MSP |  |  | 65 |  | 44 | 227 |  |  | 65 | 2024-08-01 | 2027-08-01
Identity | Saurabh Bharadwaj | UAE | Mashreq SailPoint - Non Human Acc development | Active | SailPoint | Architect | Professional Services |  |  | 8 |  | 2 | 6 | 0 | 0 | 8
Identity | Rakesh Vadnala | India | Mashreq SailPoint - Non Human Acc development | Active | SailPoint | Consultant | Professional Services |  |  | 20 |  | 0 | 20 | 0 | 0 | 20
Identity | Shashant | India | ADNEC CyberArk | Active | CyberArk | Consultant | MSP |  |  | 132 |  | 25 | 107 |  |  | 132 | 2025-03-05 | 2025-09-04
Identity | Kavin | UAE | ADNEC CyberArk | Active | CyberArk | Consultant | MSP |  |  | 30 |  | 4 | 26 |  |  |  | 2025-03-05 | 2025-09-04
Identity | Sandeep Dwivedi | UAE | NI Egypt- Log movement | Extra | SailPoint | Tech-ops Manager | Support |  |  | 1 |  | 1 | 0
Identity | Preshit Ghode | India | NI Egypt- Log movement | Extra | SailPoint | Consultant | Support |  |  | 5 |  | 5 | 0
Identity | Sandeep Dwivedi | UAE | Ni UAE FAM Upgrade | Extra | SailPoint | Technical Manager | support |  |  | 5 |  | 5 | 0
Identity | Karthik NSP | UAE | Ni UAE FAM Upgrade | Extra | SailPoint | Sr Consultant | support |  |  | 5 |  | 5 | 0
Identity | Preshit Ghode | India | Ni UAE FAM Upgrade | Extra | SailPoint | Engineer | support |  |  | 12 |  | 3 | 9
Identity | Saurabh Bharadwaj | UAE | Mashreq SailPoint - Health Checkup | Active | SailPoint | Architect | Professional Services |  |  | 6 |  | 1.2 | 4.8 | 0 | 0 | 6
Identity | Resource | India | Mashreq SailPoint - Health Checkup | Active | SailPoint | Consultant | Professional Services |  |  | 12 |  | 0.2 | 11.8 | 0 | 0 | 12
Identity | Kanchan Mishra | UAE | NI Egypt | Active | SailPoint | Consultant | Professional Services |  |  | 11 |  | 1 | 10 | 0 | 0 | 11
Identity | Swapnil Deka | UAE | NI Support | Extra | SailPoint | Engineer | support |  |  | 2 |  | 2
Identity | Kanchan Mishra | UAE | NI Support | Extra | SailPoint | Consultant | support |  |  | 0.5 |  | 0.5
Identity | Rushikesh | UAE | NI Support | Extra | SailPoint | Engineer | support |  |  | 0.5 |  | 0.5
Note on I27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requirement for onboarding 3rd party datasouce (Bayanty) Reply: Added 12 days
Note on K80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Taken from Rushikesh
Note on I87: Bhushan Sisode: IAM & PAM - 16 hrs NON IAM & AXA - 8 hrs
Note on I88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to Discuss
Note on I89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 Year (2 days in a week onsite )
Note on K89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025- 105 but its for 2 year
Note on K90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Taken form rushikesh
Note on R93: Bhushan Sisode: AMC Started after PS Conditional sign off
Note on F97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AMC started after PS conditional sign off
Note on K111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start billing 1st may
Note on K113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start billing in May
Note on K114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Every month 11 days till may ,later 22 days per month
Note on K115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start billing from Jan 1st - 11 days per month till may and stop
Note on K129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Billed till june end 25
Note on K130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 days give to shandeep
Note on K131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Billing till April end
Note on K132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start billing from July 25 Reply: Replacement of Chaitanya
Note on K133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start billing from June 1st 25
Note on K135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start billing from jan 1st -12 days per month billing till June and then normal 22 days billing
Note on K141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 days taken from L3_2
Note on K154: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total allocated days = 22 but scope shared by NI team only requires 11 days

## Milestone Status
NO. | PROJECT ID | Project Type | PROJECT DATA | PROJECT MANAGER | MILESTONE DESCRIPTION | Milestone Status | PLANNED START DATE | PLANNED/Estimated END DATE | Actual End Date | Project Status
1 | RN-239 | Sailpoint | Aldar Phase 2 | Laxmi | M8 - 20% upon Release 4(2 apps) - UAT and Go-Live | Not Started | 2023-03-17
2 | RN-273 | SailPoint | QIB-Phase 3 (LPO1) | Pallavi Nair | M1 - Sailpoint API Traffic - 50% advance with PO | Completed |  |  | 2023-08-15
3 | RN-273 | SailPoint | QIB-Phase 3 (LPO1) | Pallavi Nair | M2 - Sailpoint API Traffic - 50% after integration | On Hold
4 | RN-273 | SailPoint | QIB-Phase 3 (LPO2) | Pallavi Nair | M1- SailpointGOVcm&LCM EFMS-50% advance with PO | Completed |  |  | 2023-08-15
5 | RN-273 | SailPoint | QIB-Phase 3 (LPO2) | Pallavi Nair | M2 - SailpointGOVcm&LCM EFMS- 50% after integration | On Hold
6 | RN-273 | SailPoint | QIB-Phase 3 (LPO3) | Pallavi Nair | M1 - IAM Integration for NewGen - 50% advance with PO | Completed |  |  | 2023-08-15
7 | RN-273 | SailPoint | QIB-Phase 3 (LPO3) | Pallavi Nair | M2 - IAM Integration for NewGen API - 50% after integration | On Hold
8 | RN-273 | SailPoint | QIB-Phase 3 (LPO4) | Pallavi Nair | M1 - Legal System-IAM Integration- 50% advance with PO | Completed |  |  | 2023-08-15
9 | RN-273 | SailPoint | QIB-Phase 3 (LPO4) | Pallavi Nair | M2 - Legal System-IAM Integration- 50% after integration | On Hold
10 | RN-273 | SailPoint | QIB-Phase 3 (LPO5) | Pallavi Nair | M1 - SAS Compliance - 50% advance with PO | Completed |  |  | 2023-08-15
11 | RN-273 | SailPoint | QIB-Phase 3 (LPO5) | Pallavi Nair | M2 - SAS Compliance - 50% after integration | On Hold
12 | RN-273 | SailPoint | QIB Phase 3 - 40 hrs Governance_09042023_CR | Pallavi Nair | M1 - 30 days (15 Apps + PAM Integration) | Completed |  |  | 2023-08-01
13 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | Y3- License cost shall be paid annually for 3 Years within 30 days. Subject to submission of complete documentation (Invoice, License Activation Report, Statement of Account) | Not Started | 2025-08-21 | 2026-08-20
14 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | 1- License Amount | Completed |  |  | 2023-11-15
15 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Platform Installation for UAT and Production environment(30%) | Completed | 2024-03-04 | 2024-06-28 | 2024-09-20
16 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Internal UAT testing and acceptance for 24 application(5 Apps will be integrated directly in production)(25%) | Completed | 2024-05-13 | 2024-08-09 | 2024-11-27
17 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Business owner UAT completion for 29 Apps | Completed | 2024-07-15 | 2024-12-05 | 2024-12-05
18 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Post Go Live testing(10%) | Completed | 2024-09-23 | 2024-11-29 | 2025-01-02
19 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Knowledge Transfer (10%) | Delayed | 2024-11-04 | 2025-02-28
20 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M1.YEar1.End of each month | Not Started | 2025-03-01 | 2025-03-31
21 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M2.YEar1.End of each month | Not Started | 2025-04-01 | 2025-04-30
22 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M3.YEar1.End of each month | Not Started | 2025-05-01 | 2025-05-31
23 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M4.YEar1.End of each month | Not Started | 2025-06-01 | 2025-06-30
24 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M5.YEar1.End of each month | Not Started | 2025-07-01 | 2025-07-31
25 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M6.YEar1.End of each month | Not Started | 2025-08-01 | 2025-08-30
26 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M7.YEar1.End of each month | Not Started | 2025-09-01 | 2025-09-30
27 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M8.YEar1.End of each month | Not Started | 2025-10-01 | 2025-10-31
28 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M9.YEar1.End of each month | Not Started | 2025-11-01 | 2025-11-30
29 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M10.YEar1.End of each month | Not Started | 2025-12-01 | 2025-12-31
30 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M11.YEar1.End of each month | Not Started | 2026-01-01 | 2026-01-31
31 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M12.YEar1.End of each month | Not Started | 2026-02-01 | 2026-02-28
32 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Year2 Resource Cost | Not Started | 2026-03-01 | 2026-03-31
33 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 1 : 20 % Project Customer Kick off, Design Workshops, Recruitment Gathering, Gaps Assessment & High-Level Design with HLD Submission (all in scope Apps) | Completed | 2024-02-22 |  | 2024-05-10
34 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 2 : 20% Installation & Base Setup, LCM, Compliance Module | On Hold | 2024-02-20 | 2024-07-29
35 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 3 :25 % Sprint 1: Integration of 2 Core Apps – UAT | On Hold | 2024-05-14 | 2024-06-03
36 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 4 : 25% Sprint 2: SailPoint Integration: 4 Apps UAT | Not Started | 2024-07-30 | 2024-09-08
37 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 5 : 10% OD, Final Go-live, Documentation, Training & Sign-Off | Not Started | 2024-09-09 | 2024-10-30
38 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 6 : SailPoint Technical Admin Training for Two Users | Not Started | 2024-10-15 | 2024-10-30
39 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 7 : Onsite Support :6 months, Offsite Support: 6 months. After completion of each quarter, RNS shall raise invoice | Not Started | 2024-11-01 | 2025-01-31
40 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 7 : Onsite Support :6 months, Offsite Support: 6 months. After completion of each quarter, RNS shall raise invoice | Not Started | 2025-02-01 | 2025-04-30
41 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 7 : Onsite Support :6 months, Offsite Support: 6 months. After completion of each quarter, RNS shall raise invoice | Not Started | 2025-05-01 | 2025-07-31
42 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 7 : Onsite Support :6 months, Offsite Support: 6 months. After completion of each quarter, RNS shall raise invoice | Not Started | 2025-08-01 | 2025-10-31
43 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | license | Completed |  |  | 2023-12-01
44 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | 30% to be invoiced Upon Project Kick-off | Completed | 2024-01-30 |  | 2024-01-30
45 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | 30% to be invoiced Upon UAT Testing Completion of 5 Apps UNBILLED | On Hold | 2024-03-24 | 2024-07-30
46 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | 20% to be invoiced Upon UAT Testing Completion of 10 Apps UNBILLED | Not Started | 2024-05-24 | 2024-07-28
47 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | 20% to be invoiced Upon Project Sign-off | Not Started | 2024-07-29 | 2024-08-06
48 | RN-422 | SailPoint | KalaamAlQureshi_SailPointServices_Dec_2023 | Laxmi | Milestone 1: High Level Design Sign-off - 20% | Completed | 2024-05-08 | 2024-08-13 | 2024-08-13
49 | RN-422 | SailPoint | KalaamAlQureshi_SailPointServices_Dec_2023 | Laxmi | Milestone 2: Installation Sign-off of PROD Environment - 30% | Completed | 2024-05-06 |  | 2024-07-04
50 | RN-422 | SailPoint | KalaamAlQureshi_SailPointServices_Dec_2023 | Laxmi | Milestone 3: UAT Sign-Off for 3 applications - 30% | Completed | 2024-05-29 | 2025-02-20
51 | RN-422 | SailPoint | KalaamAlQureshi_SailPointServices_Dec_2023 | Laxmi | Milestone 4: Sign-Off for RBAC (3 application) & Final Go-live, Documentation and Handover- 20% | On Track | 2025-05-13 | 2025-06-05
52 | RN-425 | SailPoint | Network International Dubai FAM Upgrade | Laxmi | a. 50% to be invoiced upon Project Kick-off | Completed | 2024-07-04 | 2024-07-04 | 2024-07-04
53 | RN-425 | SailPoint | Network International Dubai FAM Upgrade | Laxmi | b. 50% to be incoived upon Project Sign-off | Delayed | 2024-07-10 | 2024-11-08
54 | RN-446 | SailPoint | MAshreq Bank sailpoint- phase 3 | Pallavi Nair | R1 Go Live and Stabilisation Signoff - 30% | Completed | 2024-07-25 | 2025-01-22 | 2025-01-22
55 | RN-446 | SailPoint | MAshreq Bank sailpoint- phase 3 | Pallavi Nair | R2 Go Live and Stabilisation Signoff - 25% | Completed | 2024-12-16 | 2025-02-04 | 2024-12-10
56 | RN-446 | SailPoint | MAshreq Bank sailpoint- phase 3 | Pallavi Nair | R3 Go Live and Stabilisation Signoff - 25% | Completed | 2024-12-16 | 2025-01-22 | 2025-01-22
57 | RN-446 | SailPoint | MAshreq Bank sailpoint- phase 3 | Pallavi Nair | Final Payment on Delivery Closure Report Sign Off - 20% | Not Started | 2024-12-16 | 2025-04-04
58 | RN -445 | Sailpoint | Tawazun Coucil | Bhushan | Milestone 1: SailPoint Upgrade (Version 8.1 to 8.4 P1) UAT | Completed | 2024-08-14 | 2024-09-26 | 2024-09-04
59 | RN -445 | Sailpoint | Tawazun Coucil | Bhushan | Milestone 2: SailPoint Upgrade (Version 8.1 to 8.4 P1) PROD | Completed | 2024-09-27 | 2024-11-07 | 2024-10-01
60 | RN -445 | Sailpoint | Tawazun Coucil | Bhushan | Milestone 3: Workflow Enhancements | Delayed | 2024-11-08 | 2025-02-14
61 | RN-482 | SailPoint | SIB | Pallavi Nair | 50% UAT Signoff for IIQ Upgrade (8.1-->8.3p3) | Delayed | 2024-12-09 | 2025-03-05
62 | RN-482 | SailPoint | SIB | Pallavi Nair | 50% Signoff for IIQ Prod Upgrade (8.1-->8.3p3) | Delayed | 2025-01-17 | 2025-03-14
63 | RN-482 | SailPoint | SIB | Pallavi Nair | 50% UAT Signoff FAM Upgrade (8.2-->8.4p3) | On Track | 2025-01-22 | 2025-03-31
64 | RN-482 | SailPoint | SIB | Pallavi Nair | 50% on Sign off FAM Prod Upgrade (8.2→8.4p3) | On Track | 2025-01-31 | 2025-03-31
65 | -- | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | UAT Environment Sign Off for Upgrade (8.1-->8.3p3) = 20% | Not Started
66 | -- | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | PROD & DR Environments Sign Off for Upgrade (8.1-- >8.3p3) = 20% | Not Started
67 | -- | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | Sprint 1: UAT Sign-Off for Sprint 1 applications (4 applications) =15 % | Not Started
68 | -- | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | Sprint 2: UAT Sign-Off for Sprint 2 applications (3 applications) =15 % | Not Started
69 | -- | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | Sign-Off for RBAC (5 applications) = 15% | Not Started
70 | -- | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | Sign-Off for RBAC(4 applications) Final Go-live, Documentation and Handover = 15% | Not Started
71 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2025-01-01 | 2025-01-31 | 2025-02-10
72 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Delayed | 2025-02-01 | 2025-02-28
73 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-03-01 | 2025-03-31
74 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-04-01 | 2025-04-30
75 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-05-01 | 2025-05-31
76 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-06-01 | 2025-06-30
77 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-07-01 | 2025-07-31
78 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-08-01 | 2025-08-31
79 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-09-01 | 2025-09-30
80 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-10-01 | 2025-10-31
81 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-11-01 | 2025-11-30
82 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-12-01 | 2025-12-31
83 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | Y12 - License cost shall be paid annually for 3 Years within 30 days. Subject to submission of complete documentation (Invoice, License Activation Report, Statement of Account) | Completed | 2024-08-21 | 2025-08-20 | 2025-08-20 | Closed
84 | RN - 470 | Sailpoint | ADCB - SAP SuccessFactor and IAM Enhancement | Ajinkya | Milestone 4: SAP Success factor Application Integration PROD - 20% | Completed | 2024-10-29 |  | 2025-02-06 | Closed on 6-Feb-25
85 | RN - 470 | Sailpoint | ADCB - SAP SuccessFactor and IAM Enhancement | Ajinkya | Milestone 5: Workflow Enhancement and Exchange PROD - 20% | Completed | 2024-10-30 |  | 2025-02-06 | Closed on 6-Feb-25
86 |  | SailPoint | Mashreq - Fieldglass | Pallavi Nair | Milestone 2- IAM -Field glass integration to enable Field glass automated user life cycle management - 40 % | Completed | 2024-11-25 | 2025-01-22 | 2025-01-22 | Closed on 22-Jan-25
87 | RN - 515 | SailPoint | Airtel Phase 3 | Laxmi | Milestone 1: Workshop and Design for 20 Applications (SailPoint) & 20 Applications (ForgeRock) with HLD Submission = 10% | On Track | 2025-01-13 08:00
88 | RN - 515 | SailPoint | Airtel Phase 3 | Laxmi | Milestone 2: Workshop and Design for 1 Application (FAM), 10 Applications (SailPoint) & 10 Applications (ForgeRock) with HLD Submission = 10% | On Track
89 | RN - 515 | SailPoint | Airtel Phase 3 | Laxmi | Milestone 3: RBAC (SailPoint) 20 Applications Integration with UAT for target application + SOD (SailPoint) 20 Applications Finalization & Implementation = 20% | Not Started
90 | RN - 515 | SailPoint | Airtel Phase 3 | Laxmi | Milestone 4: Sprint 1-15 SailPoint Applications Integration and UAT for initial target applications + 15 Forge Rock Applications Integration and UAT for initial target applications = 30% | Not Started
91 | RN - 515 | SailPoint | Airtel Phase 3 | Laxmi | Milestone 5: Sprint 215 SailPoint Applications Integration and UAT for target applications + 15 ForgeRock Applications Integration and UAT for target applications + 1 FAM Application Integration in 2 environment 13 instances = 30% | Not Started
92 |  | SailPoint | Airtel Phase 3 Support | Laxmi | Q1 Managed Support | Completed
93 |  | SailPoint | Airtel Phase 3 Support | Laxmi | Q2 Managed Support | On Track
94 |  | SailPoint | Airtel Phase 3 Support | Laxmi | Q3 Managed Support | Not Started
95 |  | SailPoint | Airtel Phase 3 Support | Laxmi | Q4 Managed Support | Not Started
Note on F93: Bhushan Sisode This Support is valid till 3 years

## Billed_2024 (hidden)
S.No. | Department | Resource | Location | Customer Name | Project Name | Role | Engagement Type | Allocated Billed Days | Utilized Billed Days(Project plan) | Remaining Billed Days(Project plan) | Utilized Billed hrs (Zoho) | Utilized Billed days (Zoho) | Remaining Billed Days (Zoho) | Project Start Date | Project End Date | Revised End Date | Comments
1 | Identity | Karthikeyan Subramanian | UAE | DOHA Bank | SailPoint | Architect | Professional Services | 119.5 | 45 | 74.5 | 246.3 | 30.7875 | 88.71 | 2024-02-22 | 2024-10-30 | TBD
2 | Identity | Prathmesh | India | DOHA Bank | SailPoint | Engineer | Professional Services | 5 | 5 | 0 | 27 | 3.375 | 1.63
3 | Identity | Rakesh Vadnala | UAE | DOHA Bank | SailPoint | Engineer | Professional Services | 47.5 | 13 | 34.5 | 209 | 26.125 | 21.38
4 | Identity | Vaishnavi Makarand | India | DOHA Bank | SailPoint | Engineer | Professional Services | 14 | 0 | 14 | 0 | 0 | 14
5 | Identity | Kanchan Mishra | UAE | NIJordan_Sept_2023 | SailPoint | Architect | Professional Services | 22 | 22 | 0 | 198.3 | 24.7875 | -2.79 | 2023-10-19 | 2024-07-30 | 2024-12-24 | Full Payment Completed
6 | Identity | Srikant Bavandla | UAE | NIJordan_Sept_2023 | SailPoint | Architect | Professional Services | 1 | 1 | 0 | 0 | 0 | 1 | 2023-10-19 | 2024-07-30
7 | Identity | Vaishnavi Makarand | India | NIJordan_Sept_2023 | SailPoint | Engineer | Professional Services | 17 | 17 | 0 | 143 | 17.875 | -0.88 | 2023-10-19 | 2024-07-30
8 | Identity | Swapnil Deka | UAE | NIJordan_Sept_2023 | SailPoint | Engineer | Professional Services | 35 | 31 | 4 | 259 | 32.375 | 2.63 | 2023-10-19 | 2024-07-30
9 | Identity | Saurabh Bharadwaj | UAE | NI SouthAfrica_Sept_2023 | SailPoint | Architect | Professional Services | 26 | 26 | 0 | 225.3 | 28.1625 | -2.16 | 2023-11-01 | 2024-04-22 | 2024-12-02 | Signed off
10 | Identity | Prathmesh | India | NI SouthAfrica_Sept_2023 | SailPoint | Engineer | Professional Services | 5 | 5 | 0 | 40 | 5 | 0 | 2023-11-01 | 2024-04-22
11 | Identity | Rakesh Vadnala | UAE | NI SouthAfrica_Sept_2023 | SailPoint | Engineer | Professional Services | 48.5 | 48.5 | 0 | 372.3 | 46.5375 | 1.96 | 2023-11-01 | 2024-04-22
12 | Identity | Vaishnavi Makarand | India | NI SouthAfrica_Sept_2023 | SailPoint | Engineer | Professional Services | 5.5 | 5.5 | 0 | 32 | 4 | 1.5 | 2023-11-01 | 2024-04-22
13 | Identity | Vamshi | UAE | NI Egypt_Phase 2 | SailPoint | Architect | Professional Services | 50.25 | 45.5 | 4.75 | 394 | 49.25 | 1 | 2023-12-26 | 2024-05-30 | Project officially closed
14 | Identity | Srikant Bavandla | UAE | NI Egypt_Phase 2 | SailPoint | Architect | Professional Services | 10.5 | 5.5 | 5 | 39 | 4.875 | 5.63 | 2023-12-26 | 2024-05-30
15 | Identity | Niraj Joshi | UAE | NI Egypt_Phase 2 | SailPoint | Engineer | Professional Services | 48.25 | 11.5 | 36.75 | 88 | 11 | 37.25 | 2023-12-26 | 2024-05-30
16 | Identity | Rakesh Vadnala | UAE | NI Egypt_Phase 2 | SailPoint | Engineer | Professional Services | 2 | 2 | 0 | 16 | 2 | 0 | 2023-12-26 | 2024-05-30
17 | Identity | Swapnil Deka | UAE | NI Egypt_Phase 2 | SailPoint | Engineer | Professional Services | 4 | 4 | 0 | 32 | 4 | 0 | 2023-12-26 | 2024-05-30
18 | Identity | Karthik NSP | UAE | Airtel - Phase 2 | IIQ | Architect | Professional Services | 70 | 70 | 0 | 1007 | 125.875 | -55.88 | 2023-12-11 | 2024-09-10 | 2024-10-05 | project signed Off
19 | Identity | Amala Sunny | UAE | Airtel - Phase 2 | IIQ/Forgerock | Engineer | Professional Services | 92 | 92 | 0 | 793.18 | 99.1475 | -7.15 | 2023-12-11 | 2024-09-10
20 | Identity | Preshit Ghode | India | Airtel - Phase 2 | IIQ | Engineer | Professional Services | 91 | 91 | 0 | 652 | 81.5 | 9.5 | 2023-12-11 | 2024-09-10
21 | Identity | Niraj Joshi | UAE | Airtel - Phase 2 | IIQ | Engineer | Professional Services | 48 | 48 | 0 | 248 | 31 | 17 | 2023-12-11 | 2024-09-10 |  |  | no chnges made
22 | Identity | Rakesh Vadnala | UAE | Airtel - Phase 2 | IIQ | Engineer | Professional Services | 51 | 41 | 10 | 232 | 29 | 22 | 2023-12-11 | 2024-09-10
23 | Identity | Aishwary Kumar | UAE | Airtel - Phase 2 | IIQ | Engineer | Professional Services | 47 | 47 | 0 | 328 | 41 | 6 | 2023-12-11 | 2024-09-10
24 | Identity | Kanchan Mishra | UAE | Airtel - Phase 2 | Forgerock/SMS OTP | Architect | Professional Services | 146 | 150.95 | -4.95 | 1221 | 152.625 | -6.63 | 2023-12-11 | 2024-09-10
25 | Identity | Shandeep Srinivas | UAE | Airtel - Phase 2 | Forgerock/SMS OTP | Engineer | Professional Services | 90 | 90 | 0 | 790.3 | 98.7875 | -8.79 | 2023-12-11 | 2024-09-10
26 | Identity | Shandeep Srinivas | UAE | Airtel Phase 2A - Multisite Installation | Forgerock | Engineer | Professional Services | 26 | 1.975 | 24.025 | 0 | 0 | 26 | 2024-07-10 | TBD
27 | Identity | Kanchan Mishra | UAE | Airtel Phase 2A - Multisite Installation | Forgerock | Architect | Professional Services | 11 | 1.25 | 9.75 | 0 | 0 | 11 | 2024-07-10 | TBD
28 | Identity | Karthik NSP | UAE | Airtel - Phase 3 | IIQ | Architect | Professional Services | 24 | 0 | 24 | 0 | 0 | 24 | 2025-01-13 | 2028-03-02
29 | Identity | Karthikeyan Subramanian | UAE | Airtel - Phase 3 | IIQ | Architect | Professional Services | 80 | 0 | 80 | 0 | 0 | 80 | 2025-01-13 | 2025-01-13
30 | Identity | Karthik NSP | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 140 | 0 | 140 | 0 | 0 | 140 | 2025-01-13 | 2025-01-13
31 | Identity | Amala Sunny | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 90 | 0 | 90 | 0 | 0 | 90 | 2025-01-13 | 2025-01-13
32 | Identity | Rakesh Vadnala | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 30 | 0 | 30 | 0 | 0 | 30 | 2025-01-13 | 2025-01-13
33 | Identity | Swapnil Deka | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 50 | 0 | 50 | 0 | 0 | 50 | 2025-01-13 | 2025-01-13
34 | Identity | Shilpi | UAE | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 129 | 0 | 129 | 0 | 0 | 129 | 2025-01-13 | 2025-01-13
35 | Identity | New Resources 1 | India | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 155 | 0 | 155 | 0 | 0 | 155 | 2025-01-13 | 2025-01-13
36 | Identity | New Resources 2 | India | Airtel - Phase 3 | IIQ | Engineer | Professional Services | 155 | 0 | 155 | 0 | 0 | 155 | 2025-01-13 | 2025-01-13
37 | Identity | Shandeep Srinivas | UAE | Airtel - Phase 3 | IIQ - RBAC | Engineer | Professional Services | 90 | 0 | 90 | 0 | 0 | 90 | 2025-01-13 | 2025-01-13
38 | Identity | Hrushikesh Ubale | India | Airtel - Phase 3 | FAM | Engineer | Professional Services | 22 | 0 | 22 | 0 | 0 | 22 | 2025-01-13 | 2025-02-11
39 | Identity | Kanchan Mishra | UAE | Airtel - Phase 3 | Forgerock | Architect | Professional Services | 90 | 3 | 87 | 0 | 0 | 90 | 2025-01-13 | 2026-05-15
40 | Identity | Kanchan Mishra | UAE | Airtel - Phase 3 | Forgerock | Engineer | Professional Services | 10 | 0 | 10 | 0 | 0 | 10 | 2025-01-13 | 2025-01-13
41 | Identity | Shandeep Srinivas | UAE | Airtel - Phase 3 | Forgerock | Engineer | Professional Services | 90 | 6 | 84 | 0 | 0 | 90 | 2025-01-13 | 2025-01-13
42 | Identity | Amala Sunny | UAE | Airtel - Phase 3 | Forgerock | Engineer | Professional Services | 100 | 0 | 100 | 0 | 0 | 100 | 2025-01-13 | 2025-01-13
43 | Identity | Chaitanya Kulkarni | India | Airtel - Phase 3 | Forgerock | Engineer | Professional Services | 90 | 0.58 | 89.42 | 0 | 0 | 90 | 2025-01-13 | 2025-01-13
44 | Identity | Karthikeyan Subramanian | UAE | DMT | Sailpoint | Architect | Professional Services | 103 | 103 | 0 | 741 | 92.625 | 10.38 | 2023-10-13 | 2024-11-30 | 2024-11-30 | Received Complete payment
45 | Identity | Infant Ujval Rex | UAE | DMT | Sailpoint | Engineer | Professional Services | 88.75 | 80 | 8.75 | 399.45 | 49.9312 | 38.82 | 2023-10-13 | 2024-11-30
46 | Identity | Aishwary Kumar | UAE | DMT | Sailpoint | Engineer | Professional Services | 40 | 11.25 | 28.75 | 98 | 12.25 | 27.75 | 2023-10-13 | 2024-11-30
47 | Identity | Rakesh Vadnala | UAE | DMT | Sailpoint | Engineer | Professional Services | 3 | 3 | 0 | 24 | 3 | 0 | 2023-10-13 | 2024-11-30
48 | Identity | Karthik NSP | UAE | Intigral - Phase 2 | Sailpoint | Architect | Professional Services | 31 | 10 | 21 | 81 | 10.125 | 20.88 | 2024-02-17 | 2024-12-31 | TBD
49 | Identity | Aishwary Kumar | UAE | Intigral - Phase 2 | Sailpoint | Engineer | Professional Services | 49 | 17 | 32 | 139.45 | 17.4312 | 31.57 | 2024-02-17 | 2024-12-31
50 | Identity | Rushikesh Chaudhari | India | Intigral - Phase 2 | SailPoint | Engineer | Professional Services | 32 | 0 | 32 | 32 | 4 | 28 | 2024-02-17 | 2024-12-31
51 | Identity | Saurabh Bharadwaj | UAE | DIB | Sailpoint | Architect | Professional Services | 73 | 87.6 | -14.6 | 519.15 | 64.8937 | 8.11 | 2022-01-17 | 2022-06-19 | 2024-11-14 | Signed Off
52 | Identity | Swapnil Deka | UAE | DIB | Sailpoint | Engineer | Professional Services | 62 | 59 | 3 | 754.3 | 94.2875 | -32.29 | 2022-01-17 | 2022-06-19
53 | Identity | Aishwary Kumar | UAE | DIB | Sailpoint | Engineer | Professional Services | 65 | 65 | 0 | 662 | 82.75 | -17.75 | 2022-01-17 | 2022-06-19
54 | Identity | Srikant Bavandla | UAE | Abu Dhabi Media Company | SailPoint | Architect | Professional Services | 74.5 | 56.3 | 18.2 | 1183 | 147.875 | -73.38 | 2023-09-06 | 2024-08-19 | 2024-12-24
55 | Identity | Infant Ujval Rex | UAE | Abu Dhabi Media Company | SailPoint | Engineer | Professional Services | 136.5 | 143.5 | -7 | 962.3 | 120.2875 | 16.21 | 2023-09-06 | 2024-08-19
56 | Identity | Rushikesh Chaudhari | India | Abu Dhabi Media Company | SailPoint | Engineer | Professional Services | 139 | 95.5 | 43.5 | 827 | 103.375 | 35.63 | 2023-09-06 | 2024-08-19
57 | Identity | Karthikeyan Subramanian | UAE | Abu Dhabi Media Company | SailPoint | Architect | Professional Services | 51 | 38.9 | 12.1 | 711 | 88.875 | -37.88 | 2023-09-06 | 2024-08-19
58 | Identity | Shandeep Srinivas | UAE | Abu Dhabi Media Company | SailPoint | Engineer | Professional Services | 10 | 11.5 | -1.5 | 87.3 | 10.9125 | -0.91 | 2023-09-06 | 2024-08-19
59 | Identity | Aishwary Kumar | UAE | Abu Dhabi Media Company | SailPoint | Engineer | Professional Services | 19 | 22 | -3 | 0 | 0 | 19 | 2023-09-06 | 2024-08-19
60 | Identity | Karthik NSP | UAE | Mashreq Phase 2 | SailPoint | Architect | Professional Services | 20 | 10 | 10 | 348.3 | 43.5375 | -23.54 | 2023-10-15 | 2024-02-26 | TBD | Received Complete payment
61 | Identity | Shandeep Srinivas | UAE | Mashreq Phase 2 | SailPoint | Engineer | Professional Services | 29 | 29 | 0 | 332.3 | 41.5375 | -12.54 | 2023-10-15 | 2024-02-26
62 | Identity | Amala Sunny | UAE | Mashreq Phase 2 | SailPoint | Engineer | Professional Services | 9 | 3 | 6 | 42 | 5.25 | 3.75 | 2023-10-15 | 2024-02-26
63 | Identity | Shilpi | UAE | Mashreq Phase 2 | SailPoint | Engineer | Professional Services | 22 | 8 | 14 | 176 | 22 | 0 | 2023-10-15 | 2024-02-26
64 | Identity | Vaishnavi Makarand | India | Mashreq Phase 2 | SailPoint | Engineer | Professional Services | 20 | 14 | 6 | 56 | 7 | 13 | 2023-10-15 | 2024-02-26
65 | Identity | Sandeep Dwivedi | UAE | AXA_Gulf Insurance Group | SailPoint | Architect | Professional Services | 0 | 0 | 0 | 15 | 1.875 | -1.88 | Signed off |  |  | Received Complete payment
66 | Identity | Karthik NSP | UAE | AXA_Gulf Insurance Group | SailPoint | Engineer | Professional Services | 8 | 0.5 | 7.5 | 0 | 0 | 8 | 2024-04-24 | 2024-04-24
67 | Identity | Rushikesh Chaudhari | India | AXA_Gulf Insurance Group | SailPoint | Engineer | Professional Services | 2 | 2 | 0 | 242.15 | 30.2688 | -28.27
68 | Identity | Vamshi | UAE | AXA_Gulf Insurance Group – Upgrade | SailPoint | Architect | Professional Services | 10 | 10 | 0 | 120 | 15 | -5 | Signed off |  |  | Received Complete payment
69 | Identity | Rushikesh Chaudhari | India | AXA_Gulf Insurance Group – Upgrade | SailPoint | Engineer | Professional Services | 10 | 8 | 2 | 242.15 | 30.2688 | -20.27
70 | Identity | Preshit Ghode | India | AXA_Gulf Insurance Group – Upgrade | SailPoint | Engineer | Professional Services | 13 | 13 | 0 | 140.3 | 17.5375 | -4.54
71 | Identity | Vamshi | UAE | Azaq_kalaam | SailPoint | Architect | Professional Services | 83 | 41.6 | 41.4 | 560 | 70 | 13 | 2024-04-29 | 2025-02-04 | 2025-06-05
72 | Identity | Niraj Joshi | UAE | Azaq_kalaam | SailPoint | Engineer | Professional Services | 65 | 79.7 | -14.7 | 248 | 31 | 34 | 2024-04-29 | 2025-02-04
73 | Identity | Rakesh Vadnala | UAE | Azaq_kalaam | SailPoint | Engineer | Professional Services | 3 | 3 | 0 | 24 | 3 | 0 | 2024-04-29 | 2025-02-04
74 | Identity | Shandeep Srinivas | UAE | Azaq_kalaam | SailPoint | Engineer | Professional Services | 5 | 5 | 0 | 81 | 10.125 | -5.13 | 2024-04-29 | 2025-02-04
75 | Identity | Karthikeyan Subramanian | UAE | Mashreq Phase 3 | SailPoint | Architect | Professional Services | 6 | 4 | 2 | 46 | 5.75 | 0.25 | 2024-07-08 | 2025-01-17
76 | Identity | Shilpi | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 54 | 54 | 0 | 587.01 | 73.3762 | -19.38 | 2024-07-08 | 2025-01-17
77 | Identity | Swapnil Deka | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 48 | 48 | 0 | 320 | 40 | 8 | 2024-07-08 | 2025-01-17
78 | Identity | Shandeep Srinivas | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 32 | 37 | -5 | 336 | 42 | -10 | 2024-07-08 | 2025-01-17
79 | Identity | Amala Sunny | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 54 | 54 | 0 | 420 | 52.5 | 1.5 | 2024-07-08 | 2025-01-17
80 | Identity | Karthik NSP | UAE | Mashreq Phase 3 | SailPoint | Architect | Professional Services | 22 | 22 | 0 | 0 | 0 | 22 | 2024-07-08 | 2025-01-17
81 | Identity | Saurabh Bharadwaj | UAE | Mashreq Phase 3 | SailPoint | Architect | Professional Services | 11 | 4 | 7 | 0 | 0 | 11 | 2024-07-08 | 2025-01-17
82 | Identity | Karthik NSP | UAE | Mashreq Phase 3 | SailPoint | Sr Consultant | Professional Services | 73 | 40 | 33 | 508 | 63.5 | 9.5 | 2024-07-08 | 2025-01-17 |  |  | 41 - 30 required , rest can be transferred----(Mashreq Phase3a -Fieldglass)
83 | Identity | Harsh Aru | India | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 17 | 17 | 0 | 0 | 0 | 17 | 2024-07-08 | 2025-01-17
84 | Identity | Rakesh Vadnala | UAE | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 40 | 10 | 30 | 144 | 18 | 22 | 2024-07-08 | 2025-01-17
85 | Identity | Preshit Ghode | India | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 11 | 8 | 3 | 64 | 8 | 3 | 2024-07-08 | 2025-01-17
86 | Identity | Shruti C | India | Mashreq Phase 3 | SailPoint | Engineer | Professional Services | 17 | 17 | 0 | 0 | 0 | 17 | 2024-07-08 | 2025-01-17
87 | Identity | Karthik NSP | UAE | Mashreq Fieldglass | SailPoint | Architect | Professional Services | 13 | 13 | 0 | 84 | 10.5 | 2.5 | 2024-11-25 | 2025-01-17
88 | Identity | Srikant Bavandla | UAE | Mashreq Fieldglass | sailpoint | Engineer | Professional Services | 10 | 10 | 0 | 80 | 0 | 10 | 2024-11-25 | 2025-01-17
89 | Identity | Shandeep Srinivas | UAE | Mashreq Fieldglass | SailPoint | Engineer | Professional Services | 15 | 15 | 0 | 128 | 16 | -1 | 2024-11-25 | 2025-01-17
90 | Identity | Srikant Bavandla | UAE | Tawazun | SailPoint | Architect | Professional Services | 41.5 | 39.75 | 1.75 | 344 | 43 | -1.5 | 2024-07-15 | 2025-01-27 |  | 2nd Milestone Completed
91 | Identity | Niraj Joshi | UAE | Tawazun | SailPoint | Engineer | Professional Services | 14 | 10.5 | 3.5 | 48 | 6 | 8 | 2024-07-15 | 2025-01-27
92 | Identity | Vaishnavi Makarand | India | Tawazun | SailPoint | Engineer | Professional Services | 64 | 61 | 3 | 299 | 37.375 | 26.63 | 2024-07-15 | 2025-01-27
93 | Identity | Saurabh Bharadwaj | UAE | ADCB Phase 2 | SailPoint | Architect | Professional Services | 69 | 1 | 68 | 0 | 1 | 68 | 2024-07-15
94 | Identity | Shilpi | UAE | ADCB Phase 2 | SailPoint | Engineer | Professional Services | 50 | 1 | 49 | 0 | 1 | 49 | 2024-07-15
95 | Identity | Rushikesh Chaudhari | India | ADCB Phase 2 | SailPoint | Engineer | Professional Services | 30 | 0 | 30 | 0 | 0 | 30 | 2024-07-15
96 | Identity | Swapnil Deka | UAE | ADCB Phase 2 | SailPoint | Engineer | Professional Services | 21 | 0 | 21 | 0 | 0 | 21 | 2024-07-15
97 | Identity | Saurabh Bharadwaj | UAE | EDC | SailPoint | Architect | Professional Services | 50 | 50 | 0 | 0 | 35 | 15 | 2024-02-19 |  | signedoff
98 | Identity | Shilpi | UAE | EDC | SailPoint | Engineer | Professional Services | 83.5 | 80 | 3.5 | 0 | 46 | 37.5 | 2024-02-19
99 | Identity | Niraj Joshi | UAE | EDC | SailPoint | Engineer | Professional Services | 17.5 | 17.5 | 0 | 0 | 41 | -23.5 | 2024-02-19
100 | Identity | Vamshi | UAE | SIB | IIQ- Upgrade 8.1 to 8.4 P | Architect | Professional Services | 11 | 4 | 7 | 0 | 0 | 11 | 2024-10-03 | 2025-01-10 |  | Kick-off Done
101 | Identity | Niraj Joshi | UAE | SIB | IIQ- Upgrade 8.1 to 8.4 P | Engineer | Professional Services | 11 | 3 | 8 | 0 | 0 | 11 | 2024-10-03
102 | Identity | Preshit Ghode | India | SIB | IIQ- Upgrade 8.1 to 8.4 P | Engineer | Professional Services | 17 | 0.5 | 16.5 | 0 | 0 | 17 | 2024-10-03
103 | Identity | Sandeep Dwivedi | UAE | SIB | FAM - Upgrade | Architect | Professional Services | 4 | 1 | 3 | 0 | 0 | 4 | 2024-10-03
104 | Identity | Vamshi | UAE | ZAND Bank | ZAND - SailPoint Enhancement | Technical Consultant | Professional Services | 13 | 13 | 0 | 104 | 13 | 0 | 2024-09-30 | 2024-11-01 |  | signed off
105 | Identity | Vamshi | UAE | ZAND Bank | ZAND - SailPoint Enhancement | Architect | Professional Services | 5 | 5 | 0 | 40 | 5 | 0 | 2024-09-30
106 | Identity | Karthikeyan Subramanian | UAE | QIB | QIB Phase 3 SailPoint | Architect | Professional Services | 33 | 8.1 | 24.9 | 138 | 17.25 | 15.75 | 2023-04-01 | 2023-07-30 |  | On Hold
107 | Identity | Rakesh Vadnala | UAE | QIB | QIB Phase 3 SailPoint | Engineer | Professional Services | 2 | 0 | 2 | 0 | 0 | 2 | 2023-04-01
108 | Identity | Shilpi | UAE | QIB | QIB Phase 3 SailPoint | Engineer | Professional Services | 45 | 12 | 33 | 113 | 14.125 | 30.88 | 2023-04-01
109 | Identity | Saurabh Bharadwaj | UAE | ADCB - SAPsuccessfactor and CR | SAP Success Factor Enhancement | Architect | Professional Services | 25 | 25 | 0 | 320 | 40 | -15 | 2024-09-04 |  | 2025-02-06 | Completed
110 | Identity | Rakesh Vadnala | UAE | ADCB - SAPsuccessfactor and CR | SAP Success Factor Enhancement | Engineer | Professional Services | 25 | 25 | 0 | 352 | 44 | -19 | 2024-09-04 |  | 2025-02-06
111 | Identity | Rushikesh Chaudhari | India | ADCB - SAPsuccessfactor and CR | SAP Success Factor Enhancement | Engineer | Professional Services | 5 | 5 | 0 | 317 | 39.625 | -34.63 | 2024-09-04 |  | 2025-02-06
112 | Identity | Kavin | UAE | Presidential Flights | PF Cyberark | Sr. Technical Consultant | Professional Services | 2 | 2 | 0 |  |  |  | 2024-10-07 | 2024-12-11 | Signed off
113 | Identity | Shashant | India | Presidential Flights | PF Cyberark | Sr. Technical Consultant | Professional Services | 2 | 2 | 0 |  |  |  | 2024-10-07
114 | Identity | Rakesh Vadnala | UAE | Katim | Katim LLC | Technical Consultant | Professional Services | 15 | 15 | 0 |  |  |  | 2024-11-25 | 2024-12-16
115 | Identity | Sandeep Dwivedi | UAE | SIB FAM | SailPoint | Tech-ops Manager | Professional Services | 19 | 3 | 16 |  |  |  | 2024-06-21 | 2025-06-20
116 | Identity | Preshit Ghode | India | SIB FAM | SailPoint | Consultant | Professional Services | 2 | 0 | 2 |  |  |  | 2024-06-21 | 2025-06-20
117 | Identity | Vaishnavi Makarand | India | DIB Support | SailPoint | Consultant | Support | 10 | 10 | 0 |  |  |  | 2024-12-31 | 2025-12-30
118 | Identity | Sandeep Dwivedi | UAE | DIB Support | SailPoint | Tech-ops Manager | Support | 5 | 5 | 0 |  |  |  | 2024-12-31 | 2025-12-30
119 | Identity | Preshit Ghode | India | SIB Support | SailPoint | Consultant | Support | 2 | 0 | 1 |  |  |  | 2024-06-21 | 2025-06-20
120 | Identity | Sandeep Dwivedi | UAE | SIB Support | SailPoint | Tech-ops Manager | Support | 19 | 3 | 16 |  |  |  | 2024-06-21 | 2025-06-20
121 | Identity | Preshit Ghode | India | AXA Support | SailPoint | Consultant | Support | 27 | 10 | 17 |  |  |  | 2024-11-05 | 2025-11-04
122 | Identity | Sandeep Dwivedi | UAE | AXA Support | SailPoint | Tech-ops Manager | Support | 16 | 12 | 0 |  |  |  | 2024-11-05 | 2025-11-04
123 | Identity | Rushikesh Chaudhari | India | AXA Support | SailPoint | Consultant | Support | 4 | 4 | 0 |  |  |  | 2024-11-05 | 2025-11-04
124 | Identity | Preshit Ghode | India | AXA CR | SailPoint | Consultant | Professional Services | 7 | 7 | 0
125 | Identity | Sandeep Dwivedi | UAE | AXA CR | SailPoint | Tech-ops Manager | Professional Services | 1 | 1 | 0
126 | Identity | Rushikesh Chaudhari | India | AXA CR | SailPoint | Consultant | Professional Services | 30 | 30 | 0
127 | Identity | Karthik NSP | UAE | AXA CR | SailPoint | Senior Consultant | Professional Services | 30 | 30 | 0
128 | Identity | Sandeep Dwivedi | UAE | Tawazun Support | SailPoint | Tech-ops Manager | Support | 1 | 0 | 1 |  |  |  | 2024-09-30 | 2025-09-29
129 | Identity | Niraj Joshi | UAE | Tawazun Support | SailPoint | Consultant | Support | 2 | 1 | 1 |  |  |  | 2024-09-30 | 2025-09-29
130 | Identity | Rakesh Vadnala | UAE | Tawazun Support | SailPoint | Consultant | Support | 2 | 2 | 0 |  |  |  | 2024-09-30 | 2025-09-29
131 | Identity | Vaishnavi Makarand | India | Tawazun Support | SailPoint | Consultant | Support | 2 | 2 | 0 |  |  |  | 2024-09-30 | 2025-09-29
132 | Identity | Srikant Bavandla | UAE | Tawazun Support | SailPoint | Architect | Support | 1 | 1 | 0 |  |  |  | 2024-09-30 | 2025-09-29
135 | Identity | Hrushikesh Ubale | India | PHCC Support | SailPoint | Consultant | Support | 15 | 8 | 7 |  |  |  | 2023-03-02 | 2026-03-02
136 | Identity | Sandeep Dwivedi | UAE | PHCC Support | SailPoint | Tech-ops Manager | Support | 4 | 0 | 4 |  |  |  | 2023-03-02 | 2026-03-02
137 | Identity | Shashant | India | Sukoon Insurance (24-25) | Cyberark | Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 2024-11-24 | 2025-11-24
138 | Identity | Kavin | UAE | Sukoon Insurance (24-25) | Cyberark | Sr. Technical Consultant | Support | 8 | 1 | 7 |  |  |  | 2024-11-24 | 2025-11-24
139 | Identity | Sandeep Dwivedi | UAE | ADJD | Cyberark | Tech-ops Manager | Support | 1 | 0 | 1 |  |  |  | 2023-09-12 | 2024-09-11
140 | Identity | Niraj Joshi | UAE | ADMC Support | SailPoint | Technical Consultant | Support | 208 | 0 | 208 |  |  |  | Not Started | Not Started
141 | Identity | Sandeep Dwivedi | UAE | DMT Support | SailPoint | Tech-ops Manager | Support | 2 | 1 | 1 |  |  |  | 2024-11-01 | 2025-10-31
142 | Identity | Rushikesh Chaudhari | India | DMT Support | SailPoint | Engineer | Support | 14 | 2 | 12 |  |  |  | 2024-11-01 | 2025-10-31
143 | Identity | Kavin | UAE | ADEK PAM | ADEK CyberArk | Sr. Technical Consultant | Professional Services | 9.2 | 10 | -0.8 |  | 7.25 | 1.95 | 2023-10-30 | 2024-12-13 | 2024-12-13
144 | Identity | Shashant | India | ADEK PAM | ADEK CyberArk | Technical Consultant | Professional Services | 25.8 | 31.2 | -5.4 |  | 26.46 | -0.66 | 2023-10-30 | 2024-12-13
145 | Identity | Kavin | UAE | OQ Trading PAM | OQ Trading CyberArk | Sr. Technical Consultant | Professional Services | 6 | 1.5 | 4.5 |  | 1 | 5 | 2023-12-18 | TBD | Received conditional sign off
146 | Identity | Shashant | India | OQ Trading PAM | OQ Trading CyberArk | Technical Consultant | Professional Services | 14 | 6.5 | 7.5 |  | 5 | 9 | 2023-12-18 | TBD
147 | Identity | Kavin | UAE | ADNEC PAM | ADNEC CyberArk | Sr. Technical Consultant | Professional Services | 7 | 24 | -17 |  | 24.31 | -17.31 | 2023-07-20 | 2024-12-05 | Signed off
148 | Identity | Shashant | India | ADNEC PAM | ADNEC CyberArk | Technical Consultant | Professional Services | 7 | 21 | -14 |  | 19.31 | -12.31 | 2023-07-20 | 2024-12-05
149 | Identity | Kavin | UAE | ADNEC PAM | ADNEC CyberArk 3 months onsite engagement | Sr. Technical Consultant | Professional Services | 66 | 66 | 0 |  | 53.87 | 12.13 | 2024-05-27 | 2024-08-26
150 | Identity | Kavin | UAE | DOH PAM | DOH CyberArk | Sr. Technical Consultant | Professional Services | 15 | 15 | 0 |  | 2.75 | 12.25 | 2019-10-27 | 2024-09-12 | Signed off
151 | Identity | Shashant | India | DOH PAM | DOH CyberArk | Technical Consultant | Professional Services | 23 | 21 | 2 |  | 15.5 | 7.5 | 2019-10-27 | 2024-09-12
152 | Identity | Shashant | India | ZMI PAM | ZMI - P Cloud | Technical Consultant | Professional Services | 17.5 | 17.5 | 0 |  | 9.8 | 7.7 | 2024-07-16 | 2024-11-12 | Signed off
153 | Identity | Kavin | UAE | ZMI PAM | ZMI - P Cloud | Sr. Technical Consultant | Professional Services | 2.5 | 2.5 | 0 |  | 0 | 2.5 | 2024-07-16 | 2024-11-12
154 | Identity | Shashant | India | Nextcare PAM | Nextcare - BT | Technical Consultant | Professional Services | 10 | 0.05 | 9.95 |  | 0 | 10 | 2024-08-16
155 | Identity | Kavin | UAE | Nextcare PAM | Nextcare - BT | Sr. Technical Consultant | Professional Services | 19 | 0.05 | 18.95 |  | 0 | 19 | 2024-08-16
156 | Identity | Rushikesh Chaudhari | India | ADCB Phase 2 Support | ADCB | Engineer | Support | 30 | 17 | 13 |  |  |  | 2024-11-01 | 2024-10-31
157 | Identity | Kavin | UAE | OQ trading Support | Cyberark | Sr. Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 10-Aug-24 | 9-Aug-25
158 | Identity | Shashant | India | OQ trading Support | Cyberark | Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 10-Aug-24 | 9-Aug-25
159 | Identity | Kavin | UAE | OQ trading Support | Cyberark | Sr. Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 2024-11-24 | 2025-11-23
160 | Identity | Shashant | India | OQ trading Support | Cyberark | Technical Consultant | Support | 8 | 0 | 8 |  |  |  | 2024-11-24 | 2025-11-23
161 | Identity | Kavin | UAE | Adek Support (Unlimited tickets) | Cyberark | Sr. Technical Consultant | Support | 36 | 0 | 36 |  |  |  | 2024-12-27 | 2027-12-26
162 | Identity | Shashant | India | Adek Support (Unlimited tickets) | Cyberark | Technical Consultant | Support | 36 | 1 | 35 |  |  |  | 2024-12-27 | 2027-12-26
163 | Identity |  |  | Intigral SailPoint Support | SailPoint |  | Support | 6 | 0 | 6
164 | Identity | Shilpi | UAE | Mashreq Support - 5 month | SailPoint | Engineer | Support | 7 | 7 | 0 |  |  |  | 2024-10-09 |  |  | Started in November 2024
165 | Identity | Amala Sunny | UAE | Mashreq Support - 5 month | SailPoint | Engineer | Support | 8 | 8 | 0 |  |  |  | 2024-10-09
166 | Identity | Preshit Ghode | India | Mashreq Support - 5 month | SailPoint | Engineer | Support | 92 | 44 | 48 |  |  |  | 2024-10-09 |  |  | Started in November 2024
167 | Identity | Kavin | UAE | Presidential Flights | Cyberark | Technical Consultant | Support | 10 | 0 | 10 |  |  |  | 2024-12-11 | 2025-12-10
168 | Identity | Kavin | UAE | Sukoon Insurance | Cyberark | Sr. Technical Consultant | Support | 8 | 3.4 | 4.6 |  |  |  | 2023-11-24 | 2024-11-23
169 | Identity | Shashant | India | Sukoon Insurance | Cyberark | Technical Consultant | Support | 8 | 3.8 | 4.2 |  |  |  | 2023-11-24 | 2024-11-23
170 | Identity | Kavin | UAE | Damac | Cyberark | Sr. Technical Consultant | Support | 15 | 0.5 | 14.5 |  |  |  | 2023-05-12 | 2025-05-11
171 | Identity | Shashant | India | Damac | Cyberark | Technical Consultant | Support | 15 | 6.3 | 8.7 |  |  |  | 2023-05-12 | 2025-05-11
172 | Identity | Shashant | India | ADJD | Cyberark | Technical Consultant | Support | 3 | 1.3 | 1.7 |  |  |  | 2023-09-11 | 2024-09-11
173 | Identity | Kavin | UAE | ADJD | Cyberark | Sr. Technical Consultant | Support | 3 | 0.7 | 2.3 |  |  |  | 2023-09-11 | 2024-09-11
174 | Identity | Sandeep Dwivedi | UAE | Carrefour (24-25) | SailPoint | Tech-ops Manager | Support | 10 | 10 | 0
175 | Identity | Rakesh Vadnala | UAE | Carrefour (24-25) | SailPoint | Consultant | Support | 18 | 18 | 0
176 | Identity | Hrushikesh Ubale | India | Carrefour (24-25) | SailPoint | Consultant | Support | 12 | 12 | 0
177 | Identity | Sandeep Dwivedi | UAE | NI Support | SailPoint | Tech-ops Manager | Support | 4 | 4 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
178 | Identity | Kanchan Mishra | UAE | NI Support | SailPoint | Senior Architect | Support | 6 | 6 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
179 | Identity | Swapnil Deka | UAE | NI Support | SailPoint | Consultant | Support | 60 | 60 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
180 | Identity | Saurabh Bharadwaj | UAE | NI Support | SailPoint | Consultant | Support | 0.5 | 0.5 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
181 | Identity | Rakesh Vadnala | UAE | NI Support | SailPoint | Consultant | Support | 0.5 | 0.5 | 0 | [6 empty] | We don’t have support contract for NI but we are still he issues/inicdents being reported by customer
182 | Identity | Shilpi | UAE | EDC | SailPoint | Technical Consultant | Support | 132 | 0 | 132 | [6 empty] | 1 Year = Remote Shared Managed Support (8/5). The Assigned resource should be handling min 2 similar customer's.
183 | Identity | Rushikesh Chaudhari | India | AXA CR Support | SailPoint | Consultant | Support | 2 | 2 | 0
184 | Identity | Karthik NSP | UAE | AXA CR Support | SailPoint | Consultant | Support | 8 | 8 | 0
185 | Identity | Preshit Ghode | India | AXA CR Support | SailPoint | Consultant | Support | 7 | 7 | 0
186 | Identity | Sandeep Dwivedi | UAE | AXA CR Support | SailPoint | Consultant | Support | 4 | 4 | 0
187 | Identity | Hrushikesh Ubale | India | Aldar Support | SailPoint | Consultant | Support | 80 | 80 | 0 |  |  |  | 2024-07-13 | 2025-07-30
188 | Identity | Sandeep Dwivedi | UAE | Aldar Support | SailPoint | Tech-ops Manager | Support | 16 | 16 | 0
189 | Identity | Hrushikesh Ubale | India | Aldar Support 200 hours Support | SailPoint | Consultant | Support | 25 | 25 | 0
190 | Identity | Sandeep Dwivedi | UAE | NI -UAE FAM Upgrade | SailPoint | Tech-ops Manager | Support | 5 | 5 | 0
191 | Identity | Karthik NSP | UAE | NI -UAE FAM Upgrade | SailPoint | Tech-ops Manager | Support | 5 | 5 | 0
192 | Identity | Preshit Ghode | India | NI -UAE FAM Upgrade | SailPoint | Consultant | Support | 12 | 12 | 0
195 | Identity | Sandeep Dwivedi | UAE | Airtel Support | SailPoint | Tech-ops Manager | Support | 70 | 70 | 0
196 | Identity | Chaitanya Kulkarni | India | Airtel Support | SailPoint | Consultant | Support | 70 | 70 | 0
197 | Identity | Amala Sunny | UAE | Airtel Support | SailPoint | Consultant | Support | 55 | 55 | 0
198 | Identity | Hrushikesh Ubale | India | Airtel Support | SailPoint | Consultant | Support | 70 | 70 | 0
199 | Identity | Suraj Kalamkar | UAE | Airtel Support | SailPoint | Consultant | Support | 139 | 139 | 0
200 | Identity | Mahipal Jadhav | India | Airtel Support | SailPoint | Consultant | Support | 139 | 139 | 0
201 | Identity | Ajit Rathod | UAE | Airtel Support | SailPoint | Consultant | Support | 139 | 139 | 0
202 | Identity | Priyanka Jagnade | India | Airtel Support | SailPoint | Consultant | Support | 139 | 139 | 0
203 | Identity | Rushikesh Jadhav | India | Airtel Support | SailPoint | Consultant | Support | 139 | 139 | 0
204 | Identity | Sandeep Dwivedi | UAE | Ni UAE FAM Upgrade | SailPoint | Technical Manager | Professional Services | 2 | 0 | 2 | 14 | 1.75 | 0.25 | 2024-07-03 | 2024-07-30
205 | Identity | Karthik NSP | UAE | Ni UAE FAM Upgrade | SailPoint | Sr Consultant | Professional Services | 2 | 0 | 2 | 24 | 3 | -1
206 | Identity | Preshit Ghode | India | Ni UAE FAM Upgrade | SailPoint | Engineer | Professional Services | 17 | 15 | 2 | 138 | 17.25 | -0.25
207 | Identity | Vendor (Shifra) | UAE | Intigral Delinia | PAM | Consultant | Support |  |  | 0
208 | Identity | Chaitanya Kulkarni | India | Airtel Phase 2A - Multisite Installation | Forgerock | Architect | Professional Services | 10 | 10 | 0
209 | Identity | Vinod | UAE | D 14 | Sailpoint | Consultant | Support | 264 | 244 | 20
210 | Identity | Rakesh Vadnala | UAE | D14 | Sailpoint | Consultant | Support | 12 | 12 | 0
211 | Identity | Aishwary Kumar | UAE | D14 | Sailpoint | Consultant | Support | 10 | 10 | 0

## Extra (hidden)
S.No | Department | Resource | Location | Customer Name | Project Name | Role | Engagement Type | Allocated Billed Days2025 | Utilized Billed Days(Project plan)2025 | Remaining Billed Days(Project plan) | Utilized Billed hrs (Zoho) | Utilized Billed days (Zoho) | Remaining Billed Days (Zoho) | Project Start Date | Project End Date | Revised End Date | Comments
1 | Identity | Sandeep Dwivedi | UAE | NI Egypt- Log movement | SailPoint | Tech-ops Manager | Support | 1 | 1 | 0
2 | Identity | Preshit Ghode | India | NI Egypt- Log movement | SailPoint | Consultant | Support | 5 | 5 | 0
3 | Identity | Sandeep Dwivedi | UAE | Ni UAE FAM Upgrade | SailPoint | Technical Manager | support | 5 | 5 | 0
4 | Identity | Karthik NSP | UAE | Ni UAE FAM Upgrade | SailPoint | Sr Consultant | support | 5 | 5 | 0
5 | Identity | Preshit Ghode | India | Ni UAE FAM Upgrade | SailPoint | Engineer | support | 12 | 3 | 9
6 | Identity | Shashant Turkar |  | ADNEC CyberArk |  |  |  | 0 | 0.5 | -0.5