## AMC Master (hidden)
PROJECT MANAGEMENT LOG TEMPLATE
PROJECT REGISTER
The PROJECT Identification portion of this table will automatically populate to the Financial Data, Deliverables and Performance, and Risk Register tabs within this workbook.
| PROJECT DATA | [12 empty] | ACCOUNT DATA |  | PROJECT MANAGEMENT
a | NO. | PROJECT ID | Type | Statius | Tower | Project Type | PROJECT NAME | Type of Payment | Suppot By | Recd Date | CUSTOMER NAME | CUSTOMER SPOC NAME | CUSTOMER SPOC EMAIL | ACCOUNT MANAGER NAME | ACCOUNT HEALTH | INTERNAL PROJECT MANAGER | Status | Scope & Support Model | SLAs | Total Health Checks | HC Completed | HC Due | Open Health Checks | Closed Health Checks | No. Incident Tickets | Open Incident Tickets | Closed Incident Tickets | START DATE | END DATE | Payment for | Term | Billing Forecast Month | Biling Status | Invoice Date | Billing Amount | Payment Satus | Forecast Revenue | Paid Date | Payment Terms
| 1 | RN-146 | Ongoing | AMC will start from 20 Feb 24 | N&S | Checkpoint | Intigral Middle East-Checkpoint | Upon delivery of licenses | RNS |  | Intigral Middle East | Selva | Selva.Rathinam@intigral.net | Ishan Arora | GREEN | Pallavi Nair | On Track | 2 HC and 6 Incidents |  | 2 | 1 | 1 | 1 | 1 | 6 | 0 | 0 | 2024-02-20 | 2025-02-19 |  |  | 2024-01-01 | Complete | 2024-01-31 | 136500 |  |  |  | Full Invoice upon delivery of licenses
| 2 | RN-165 | Ongoing | 3 Yr Contract - will start from 23 Feb 24 | N&S | Barracuda | Al Dhaffra - Barracuda WAF |  | RNS |  | Al Dhaffra Insurance | Alaa Saad | alaa.saad@aldhafrainsurance.ae | Bibinu | GREEN | Pallavi Nair | On Track | 3 Yrs - 6 Preventive and 8 Incidents |  | 6 | 1 | 1 | 7 | 1 | 8 | 0 | 0 | 2024-02-23 | 2027-02-22 |  |  | 2024-02-01 | Complete | 2024-02-13 | 116301 |  |  |  | Full Invoice upon delivery of licenses / Product
| 3 | RN-218 | Ongoing | Renewed in 24 | EDR | ivanti | OQ Trading - Ivanti |  | RNS |  | OQ Trading | Aathif Niyas | mohamed.aathif@oq.com | Ranjith George | GREEN | Pallavi Nair | On Track | 4 HCs and 6 Incidnets |  | 4 | 1 | 2 | 2 | 1 | 6 | 0 | 0 | 2024-01-11 | 2025-01-10 |  |  | 2024-01-01 | Complete | 2024-01-18 | 3095 |  |  |  | Quarterly payment after each HC
|  | RN-218 |  | Renewed in 24 | EDR | ivanti | OQ Trading - Ivanti |  | RNS |  | OQ Trading | Aathif Niyas | mohamed.aathif@oq.com | Ranjith George | GREEN | Pallavi Nair | On Track | 4 HCs and 6 Incidnets |  | 4 | 1 | 2 | 2 | 1 | 6 | 0 | 0 | 2024-01-11 | 2025-01-10 |  |  | 2024-01-01 | Complete | 2024-01-18 | 3095 |  |  |  | Quarterly payment after each HC
|  | RN-218 |  | Renewed in 24 | EDR | ivanti | OQ Trading - Ivanti |  | RNS |  | OQ Trading | Aathif Niyas | mohamed.aathif@oq.com | Ranjith George | GREEN | Pallavi Nair | On Track | 4 HCs and 6 Incidnets |  | 4 | 1 | 2 | 2 | 1 | 6 | 0 | 0 | 2024-01-11 | 2025-01-10 |  |  | 2024-01-01 | Complete | 2024-01-18 | 3095 |  |  |  | Quarterly payment after each HC
|  | RN-218 |  | Renewed in 24 | EDR | ivanti | OQ Trading - Ivanti |  | RNS |  | OQ Trading | Aathif Niyas | mohamed.aathif@oq.com | Ranjith George | GREEN | Pallavi Nair | On Track | 4 HCs and 6 Incidnets |  | 4 | 1 | 2 | 2 | 1 | 6 | 0 | 0 | 2024-01-11 | 2025-01-10 |  |  | 2024-01-01 | Complete | 2024-01-18 | 3095 |  |  |  | Quarterly payment after each HC
| 5 | RN-351 | Ongoing | New AMC | Data Sec | ForcePoint, FP | Aldar Properties PJSC_Dec 23 |  | RNS | 2023-12-06 |  |  |  | Bibinu | GREEN | Sean Faizal | On Track | 6 Incidents for 15 months |  | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 2023-12-28 | 2025-03-27 |  |  | 2023-12-01 | Complete | 2023-12-14 | 596961.36
|  | RN-351 |  |  | Data Sec | ForcePoint, FP | Aldar Properties PJSC_Dec 23 |  | RNS | 2023-12-06 |  |  |  | Bibinu | GREEN | Sean Faizal | On Track | 6 Incidents for 15 months | [6 empty] | 6 |  |  | 2023-12-28 | 2025-03-27 |  |  | 2024-06-01 |  |  | 5250
| 6 | RN-267 | Yet to Start | Will start after PS is complete | Identity | Sailpoint | DOH-Sailpoint |  | RNS |  | DOH |  |  | Bibinu |  | Pallavi Nair | Not Started | 1 HC and 7 Incidents per year |  | 1 |  |  |  |  | 7 | [7 empty] | Complete | 2023-06-12
| 7 | RN-268 | Yet to Start | Will start after PS is complete | Identity | Sailpoint | QIB-Sailpoint |  | RNS |  | QIB |  |  | Deepinder |  | Sean Faizal | Not Started | 1 HC and 9 Incidents per year |  | 1 |  |  |  |  | 7 | [6 empty] | TBD |  |  | 41625
|  | New | Yet to Start | Will start after PS is complete | Identity | Sailpoint | QIB-Sailpoint |  | RNS |  | QIB |  |  | Deepinder |  | Sean Faizal | Not Started | 1 HC and 9 Incidents per year |  | 1 |  |  |  |  | 7 | [6 empty] | TBD |  |  | 41625
| 8 | RN-417 | Yet to Start | Will start after PS is complete | N&S | Fortinet | Gargash_FortiGate Firewall 100F X 2_2023+ FortiAnalyser APL |  | RNS |  | Gargash Group | Bilal Lodhia |  | Ranjit George Mathew |  | Pallavi Nair | Not Started | 1 Year from PS Sign-off. 2 HCs and 4 Incidents |  | 2 |  |  |  |  | 4 | [6 empty] | 2024-04-01 |  |  | 3477.6 |  |  |  | 50% to be invoiced in advance and 50% upon sign-off. This can be invoiced, once the PS is complete.
| 4 | RN-213 | Ongoing | Renewed from 19 Feb 24 | Data Sec | Forcepoint DLP Boldenjames | Intigral-Forcepoint and Boldonjames |  | RNS | 2024-02-01 | Intigral Middle East | Selva | Selva.Rathinam@intigral.net | Ishan Arora | GREEN | Pallavi Nair | On Track | 2HC and 10 Incidents |  | 2 | 1 | 1 | 1 | 1 | 10 | 0 | 9 | 2024-02-19 | 2025-02-18 |  |  | 2024-02-01 | Complete |  | 121500 |  |  |  | 100% to be invoiced upon delivery of licenses
| 5 | RN-151 | Ongoing | Renewed from 16 Mar 24 | EDR | ivanti | SIB_Sharjah Islamic Bank-Ivanti |  | RNS |  | SIB |  |  | Ishan Arora | GREEN | Pallavi Nair | On Track | 3 INCIDENTS |  | 0 | NA | NA | NA | NA | 3 | 0 | 1 | 2024-03-16 | 2025-03-15 |  |  | 2024-03-01 | Complete | 2024-03-12 | 2373 |  |  |  | 50% on license
|  | RN-151 | Ongoing | Renewed from 16 Mar 24 | EDR | ivanti | SIB_Sharjah Islamic Bank-Ivanti |  | RNS |  | SIB |  |  | Ishan Arora | GREEN | Pallavi Nair | On Track | 3 INCIDENTS |  | 0 | NA | NA | NA | NA | 3 | 0 | 1 | 2024-03-16 | 2025-03-15 |  |  | 2024-09-01 |  |  | 2373 |  |  |  | and 50% after 6 months.
| 11 | RN-157 | Ongoing | will end on 04 Nov 24 | Identity | Sailpoint | AXA GULF INSURANCE GROUP (GULF) B S C DUBAI BRANCH_SailPoint_Renewal 23-24_Nov_2023 | SailPoint License Renewal 2023-2024 | RNS | 2023-10-03 | AXA | Niyaj Khan | Niyaj.khan.ext@gig-gulf.com | Ishan | GREEN | Pallavi Nair | On Track | 1000 Licenses & 8 incidents |  | 0 | NA | NA | NA | NA | 8 | 0 | 8 | 2023-11-05 | 2024-11-04 |  |  | 2023-11-01 | Complete |  | 36800 |  |  |  | 100% invoice upon license delivery
| 13 | RN-182 | Ongoing | Renewed from 24 Nov 23 | PAM | CyberArc | Oman / Sukoon Insurance - Cyberark |  | RNS |  | Oman / Sukoon Insurance | Jameel Ahamed | Jameel.Ahamed@sukoon.com | Ishan Arora | GREEN | Pallavi Nair | On Track |  |  | 2 |  |  |  |  | 6 |  |  | 2023-11-24 | 2024-11-23 |  |  | 2023-12-01 | Complete | 2023-12-12 | 11040 | Paid |  |  | To be Invoiced upon delivery of Licenses
| 14 | RN-214 | Ongoing | AMC Renewed in Dec 23 | Data Sec | ForcePoint, FP | Alef Education - Forcepoint DLP |  | RNS | 2023-12-13 | Alef Education | Srikant | srikant.dasondhi@alefeducation.com | Bibinu | GREEN | Pallavi Nair | On Track | 2 HCs and 4 Incidents |  | 2 | 0 | 2 | 2 | 0 | 4 | 1 | 7 | 2023-12-14 | 2024-12-13 |  |  | 2023-12-01 | Complete | 2023-12-28 | 231999 | Paid |  |  | To be Invoiced upon delivery of Licenses
| 15 | RN-204 | Ongoing |  | EDR | McAfee | Mashreq - McAfee |  | RNS |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Track |  |  | 2 | 1 | 1 | 1 | 1 | 12 | 0 | 5 | [5 empty] | Complete |  | 38640 | Paid
| 16 | RN-225 | Yet to Start | Will start after PS is complete | N&S | Zscaler | Mashreq - zscaler | 1 Yr Contract | RNS |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Hold |  |  | 2 |  |  |  |  | 12 | [7 empty] | Complete |  | 43000 | Paid
| 17 | RN-148 | Ongoing |  | EDR | ivanti | Ajman Bank PJSC - ivanti | 2 Yr Contract | RNS |  | Ajman Bank PJSC | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | GREEN | Sean Faizal | On Track | 2 HCs and 4 Incidents |  | 2 | 1 | 1 | 1 | 1 | 4 | 0 | 2 | 2023-01-14 | 2025-01-14 |  |  |  | Complete |  | 32780 | Paid
| 18 | RN-210 | Ongoing | AMC Kickstarted | Data Sec | ForcePoint, FP | Ajman Bank - ForcePoint-DLP | 3 Yr Contract | RNS |  | Ajman Bank | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | GREEN | Sean Faizal | On Track | 4 HC and Unlimited support |  | 4 | 0 | 1 | 4 | 0 |  |  |  | 2024-05-10 | 2027-05-09 |  |  | 2024-04-01 | Complete | 2024-04-25 | 51047
| 6 | RN-397 | Ongoing | New AMC | Data Sec | ForcePoint, FP | DIB - Forceoint DLP, Web Security & RBI |  | RNS |  | DIB | Tarique Hussain |  | Ishan Arora | GREEN | Sean Faizal | On Track | Forcepoint - 12 INC, 4 HCS WEB SECURITY - Unlimited INCs, 4 HCs RBI- 18 INCs | DLP and Web Security in progress RBI Not started | 4 | 1 | 1 | 3 | 1 | Unlimmited | NA | NA | 2024-01-01 | 2024-12-31 |  |  | 2024-02-01 | Complete | 2024-02-21 | 358600 |  |  |  | 100% to be invoiced upon delivery of licenses
| 7 | RN-121 | Ongoing | Renewed in Dec 23 | EDR | Tripwire | Mashreq - Tripwiire |  | RNS |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Track | 4 HCs and unlimited incident support |  | 4 | 1 | 1 | 3 | 1 |  |  |  | 2024-01-01 | 2024-12-31 |  |  | 2024-01-01 | Complete |  | 275000 | Paid |  |  | 100% to be invoiced upon delivery of licenses
| 21 | RN-264 | Ongoing | Will end on 22 Aug 24 | N&S | Opswat | Mashreq - Opswat |  | Vendor |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Track | 2 HCs and 6 Incidents |  | 2 | 0 | 1 | 2 | 0 | 6 |  |  | 2023-08-23 | 2024-08-22 |  |  | 2023-07-01 | Complete |  | 33120 | Paid
| 24 | RN-388 | Ongoing | Renewed from 18 Dec 23 | EDR | McAfee | Ajman Bank McAfee |  | RNS |  | Ajman Bank | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | GREEN | Sean Faizal | On Track | 2 HCs and 10 incident |  | 2 | 1 | 1 | 1 | 1 | 10 | 0 | 5 | 2023-12-31 | 2024-12-30 |  |  | 2023-11-01 | Complete |  | 144732 |  |  |  | 100% to be invoiced upon delivery of licenses
| 25 | RN-386 | Ongoing | Will end on 13 Nov 24 | EDR | Tripwire | Emirates Airlines - Tripwire | Enterprise Support and AMC | RNS |  | Emirates Airlines | Durgesh Kumar | durgeshkumar.saraswat@dnata.com | Ishan Arora | GREEN | Sean Faizal | On Track | 2 HCs and 4 Incidents |  | 2 | 1 | 1 | 1 | 1 | 4 | 0 | 3 | 2023-11-14 | 2024-11-13 |  |  | 2023-11-01 | Complete |  | 83000 |  |  |  | 100% to be invoiced upon delivery of licenses
| 26 | RN-217 | Yet to Start | Will start after PS is complete | Data Sec | ForcePoint, FP | Emrill - Forcepoint DLP and BJM |  | RNS |  | Emrill | Atif Riaz | Atif.Riaz@emrill.com | Rohit Suresh Save | GREEN | Pallavi Nair | Not Started |  |  | 2 |  |  |  |  | 4 |  |  | 2021-12-23 | 2024-12-22 |  |  |  | Complete |  | 26496 |  |  |  | Invoiced, but not paid. Inform Ops team, once the sign-off is received to clear the outstanding invoice of AMC
| 8 | RN - 272 | Ongoing | Renewed from 27 Mar 24 | N&S | Checkpoint | Brandfolio-Checkpoint |  | RNS |  | Brandfolio | Jacob John | jacob@brand-foliollc.com | Ranjith George | GREEN | Pallavi Nair | On Track | 2 HCs and 4 Incidents |  | 2 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 2024-03-28 | 2025-03-27 |  |  | 2024-03-01 | Complete | 2024-03-29 | 6000 |  |  |  | Invoiced fully
| 9 | RN-255 | Ongoing | Renewed on 09 Feb 24 | Email Sec | Proofpoint | EPC-Proofpoint | 100% on License delivery AMC - upon sign off of HC | RNS | 2024-02-01 | EPC | Jinson Papachan | jinson@epc.ae | Faizan | GREEN | Pallavi Nair | On Track | 1 Preventive + 5 Incidents / year |  | 1 | 1 | 0 | 0 | 1 | 5 | 1 | 1 | 2024-02-09 | 2025-02-08 |  |  | 2024-02-01 | Complete | 2024-02-28 | 120418 - Licenses 4907 - AMC |  |  |  | Total invoicing is complete
| 30 | RN-281 | Ongoing |  | N&S | Fortigate | Dubai Sports Council (DSC) - FortiGate |  | RNS | [5 empty] | GREEN | Vignesh | On Track | 2 HCs and 6 Incidents in a year |  | 2 | 1 |  | 1 | 1 | 6 | 1 | 5 | 2023-08-01 | 2024-07-31 |  |  | 2023-06-01 | COMPLETE | 2023-06-16 | 19740
| 10 | RN-269 | Ongoing | 3 Yr Contract | Identity | Sailpoint | PHCC-Sailpoint | 3 Yrs contract from 23 | RNS |  | PHCC |  |  |  | GREEN | Pallavi Nair | On Track | 1 HC per year, 7 incidents |  | 1 |  |  |  |  | 7 |  |  | 2024-03-01 | 2025-02-28 |  |  | 2024-04-01 |  |  | 6000
|  | RN-269 | Yet to Start | 3 Yr Contract |  | Sailpoint | PHCC-Sailpoint |  | RNS |  | PHCC |  |  |  |  | Pallavi Nair | On Track | 1 HC per year, 7 incidents |  | 1 |  |  |  |  | 7 |  |  | 2025-03-01 | 2026-02-28 |  |  | 2025-03-01 |  |  | 6000
| 32 | RN-215 |  | Ongoing | PAM | CyberArc | Damac-Cyberark |  | RNS |  | Damac | Rajesh Narayan | Rajesh.Narayanan@damacgroup.com | Bibinu | GREEN | Pallavi Nair | On Track | 12 IS |  | 0 |  |  |  |  | 12 |  |  | 2024-05-12 | 2025-05-11 |  |  |  | Complete
| 35 | RN-161 |  | Ongoing | EDR | Tenable | Department of Finance (DOF) - Tenable |  | RNS |  |  |  |  | Bibinu | GREEN | Pallavi Nair | On Track | 10 calls |  | 0 | [7 empty] | 2024-05-09 | 2025-05-08 |  |  | 2023-10-01 | COMPLETE |  | 18000
| 36 | RN-245 | Ongoing | will end on 02 Aug 24 | Data Sec | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  | Haytham | GREEN | Pallavi Nair | Completed | Major patches and service pack upgrades will be taken care as part of preventive maintenance | 4 HCs & 4 Inc (1 Yr) | 4 | 4 | 0 | 4 | 4 | 2 | 2 |  | 2023-08-03 | 2024-08-02 | Q1 Support | Aug to Oct 23 | 2023-08-01 | Complete | 2023-08-07 | 2898
|  | RN-245 | Ongoing |  |  | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  | Haytham | GREEN | Pallavi Nair | Completed | Major patches and service pack upgrades will be taken care as part of preventive maintenance |  | 4 |  |  |  |  | 2 |  |  | 2023-08-03 | 2024-08-02 | Q2 Support | Nov to Jan 24 | 2023-11-01 | Complete |  | 2898
|  | RN-245 | Ongoing |  |  | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  | Haytham | GREEN | Pallavi Nair | On Track | Major patches and service pack upgrades will be taken care as part of preventive maintenance |  | 4 |  |  |  |  | 2 |  |  | 2023-08-03 | 2024-08-02 | Q3 Support | Feb to Apr 24 | 2024-02-01 | Complete | 2024-02-14 | 2898
|  | RN-245 | Ongoing |  |  | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  | Haytham | GREEN | Pallavi Nair | On Track | Major patches and service pack upgrades will be taken care as part of preventive maintenance |  | 4 |  |  |  |  | 2 |  |  | 2023-08-03 | 2024-08-02 | Q4 Support | May to July 24 | 2024-05-01 |  |  | 2898 |  |  |  | quarterly invoicing.. One quarter invoice to be done and will do it post sign-off from the client
| 39 | RN-373 | Ongoing | Expirrin on 11 Aug 24 | N&S | Thales | DPP | 1 Yr Contract | Vendor |  | DPP | Imran |  | Ishan | GREEN | Vignesh | On Track | 4 HCs and 3 Incidents |  | 4 | 3 |  | 1 | 3 | 3 | 3 | 3 | 2023-08-12 | 2024-08-11 |  |  |  | Complete |  | 226320 | Paid
| 41 | RN-325 | Ongoing | 3 Yr Contract | N&S | Checkpoint | Support-Al Dhaffra-Checkpoint (Al Dhafra Firewall Upgrade _14 NOS) |  | RNS |  | Al Dhafra Insurance Co PSC |  |  | Ranjith | GREEN | Pallavi Nair | On Track | 1 Preventive + 6 Incidents / year |  | 1 |  |  |  |  | 6 |  |  | 2023-08-31 | 2024-08-30 | Y1 23 |  | 2023-12-01 | Complete |  | 7350 |  |  |  | Check wit Rekha, wheter it is invoiced for 3 yrs or not
| 13 | RN-325 | Yet to Start | 3 Yr Contract |  | Checkpoint | Support-Al Dhaffra-Checkpoint (Al Dhafra Firewall Upgrade _14 NOS) |  | RNS |  | Al Dhafra Insurance Co PSC |  |  | Ranjith | GREEN | Pallavi Nair | On Track | 1 Preventive + 6 Incidents / year |  | 1 |  |  |  |  | 6 |  |  | 2024-08-31 | 2025-08-30 | Y2 23 |  | 2025-02-01 |  |  | 7350 |  |  |  | Need to chk with fin-ops team
|  | RN-325 | Yet to Start | 3 Yr Contract |  | Checkpoint | Support-Al Dhaffra-Checkpoint (Al Dhafra Firewall Upgrade _14 NOS) |  | RNS |  | Al Dhafra Insurance Co PSC |  |  | Ranjith | GREEN | Pallavi Nair | On Track | 1 Preventive + 6 Incidents / year |  | 1 |  |  |  |  | 6 |  |  | 2025-08-31 | 2026-08-30 | Y3 23 |  | 2026-02-01 |  |  | 7531.65 |  |  |  | Need to chk with fin-ops team
| 42 | RN-343 | Ongoing | Will end on 11 Sep 24 | EDR | McAfee | ADJD_ MacAfee renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  |  | Check withh Rekha on the invoicing plan
|  | RN-343 | Ongoing | Will end on 11 Sep 24 |  | McAfee | ADJD_ MacAfee renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-343 | Ongoing | Will end on 11 Sep 24 |  | McAfee | ADJD_ MacAfee renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
|  | RN-343 | Ongoing | Will end on 11 Sep 24 |  | McAfee | ADJD_ MacAfee renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q4 : 12 Jun 24 | Q4 : 11 Sep 24 |  |  | 2024-09-01 |  |  | 2625 each Qtr
| 43 | RN-344 | Ongoing | Will end on 11 Sep 24 | PAM | CyberArc | ADJD_ CyberArk renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  |  | Check withh Rekha on the invoicing plan
|  | RN-344 | Ongoing | Will end on 11 Sep 24 |  | CyberArc | ADJD_ CyberArk renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-344 | Ongoing | Will end on 11 Sep 24 |  | CyberArc | ADJD_ CyberArk renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
|  | RN-344 | Ongoing | Will end on 11 Sep 24 |  | CyberArc | ADJD_ CyberArk renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q4 : 12 Jun 24 | Q4 : 11 Sep 24 |  |  | 2024-09-01 |  |  | 2625 each Qtr
| 44 | RN-345 | Ongoing | Will end on 11 Sep 24 | Data Sec | ForcePoint, FP | ADJD_ ForcePoint renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  |  | Check withh Rekha on the invoicing plan
|  | RN-345 | Ongoing | Will end on 11 Sep 24 |  | ForcePoint, FP | ADJD_ ForcePoint renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-345 | Ongoing | Will end on 11 Sep 24 |  | ForcePoint, FP | ADJD_ ForcePoint renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
|  | RN-345 | Ongoing | Will end on 11 Sep 24 |  | ForcePoint, FP | ADJD_ ForcePoint renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q4 : 12 Jun 24 | Q4 : 11 Sep 24 |  |  | 2024-09-01 |  |  | 2625 each Qtr
| 45 | RN-347 | Ongoing | Will end on 11 Sep 24 | N&S | LogRhythm | ADJD_ LogRhythm renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  |  | Check withh Rekha on the invoicing plan
|  | RN-347 | Ongoing | Will end on 11 Sep 24 |  | LogRhythm | ADJD_ LogRhythm renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-347 | Ongoing | Will end on 11 Sep 24 |  | LogRhythm | ADJD_ LogRhythm renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
|  | RN-347 | Ongoing | Will end on 11 Sep 24 |  | LogRhythm | ADJD_ LogRhythm renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q4 : 12 Jun 24 | Q4 : 11 Sep 24 |  |  | 2024-09-01 |  |  | 2625 each Qtr
| 46 | RN-346 | Ongoing | Will end on 11 Sep 24 | N&S | FireEye | ADJD_ FireEye renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  |  | Check withh Rekha on the invoicing plan
|  | RN-346 | Ongoing | Will end on 11 Sep 24 |  | FireEye | ADJD_ FireEye renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-346 | Ongoing | Will end on 11 Sep 24 |  | FireEye | ADJD_ FireEye renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
|  | RN-346 | Ongoing | Will end on 11 Sep 24 |  | FireEye | ADJD_ FireEye renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q4 : 12 Jun 24 | Q4 : 11 Sep 24 |  |  | 2024-09-01 |  |  | 2625 each Qtr
| 47 | RN-348 | Ongoing | Will end on 11 Sep 24 | EDR | Tenable | ADJD_ Tenable renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  |  | Check withh Rekha on the invoicing plan
|  | RN-348 | Ongoing | Will end on 11 Sep 24 |  | Tenable | ADJD_ Tenable renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-348 | Ongoing | Will end on 11 Sep 24 |  | Tenable | ADJD_ Tenable renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
|  | RN-348 | Ongoing | Will end on 11 Sep 24 |  | Tenable | ADJD_ Tenable renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q4 : 12 Jun 24 | Q4 : 11 Sep 24 |  |  | 2024-09-01 |  |  | 2625 each Qtr
| 48 | RN-352 | Ongoing |  | N&S | Fortinet | NGI Fortinet_Fortinet AMC |  | RNS | 2023-10-03 | NGI | Sathar | sathar@ngiuae.com | Rohit | GREEN | Vignesh | On Track | 4 HCs and 10 Incidents |  | 4 | 3 |  | 1 | 3 | 10 | 2 | 8 | 2023-10-03 | 2024-10-02 |  |  | 2023-09-01 | Complete | 2023-09-28 | 7728
| 49 | RN-392 | Ongoing | Renewed from 31 Dec 23 | Identity | Sailpoint | DIB Sailpoint - AMC |  | RNS |  | DIB | Shinu |  | Ishan | GREEN | Sean Faizal | in Progress | 5 Incidents AND 1 HC |  | 1 |  |  |  |  | 5 |  |  | 2023-12-31 | 2024-12-30 |  |  | 2024-01-01 | COMPLETE |  | 295050 |  |  |  | if 5 tickets are consumed, addl 4 tickets can be supported at the cost of 29440 AED
| 50 | RN-364 | Yet to Start | Once 1 HC and 3 INCs are complete, this milestone can be invoiced | EDR | McAfee | Cadvil Solutions_EDR & EPP_2023 | 50% to be paid in Advance & 50% to be paid on Signoff | RNS | 2023-10-03 |  |  |  | Ranjith |  | Vignesh | Not Started | 45 Licenses, 1 HCs and 3 Incidents | [13 empty] | 2023-10-01 | Complete | 2023-10-10 | 2265 |  |  |  | PS is being implemented by another vendor. Following up with customer, if the PS is complete, so that, we can start the AMC. INFORM REKHA, ONCE YOU START AMC, SO THAT SHE CAN INVOICE
|  | RN-364 | Yet to Start | Once 1 HC and 3 INCs are complete, this milestone can be invoiced |  | McAfee | Cadvil Solutions_EDR & EPP_2023 | 50% to be paid in Advance & 50% to be paid on Signoff | RNS | 2023-10-03 |  |  |  | Ranjith |  | Vignesh | Not Started | 45 Licenses, 1 HCs and 3 Incidents | [13 empty] | 2024-04-01 |  |  | 2265 |  |  |  | PS is being implemented by another vendor. Following up with customer, if the PS is complete, so that, we can start the AMC. INFORM REKHA, ONCE YOU START AMC, SO THAT SHE CAN INVOICE
| 51 | RN-315 | Ongoing | Started from 28 Dec 23 | N&S | Checkpoint | Global Shipping & Logistics DIP |  | RNS | 2023-10-17 | Global Shipping & Lgs |  |  | Ishan | GREEN | Pallavi Nair |  | 1HC and 3 Incidents |  | 1 |  |  |  |  | 3 |  |  | 2023-12-28 | 2024-12-27 |  |  | 2023-11-01 | Complete |  | 38108.5 | Paid |  |  | 100% to be invoiced upon delivery of licenses
| 52 | RN-374 | Ongoing | 3 Yr Contract till Oct 26 | N&S | Opswat | MOFA - Opswat |  | Vendor |  | MOFA |  |  |  | GREEN | Pallavi Nair | On Track | 4 HC and 2 Incidents |  | 4 |  |  |  |  | 2 |  |  | 2023-10-19 | 2026-10-18 | Y1 |  | 2025-03-01 |  |  | 12266.64 |  |  |  | AMC started after PS is complete, Bundle cost. No separate cost for AMC
| 14 | RN-404 | Ongoing | Started from 04 JAN 24 | EDR | Solarwinds | Beema Insurance - Solarwinds NCM |  | RNS |  | Wasif Khan |  |  |  | GREEN | Pallavi Nair | On Track | 4 HCs and unlimited incident support |  | 4 |  |  |  |  | Unlimited |  |  | 2024-01-04 | 2025-01-03 |  |  | 2023-11-01 | Complete | 2023-11-09 | 5798
| 54 | RN-283 | Ongoing | Check with Rekha on invoice amount and status | EDR | Manage Engine | RAK Customs Manage Engine |  | Vendor | 2023-10-01 |  |  |  | Ishan Arora | GREEN | Pallavi Nair | On Track | 8 visits/calls/sessions support for SDP,ADMP,AP | [6 empty] | 8 |  |  | 2023-10-10 | 2024-10-09 |  |  | 2023-12-01 | Complete |  |  | paid |  |  | AMC cost is a value add. So no cost
| 55 | RN-145 | Ongoing | 1 year | N&S | Checkpoint | Arcadia School - Checkpoint : 5100 appliances |  | RNS |  | Arcadia School | Uma Sankar | uma.sanker@alshirawi.ae | Ishan Arora | GREEN | Pallavi Nair | On Track | Premium support, 1 HC and 3 Incidents |  | 1 |  |  |  |  | 3 |  |  | 2023-12-13 | 2024-12-12 |  |  | 2023-11-01 | Complete |  | 37748 |  |  |  | 100% to be invoiced upon delivery of licenses
| 56 | RN-367 | Ongoing | Check with Rekha on invoice amount and status | Identity | Sailpoint | Aldar Properties PJSC_SP_RW_AMC_Sep_2023 |  | RNS | 2023-10-03 | Aldar Propertices | Sunil Sharma |  | Bibinu | GREEN | Vignesh | On Track | 24 Incident support | [6 empty] | 24 | 1 | 23 | 2023-12-04 | 2024-12-03 |  |  | 2023-12-01 | COMPLETE |  | 152869
| 57 | RN-385 | Ongoing | AMC started from 23 Dec 23 | PAM | Delinea | Intigral_Delinea AMC |  | Vendor | 2023-12-13 | Intigral Middle East | Binu | Binu.Mathew@intigral.net | Ishan Arora |  | Sean Faizal | On Track | 4 HC and 4 Incidents |  | 4 | 2 | 1 | 2 | 1 | 4 | 0 | 3 | 2023-12-23 | 2024-12-24 |  |  | 2023-11-01 | COMPLETE | 2023-11-30 | 28310 | Paid |  |  | 100% to be invoiced upon delivery of licenses
| 58 | RN-418 | Ongoing |  | N&S | Fortigate | Gargash_Fortigate FW AMC | 100% invoiced uploand HW delivery | RNS | 2023-12-22 |  |  |  | Ranjith |  | Pallavi Nair | On Track | 1 Incident | [9 empty] | 2024-11-22 | 2024-11-21 |  |  | 2023-12-01 | COMPLETE | 2023-12-27 | 2000 |  |  |  | 100% to be invoiced upon hardware delivery, Invoicing has been completed
| 59 | RN-393 | Yet to Start | 1 YR, Not Started | PAM | CyberArc | OQ Trading - CyberArc | 100% on PS Sign off | RNS | 2023-12-05 | OQ Trading |  |  | Rohit Save |  | Pallavi Nair | Not Started | 2 HCs and 6 Incidents |  | 2 |  |  |  |  | 6 | [6 empty] | TBD |  |  | 13248 |  |  |  | 100% to be invoiced upon hardware delivery. Check with Rekha, whether invoiced or not.
| 15 | RN-391 | Ongoing | 10-May-24 - 9-May-2027 | N&S | Fortigate | Tawajun Economic Counsil - Fortigate Support | Invoice every 4 months - 31 May 24 |  | 2023-12-25 | Tawajun Economic Counsil | Aslam Rashid Khan |  | Ishan Arora |  | Sean Faizal | On Track | 6 Incidents and 4 HCs |  | 4 | 1 | 1 | 3 | 1 | 6 |  |  | 2024-02-01 | 2025-05-31 |  |  | 2024-06-01 |  |  | 11040 |  |  |  | To be Invoiced Quarterly in Advance
|  | RN-391 | Ongoing | 10-May-24 - 9-May-2027 |  | Fortigate | Tawajun Economic Counsil - Fortigate Support | Invoice every 4 months - 30 Sep 24 |  | 2023-12-25 | Tawajun Economic Counsil | Aslam Rashid Khan |  | Ishan Arora |  | Sean Faizal |  | 6 Incidents and 4 HCs |  | 4 |  |  |  |  | 6 |  |  | 2024-02-01 | 2024-09-30 |  |  | 2024-10-01 |  |  | 11040 |  |  |  | To be Invoiced Quarterly in Advance
|  | RN-391 | Ongoing | 10-May-24 - 9-May-2027 |  | Fortigate | Tawajun Economic Counsil - Fortigate Support | Invoice every 4 months - 31 Jan 25 |  | 2023-12-25 | Tawajun Economic Counsil | Aslam Rashid Khan |  | Ishan Arora |  | Sean Faizal |  | 6 Incidents and 4 HCs |  | 4 |  |  |  |  | 6 |  |  | 2024-02-01 | 2025-01-31 |  |  | 2025-02-01 |  |  | 11040 |  |  |  | To be Invoiced Quarterly in Advance
| 61 | RN-399 | Ongoing | AMC started on 27 Dec 23 | EDR | Cybereason | Waha Health - CyberReason - AMC |  | RNS | [6 empty] | Pallavi Nair | On Track | 4 Incidents and 2 HCs |  | 2 |  |  |  |  | 4 |  |  | 2023-12-27 | 2024-12-26 |  |  | 2024-01-01 | Complete |  | 6624
| 62 | NEW | Yet to Start | AMC will start once PS is complete | MS AUUTOMATION | MS Automation | Microsoft Automation _ November 2023_MAAN | Yearly invoice - 60K | RNS | 2023-11-22 | Authority of Social Contribution - MAAN | Yaqoob Yousef Al Awadhi |  | Haytham |  | Sean Faizal | Not Started | [10 empty] | 1 Year |  |  |  | 2024-10-01 |  |  | 63000 |  |  |  | 15750 AED per Qtr for 1 Year. Qtrly advance can be invoiced. First Qtr advance can be invoiced from Oct 24
| 16 | RN-412 | Ongoing | AMC started from 28 Feb 24 | EDR | Tenable | DLD_ Tenable_VM_Sept_2023 |  | RNS | 2023-11-22 | Dubai Land Dept | Abdulla Yalooq |  | Ishan |  | Pallavi Nair | On Track | 4 HCs and 8 Incidents |  | 4 |  |  |  |  | 8 |  |  | 2024-02-28 | 2025-02-27 |  |  | 2023-12-01 | Complete |  | 22080
| 64 | RN-266 | Yet to Start | Will start after PS is complete | Identity | Sailpoint | DMT Sailpoint |  | RNS | From Go Live for 1 year | DMT |  |  | Ishan |  | Pallavi Nair | Not Started | 7 Incidents and 1 HC : Post Go Live AMC charges will be billed as part of the project milestones | [13 empty] | 2024-03-01 | Complete | 2024-03-28 | 55200
| 17 | RN-403 | Ongoing | Started from 24 Jan 24 | Email Sec | Proofpoint | RTS - Proofpoint |  | Vendor | 2024-01-01 | [5 empty] | Pallavi Nair | On Track | Remote support - 1yr Qtrly payment - 24 Incidents | [6 empty] | 22 |  |  | 2024-01-24 | 2025-01-23 |  |  | 2024-01-01 | COMPLETE |  | 310556
|  | RN-403 | Ongoing | Started from 24 Jan 24 |  | Proofpoint | RTS - Proofpoint |  | Vendor | 2024-01-01 | [5 empty] | Pallavi Nair | On Track | Remote support - 1yr Qtrly payment - 24 Incidents | [6 empty] | 22 |  |  | 2024-01-24 | 2025-01-23 |  |  | 2024-04-01 | COMPLETE | 2024-04-24 | 4665.5
|  | RN-403 | Ongoing | Started from 24 Jan 24 |  | Proofpoint | RTS - Proofpoint |  | Vendor | 2024-01-01 | [5 empty] | Pallavi Nair | On Track | Remote support - 1yr Qtrly payment - 24 Incidents | [6 empty] | 22 |  |  | 2024-01-24 | 2025-01-23 |  |  | 2024-07-01 |  |  | 4665.5
|  | RN-403 | Ongoing | Started from 24 Jan 24 |  | Proofpoint | RTS - Proofpoint |  | Vendor | 2024-01-01 | [5 empty] | Pallavi Nair | On Track | Remote support - 1yr Qtrly payment - 24 Incidents | [6 empty] | 22 |  |  | 2024-01-24 | 2025-01-23 |  |  | 2024-10-01 |  |  | 4665.5
| 66 | NEW | Yet to Start | Will start after PS is complete | PAM | CyberArc | ADEK - CyberArc | RNS | RNS | ADEK | ADEK |  | End of Y1 Q1 | Haytham |  | Pallavi Nair | Not Started | 3 Yrs Support, Qtrly invoicing, unlimited support | [11 empty] | Y1 Q1 |  | 2024-08-01 |  |  | 4883.33 |  |  |  | Can be invoiced at the end of each Qtr for 3 Yrs. Total value for 3 yrs is 58,000 AED
|  | NEW |  |  |  | CyberArc | ADEK - CyberArc | [5 empty] | End of Y1 Q2 |  |  |  | Not Started | [12 empty] | Y1 Q2 |  | 2024-11-01 |  |  | 4883.33
|  | NEW |  |  |  | CyberArc | ADEK - CyberArc | [5 empty] | End of Y1 Q3 | [16 empty] | Y1 Q3 |  | 2025-02-01 |  |  | 4883.33
|  | NEW |  |  |  | CyberArc | ADEK - CyberArc | [5 empty] | End of Y1 Q4 | [16 empty] | Y1 Q4 |  | 2025-05-01 |  |  | 4883.33
|  | NEW |  |  |  | CyberArc | ADEK - CyberArc | [5 empty] | Y2 -4 Qtrs | [16 empty] | Y2 - 4 Qtrs |  | AUG 25, NOV 25, FEB 26 and MAY 26 |  |  | 19533.32 |  |  |  | Split this into 4 Qtrs
|  | NEW |  |  |  | CyberArc | ADEK - CyberArc | [5 empty] | Y3 - 4 Qtrs | [16 empty] | Y3 - 4 Qtrs |  | AUG 26, NOV 26, FEB 27 and MAY 27 |  |  | 19533.32 |  |  |  | Split this into 4 Qtrs
| 67 | New | Yet to Start | Will start after PS is complete | Identity | Sailpoint | INTIGRAL | 1 Year Contract | RNS |  | Intigral |  |  | Ishan |  | Vignesh | Not Started | 3 INCIDENTS | [6 empty] | 3 | [6 empty] | 2024-01-01 | COMPLETE |  | 18400
| 68 | RN-372 | Ongoing | LM Exchnage Mimecast | Email Sec | Mimecast | LM Exchnage Mimecast | 1Yr Contract | RNS |  | LM Exchange |  |  | Ranjit |  | Vignesh | On Track | 5 Incidents | [6 empty] | 5 | 5 |  | 2023-10-24 | 2024-10-23 |  |  | 2023-10-01 | COMPLETE | 2023-10-23 | 5945
| 18 | RN-407 | Ongoing | Started from 1st Jan 24 | EDR | Tripwire | FAB Tripwire | 3 Yr Contract | RNS |  | FAB |  |  | Ishan |  | Sean Faizal | On Track | 12 Incidents and 4 HCs - 3 Yrs |  | 4 | 1 | 1 | 3 | 1 | 12 | 1 | 5 | 2024-01-01 | 2026-12-31 |  |  | 2023-12-01 | COMPLETE |  | 2699953 |  |  |  | License and AMC ost
|  | RN-407 | Ongoing | Started from 1st Jan 24 |  | Tripwire | FAB Tripwire | 3 Yr Contract | RNS |  | FAB |  |  | Ishan |  | Sean Faizal | On Track | 12 Incidents and 4 HCs - 3 Yrs |  | 4 |  |  |  |  | 12 |  |  | 2024-01-01 | 2026-12-31 |  |  | 2024-12-01 |  |  | 2699953 |  |  |  | License and AMC ost
| 19 | RN-407 | Ongoing | Started from 1st Jan 24 |  | Tripwire | FAB Tripwire | 3 Yr Contract | RNS |  | FAB |  |  | Ishan |  | Sean Faizal | On Track | 12 Incidents and 4 HCs - 3 Yrs |  | 4 |  |  |  |  | 12 |  |  | 2024-01-01 | 2026-12-31 |  |  | 2025-12-01 |  |  | 2699953 |  |  |  | License and AMC ost
| 70 | RN-224 | Yet to Start |  | Identity | Sailpoint | ADCB Saillpoint |  | RNS |  | ADCB |  |  | Ishan |  | Pallavi Nair | On Track | 8 Incidents | [6 empty] | 8 |  |  | 2023-08-04 | 2024-12-31 | [9 empty] | New contract will be initiated. For now, there is no formal AMC
| 71 | RN-280 | Ongoing | 19 Months | EDR | Tenable | DMT Tenable |  | RNS |  | DMT |  |  | Bibinu |  | Pallavi Nair | On Track | 8 Incidents, 1 HC |  | 1 |  |  |  |  | 8 |  |  | 2023-12-22 | 2025-05-01 |  |  | 2024-05-01 |  |  | 30912
| 20 | RN-413 | Ongoing | 1 year | N&S | Palo Alto | Intigral_PaloAlto_Renewal_PS/AMC_Jan_2024 | 1 Yr contract | RNS | 2024-01-16 | Intigral |  |  | Ishan |  | Pallavi Nair | On Track | 2 HCs and 8 Incidents |  | 2 |  |  |  |  | 8 |  |  | 2024-01-24 | 2025-01-23 | [5 empty] | 18400 |  |  |  | 100% to be invoiced upon delivery of licenses. Rekha to check withh customer, whether invoicing can be done or not.
| 73 | New | Yet to Start | Will start after PS is complete | Data Sec | ForcePoint, FP | Emirates Steel _Protivity _DataSecurity _ESA_DC&DLP_Nov_2023 | 1 Yr contract | RNS | 2023-12-23 | Emirates Steel / Protivity |  |  | Bibinu |  | Divya | Not Started | [14 empty] | TBD |  |  | 15456 |  |  |  | Should have been invoiced along with PS (50% of Services upon completion of Data Classification tool as per scope of work
|  | New | Yet to Start | Will start after PS is complete |  | ForcePoint, FP | Emirates Steel _Protivity _DataSecurity _ESA_DC&DLP_Nov_2023 | 1 Yr contract | RNS | 2023-12-23 | Emirates Steel / Protivity |  |  | Bibinu |  | Divya | Not Started | [14 empty] | TBD |  |  | 15456 |  |  |  | Should have been invoiced along with PS (50% of Services upon completion of DLP Suite as per scope of work
| 21 | RN-183 | Ongoing | Start from 10 March 24 | EDR | Solarwinds | Power International Holding_Qatar_Solarwinds | 15 Months contract | RNS | 2024-02-29 | PIH - Power Intl Holding |  |  | Sumantra Basu |  | Pallavi Nair | On Track | Unlimited 8x5 support with 2 hrs response time | [9 empty] | 2024-03-10 | 2025-05-29 |  |  | 2024-03-01 | COMPLETE |  | 123210 |  |  |  | Value in QAR. 100% to be invoiced upon delivery / renewal of licenses and AMC 100% advance
| 75 | RN-419 | Completed | Aldar Sailpoint 100 Hhrs | Identity | Sailpoint | Aldar | 200 hrs (monring checks) | RNS |  | Aldar Propertices |  |  | Bibinu |  | Pallavi Nair | On Track | 0 Hrs | 50% on commencement of the service | [8 empty] | 2023-10-03 | 2024-10-02 |  |  | 2023-12-01 | COMPLETE | 2023-12-14 | 19950 |  |  |  | 50% in advance
|  | RN-419 | Ongoing | Aldar Sailpoint 100 Hhrs |  | Sailpoint | Aldar | 200 hrs (monring checks) | RNS |  | Aldar Propertices |  |  | Bibinu |  | Pallavi Nair | On Track | 100 hrs | 50% on upon consumption of 100 hours | [8 empty] | 2023-10-03 | 2024-10-02 |  |  | 2024-05-05 |  |  | 19950 |  |  |  | 50% upon completion of 100 Hrs. Informed op team of consumption of 100 hrs on 22 May 24
| 22 | RN-143 | Ongoing | Started from 27 Mar 24 | VMWare | Carbon Black | Tawajun Economic Counsil - Carbon Black | 1 Yr Contract | RNS |  | Tawajun Economic Counsil |  |  | Ishan |  | Sean Faizal | On Track | 4 HCs and 6 Incidents | 100% to be invoiced upon delivery of licenses | 4 | 1 | 1 | 3 | 1 | 6 | 0 | 2 | 2024-03-27 | 2025-03-26 |  |  | 2024-03-01 | Complete | 2024-03-29 | 39470 |  |  |  | FULLY INVOICED
| 23 | RN-164 | Ongoing | Renewed from 22 Mar 24 | Data Sec | ForcePoint, FP | UBL - Forcepoint Web Security | 1 Yr Contract | RNS |  | UBL - UAE, Bahrain & Qatar | Talha Ahmed Seddiqi | talha.siddiqui@ubl.com.pk | Ishan Arora | GREEN | Pallavi Nair | On Track | [10 empty] | 2024-03-22 | 2025-03-21 |  |  | TBD |  |  | 58037 |  |  |  | 100% to be invoiced upon delivery of licenses & AMC to be invoiced upon sign-off. ORDER IS NOT PROCESSED. CHECK WITH REKHA BEFORE START OF THE AMC
| 24 | RN-169 | Ongoing | Renewed from 02 Apr 24 | EDR | Solarwinds | MBRHE Solarwinds | 1 Year Contract | RNS |  | MBRHE | Mohammad Amjad | mamjad@mbrhe.ae | Ishan Arora | GREEN | Pallavi Nair | On Track | 4 HCs and 6 Incidnets |  | 4 |  |  |  |  | 6 |  |  | 2024-04-02 | 2025-04-01 |  |  | 2024-05-01 |  |  | 106534 |  |  |  | 100% to be invoiced upon delivery of licenses
| 25 | RN-439 | Ongoing | 1 YR, Not Started | Identity | Sailpoint | SIB new 100 hr support - 2024 -25 | RNS |  |  | SIB | Mubashir Hafiz | mubashir.hafeez@sib.ae | Faizan | GREEN | Vignesh | On Track | 100hrs Support | [9 empty] | 2024-06-21 | 2025-06-20
| 25 | RN-149 | Ongoing | 3 years | N&S | Fortigate | Mofaic Fortigate | 3 Yr Contract | [7 empty] | Pallavi Nair | [11 empty] | 2021-12-13 | 2024-12-12
Proposals to be checked
|  | NEW |  | PO not received |  | Trendmicro | CBD_Trendmicro_AMC Renewal_Q3_2023 |  | RNS | 2023-10-03 |  |  | Shihab Packer | Faizan |  | Pallavi Nair
|  | NEW |  |  |  |  | Zakher Marine International_Email Security |  | RNS
|  | RN-437 | Ongoing |  |  |  | Tawazun Council Tenable | ! Year | RNS |  | Tawajun Economic Counsil | Hamad AlZaabi |  | Ishan Arora |  | Sean Faizal | On Track |  |  | 4 | 0 | 1 | 4 | 0 | 8 | 0 | 1
|  | RN-438 | Ongoing |  |  |  | TIP Ivanti | 1 Year | RNS |  | TIP | Sumeet Singal |  | Ishan Arora |  | Sean Faizal | On Track |  |  | 4 | 0 | 1 | 4 | 0 | 12 | 0 | 1
|  | New | Yet to Start | Will start after PS is complete |  |  | AD Louvre - Nazomi | 3 yrs | RNS |  | AD Louvre |  |  |  |  | Sean Faizal | Not Started | 8 inc 2 HC
|  | New |  |  |  |  | TEC Forcepoint | 1 Year Contract |  |  | TEC | [5 empty] | On Track
|  | New | Yet to Start | Will start after PS is complete |  |  | Addof - tenable.sc | 1 Year | RNS |  | Addof |  |  |  |  | Sean Faizal | Not Started | 8 inc 2 HC
|  | RN-262 |  |  |  |  | DAS Project (IT Support)
|  | RN-306 |  |  |  |  | Support-Value Add Services (Non Billable)
|  | RN-321 |  |  |  |  | Support effort spent on KT, Pre Sales, Certifications, Trainings, Shadowing etc.,.
|  | RN-336 |  |  |  |  | Leave Tracker
|  | RN-354 |  |  |  |  | Government Holidays
|  | RN-355 |  |  |  |  | ForgeRock Practice Development
Note on C16: CS Rao:Project team can track HC and incidnets. Invoicing will be planned by KD
Note on C17: CS Rao:Project team can track HC and incidnets. Invoicing will be planned by KD

## PS Project Register
PROJECT MANAGEMENT LOG TEMPLATE
PROJECT REGISTER
The PROJECT Identification portion of this table will automatically populate to the Financial Data, Deliverables and Performance, and Risk Register tabs within this workbook.
PROJECT DATA | [6 empty] | CUSTOMER DATA |  |  | ACCOUNT DATA |  | PROJECT MANAGEMENT | [5 empty] | TERMS
NO. | PROJECT ID | Project Type | Tower | Led By | PROJECT NAME | Project Scope | CUSTOMER NAME | CUSTOMER SPOC NAME | CUSTOMER SPOC EMAIL | ACCOUNT MANAGER NAME | ACCOUNT HEALTH | INTERNAL PROJECT MANAGER | PROJECT COMPLEXITY | Status | Total Milestones | Milestones Open | Milestones Closed | START DATE | END DATE | Revised End Date | Actual End Date | % Completion | REMARKS |  | Rekha comments
1 | RN-82 | VAPT | IntelliStrike | RNS | CUBE - VAPT - 2022 |  | Cube Payments | Benjamin Chao | benchua@cubepayment.com | KD | RED | Vignesh | Low | On Hold | 5 | 4 | 1 | 2022-03-03 | 2023-05-16 | TBD |  | 40% | Delayed due to unresponsive customer. 2nd Qtr assessment is yet to start. Legal action has been initiated by CFO - Check with Rekha
3 | RN-101 | ForcePoint, FP | NW & Sec | RNS | TIP - Forcepoint, BJ and DLP |  | Tawazun Industrial Park | Sumeet Singhal | susinghal@tip.ae | Ishan Arora | GREEN | Sean Faizal | Medium | Delayed | 9 | 8 | 1 | 2022-05-15 | 2023-08-25 | 2025-04-05 |  | 99% | Sign-off initiated | Due to unresponsive internal team from customer side
4 | RN-252 | VAPT | IntelliStrike | RNS | EPC-VAPT_2023 | platform and Web assessment - 5 iterations | EMIRATES POLICY CENTER | Jinson Pappachan | jinson@epc.ae | Ranjit George | GREEN | Sean Faizal | Low | On Hold | 2 | 0 | 2 | 2023-04-06 | 2024-02-07 | TBD |  | 65% | Conditional sign-off recieved | delay from Customer
7 | RN-298 | Forcepoint DLP & BJ | NW & Sec | RNS | Nextcare - FP DLP & Data classification | FP Web, DC & DLP and BJ | Nextcare | Zaher | Zaher.ElAli@nextcarehealth.com | Ishan Arora | GREEN | Sean Faizal | Low | Delayed | 9 | 4 | 5 | 2023-07-03 | 2024-01-10 | 2025-07-30 |  | 60% | Data classification: on hold as per nextcare's request to redo the excersice. DLP installation and configuration complete, dept-specific configuration is pending and is contingent on data classification | Delay from Customer's internal teams
8 | RN-301 | Akamai | NW & Sec | Vendor | Nextcare_Akamai_AAP & DSA | Edge DNS & AAP - 25 apps | Nextcare | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Haytham | AMBER | Sean Faizal | Medium | On Hold | 2 | 1 | 1 | 2023-07-10 | 2023-11-20 | TBD |  | 75% | Application requirement changed (Nextcare), Pulse V2 replaced by Pulse V3, Application testing underway along with updated configurations. | Application requirements changed, Pulse V2 replaced by Pulse V3, testing underway for the same.
11 | RN-320 | Managed Services | NW & Sec | RNS | Nextcare_Managed_APM_&_IT_Incidents |  | Nextcare | Tom Badger | tom.badger@nextcarehealth.com | Haytham | AMBER | Sean Faizal | Low | On Hold | 2 | 2 | 0 | 2024-01-31 | 2024-04-22 | 2025-04-30 |  | 95% | As per Toms recommendation, RNS team can proceed with the monitoring of the solution including manning the phones and directing to relevent teams. RNS will not have access to the ticketing system due to compliance issue (Alliance). Ameya to revert and confirm the strategy to to proceeed forward and plan the final KT session.
34 | RN-425 | Sailpoint | Sailpoint | RNS | NI UAE -Sailpoint FAM Upgrade |  | NI Dubai Network International | Rejish Kandath | Fuard.Saban@network.global | Sagar Chopra | GREEN | Laxmi | Low | Delayed | 6 | 2 | 4 | 2024-07-03 | 2024-07-30 | TBD |  | 57% | Downgraded the FAM services in UAT to the version 8.1 SP5 - We have started upgrading to the latest version with the PROD Data and start our impact analysis
2 | RN-122 | Sailpoint | Sailpoint | RNS | ADCB - SailPoint Phase 2 |  | ADCB | Jeny | JenyAnniePhilip.ext@adcb.com | Sagar Chopra | RED | Laxmi | Medium | On Hold | 16 | 16 | 0 | 2024-07-15 |  |  |  | 10%
49 | RN-305 | VAPT | IntelliStrike | RNS | ENI_Emirates National Investments - VAPT |  | ENI | Omer | jjohn@eni.ae | Ashida | GREEN | Vignesh | Low | Delayed | 3 | 1 | 2 | 2023-08-18 | TBD | TBD |  | 80% | Waiting for the retesting dates from customer. (POC change from ENI) | Delay from Customer
51 | RN-358 | VAPT | IntelliStrike | RNS | DNI_VAPT internal and External Remediation_2023 |  | Dubai National Insurance | Saju | saju.pv@dni.ae | Faizan | GREEN | Vignesh | Low | Delayed | 3 | 3 | 0 | 2023-10-17 | TBD | TBD |  | 83% | Waiting for customer to share creds to commence the external web app retesting. And Onsite date confirmation | Delay from Customer
22 | RN-361 | Sailpoint | Sailpoint | RNS | Mashreq Sailpoint Phase 2 |  | MASHREQ BANK | Nagesh | NageshD@mashreq.com | Sagar Chopra | GREEN | Laxmi | Medium | On Hold | 3 | 2 | 1 | 2023-10-15 | 2024-02-26 | TBD |  | 75% | Helix UAT complete. Discussions are in progress for CDP. All environments are upgraded and signed off-Invoiced.payment received for all
29 | RN-382 | CyberArk | Sailpoint | RNS | OQ Trading_PAM |  | OQ Trading | Abhilash Radhadevi | abhilash.radhadevi@oq.com | Unnikrishnan | GREEN | Pallavi Nair | Low | On Hold | 9 | 7 | 2 | 2023-01-15 | 2024-07-26 | TBD |  | 40% | Informed customer on three-week notice to redeploy our team members.
95 | New | BeyondTrust | BeyondTrust | Vendor + RNS | Nextcare - BeyondTrust |  | Nextcare | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Ishan Arora | GREEN | Pallavi Nair | Low | On Hold | 4 | 3 | 1 | 2024-08-19 | 2024-10-28 | TBD |  | 72% | 516/1000 assets onboarded, we are waiting for the remaining asset information from nextcare team, and update from nextcare team on the new suggestions (post training)
15 | RN-273 | Sailpoint | Sailpoint | RNS | QIB (Phase 3) Sailpoint |  | QIB | Soloman | Solomon.Sagayaraj@qib.com. | Deepinder Singh | GREEN | Pallavi Nair | Medium | Delayed | 5 | 3 | 2 | 2023-04-01 | 2023-07-30 | TBD |  | 28% | Started the testing process, but to fully validate it in the UAT environment, we require the below: 1. Access to UAT servers 2. Resolution of the AD credential issue
20 | RN-334 | Sailpoint | Sailpoint | RNS | Abu Dhabi Media Company |  | AD Media | Badar | Bader.Zyoud@admn.ae | Maha | GREEN | Laxmi | High | On Track | 5 | 1 | 4 | 2023-09-06 | 2024-08-19 | 2025-04-15 |  | 99% | Training part needs to be confirmed with Bader . After Project closure he is asking to start Nirajs support Nitesh to check with KD on revoking Niraj's support if client is not confirming
21 | RN-365 | Sailpoint | Sailpoint | RNS | NIJordan_SailPoint_Sept_2023 |  | Network International LLC | Fuard Saban | Fuard.Saban@network.global | Sagar Chopra | GREEN | Pallavi Nair | Medium | On Track | 3 | 2 | 1 | 2023-10-19 | 2024-07-30 | 2025-04-21 |  | 96% | UAT Signoff received on 8/4 8/4 - Go Live planned next week, date to be shared by Jordan Team
32 | RN-422 | Sailpoint | Sailpoint | RNS | KalaamAlQureshi_SailPointServices_Dec_2023 |  | Kalaam_AlQureshi | Ahmed Imtiaz | rana.mostafa@alquraishi.com | Ishan Arora | GREEN | Laxmi | Medium | On Track | 6 | 3 | 3 | 2024-04-29 | 2025-02-04 | 2025-06-05 |  | 75% | Go live completed on 24th March for 3 apps and JML
36 | RN-330 | ISO BCP & RA | IntelliAssure | RNS | ECAE- Audit |  | Emirates College of Adv Edn | Ahmed Mansour | Mohamed.alhosani@adnec.ae | Haytham | GREEN | Ajinkya | Low | On Track | 1 | 0 | 1 | 2023-10-10 |  | 2026-03-31 |  | 35% | 3 Years consultancy. 1st yr scope - BCP Audit & Testing is complete. Sign off received for 1st year. 2 nd Year Audit activities completed, some documents are being updated according to client's template
42 | RN-414 | Forcepoint DLP & BJ | NW & Sec | Vendor + RNS | Emirates Stell_Protivity_DataSecurity_ESA_DC&DLP_Nov_2023 |  | Emirates Steel / Protivity ME | Parthasardhi S | Parthasarathi@emiratessteel.com | Bibinu Ajith | GREEN | Divya | Medium | On Track | 3 | 2 | 1 | 2024-03-01 | 2024-07-19 | 30-12-2024 |  | 80% | Boldon James UAT is in progress
43 | RN-415 | ISO Consulting | IntelliAssure | RNS | Health at Hand_ISO Consultancy & Cert |  | Health at Hand / Next Care | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Haytham | GREEN | Vignesh | Low | On Track | 7 | 5 | 2 | 2024-02-29 | TBD |  |  | 69% | Following up on internal Audit | Delay from Customer
52 | RN-363 | VAPT | IntelliStrike | RNS | GPSSA_VAPT |  | General Pension and Social Security Authority (GPSSA) | Senthil Kumar | vishnu.padmakumar@gpssa.gov.ae | Komal | GREEN | Vignesh | Low | On Track | NA | NA | NA | 2024-10-30 | 2025-10-29 |  |  | 28% | Mobile application assessment completed. Upon on customer confirmation, we can do retesting | Delay from Customer
55 | RN-396 | VAPT | IntelliStrike | RNS | Al Ahli Bank_VAPT Dec 23_Qatar |  | Al Ahli Bank_Qatar | Dexter Ccasagnap | dexter.casagnap@ahlibank.com.qa | Sumantra Basu | GREEN | Vignesh | Low | On Track | 3 | 1 | 2 | 2023-12-14 | 2025-04-30 |  |  | 86% | Retesting in progress | Delay from Customer
73 | RN-443 | VAPT | IntelliStrike | RNS | Leos Development-VAPT | 1 test & 2 retest | LEOS | Daniel Steyn | daniel.steyn@leosuk.com | Ashida Khan | GREEN | Sean Faizal | Low | On Hold | 3 | 3 | 0 | 2024-06-26 | 2024-11-01 | TBD |  | 50% | Phase 1 complete, LEOS IT directore replaced, Phase 2 & 3 on hold
58 | RN-424 | VAPT | IntelliStrike | RNS | Al Nabooda VAPT |  | Al Nabooda | Ratheesh | ratheesh.ravindran@nabooda-auto.com | Manish Narayanan | GREEN | Vignesh | Medium | On Track | 4 | 1 | 3 | 2024-05-06 | 2025-04-30 |  |  | 77% | Second phase commenced
64 | RN-434 | ISO Consulting | IntelliAssure | RNS | Sharjah Asset Management |  | Sharjah Asset Management | Shaikha Al Marzooqi | shaikha.almarzooqi@sam.ae |  | GREEN | Ajinkya | Low | On Track | 8 | 3 | 5 | 2024-06-25 |  | TBD |  | 50% | Documentation review is in progress
74 | RN-442 | ISO Consulting | IntelliAssure | RNS | Ajman Chambers | ISO 27001 Implementation & Internal Audit | Ajman Chambers | Ahmed Fathi | afathi@ajmanchamber.ae | Komal | GREEN | Vignesh | Medium | On Track | 9 | 4 | 5 | 2024-06-19 | TBD | TBD |  | 59% | 6/2/25 - Documents shared with customer for review. Training completed. Implementation assistance in progress
79 | RN-446 | Sailpoint | Sailpoint | RNS | Mashreq Bank sailpoint- phase 3 |  | Mashreq Bank | Nagesh | NageshD@mashreq.com | Sagar Chopra | GREEN | Pallavi Nair | High | On Track | 5 | 1 | 4 | 2024-07-08 | 2025-02-05 | 2025-04-30 |  | 95% | Non Human design document signoff received on 8/4 Dormant CR to be raised by mashreq
85 | RN-185 | Sailpoint | Sailpoint | RNS | Intigral |  | Intigral ME | Karthik | basil.joy@intigral.net | Sagar Chopra | GREEN | Laxmi | Low | On Hold | 3 | 3 | 0 | 2024-02-17 | 2024-12-31 |  |  | 22% | 3 apps finalized , 2 apps UAT completed and signed off
80 | RN-445 | Sailpoint | Sailpoint | RNS | Tawazun Sailpoint |  | Tawazun Council | Vishal | vchirackal@tawazun.gov.ae | Sagar Chopra | GREEN | Bhushan | Medium | Delayed | 4 | 1 | 3 | 2024-07-15 | 2025-01-27 | 2025-04-15 |  | 98% | KD Sir Advised to Jp Sir to visit Tawazun
89 | RN-461 | VAPT | IntelliStrike | RNS | SOBHA REALTY - VAPT |  | SOBHA REALTY | Meenu | meenu.joseph@sobharealty.com | Ashida Khan | GREEN | Vignesh | Medium | On Track | 6 | 6 | 0 | 2024-07-29 | 2024-12-04 | 2025-05-08 |  | 25% | kickoff done on 29th July Phase 1 & 2 assessments in progress(Web App Assessments in progress)
93 | RN-473 | Akamai | Nw & Sec | Vendor | TDRA - Akamai | TDRA | TDRA | Saeed | saeed.mohammed@tdra.gov.ae | Komal | GREEN | Vignesh | Medium | On Track | 5 | 1 | 4 | 2024-07-17 | 2024-10-05 | 2025-03-31 |  | 70% | Testing is completed. Go live needs to scheduled. Customer to confirm Go Live date for App & API protector.
98 | RN-476 | SDLC Tool Deployment | NW & Sec | Vendor | Checkmarx - Invicti - MOFA |  | MOFA | Sofeya | sofeya.aljneibi@mofa.gov.ae | Bibinu | GREEN | Divya | Medium | On Track |  |  | 0 | 2024-08-29 | 30-12-2024 |  |  | 90% | KT sessions are remaining
91 | RN-468 | Zscaler | Network Security | Vendor | Mashreq Bank-Zscaler ZIA ZPA | 5000 Users rollout and configuaration | Mashreq Bank | Wajeed Mohamad | WajeedM@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | High | On Track | 6 | 4 | 2 | 2024-08-02 | 2025-06-30 |  |  | 72% | Pilot rollout complete. currently 2500+ users have been onboarded the platform. Zscaler testing VoIP connectors for awaya and client to server latency use cases
92 | RN-469 | Qualys | NW & Sec | RNS + Vendor | NEXTCARE QUALYS |  | Nextcare | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Ishan | GREEN | Sean Faizal | Low | On Track | 6 | 3 | 3 | 2024-08-14 | 2025-12-30 | 2025-03-10 |  | 80% | VMDR & WAS configuration is in progress; Agent deployment is completed; Fine-tuning activities in progress
19 | RN-338 | Sailpoint | Sailpoint | RNS | Doha Bank - Sailpoint |  | Doha Bank | Mohamed Shah | mshah@dohabank.com.qa | Deepinder Singh | AMBER | Laxmi | Medium | On Hold | 6 | 4 | 2 | 2024-02-22 | 2024-10-30 | TBD |  | 40% | JML Configuration in Progress
106 | RN - 479 | VAPT | IntelliStrike | RNS | Katim - VAPT |  | KATIM | Jithin Raj | jithin.raj@katim.com | Ishan Arora | GREEN | Vignesh | Medium | On Track | 3 | 0 | 3 | 2024-09-20 | TBD |  |  | 10% | Threat modelling report shared with customer. Waiting for customer confirmation to proceed with VAPT
107 | RN - 480 | ISO Consulting | IntelliAssure | RNS | Katim - ISO |  | KATIM | Jithin Raj | jithin.raj@katim.com | Ishan Arora | GREEN | Vignesh | Medium | On Track | 10 | 1 | 9 | 2024-09-20 | 2025-03-30 | 2025-04-30 |  | 80% | 9/10 - Gap analysis sttakeholders meeting completed 6/2/25 - UAE IA gap analysis, risk assessment and SSDLC activities are pending
108 | RN - 483 | VAPT | IntelliStrike | RNS | Ahli Bank - VAPT 2024 (Secure Code review) |  | Al Ahli Bank | Dexter | dexter.casagnap@ahlibank.com.qa | Sumantra Basu | GREEN | Vignesh | Medium | On track | 4 | 1 | 3 | 2024-09-20 | 2025-04-14 | 2025-05-07 |  | 57% | Source code review assessment completed. NO API assessment required. Remediation in progress
110 | RN-482 | Sailpoint | SailPoint | RNS | SIB - Upgrade |  | SIB | Sherin Akber | sherin.akber@sib.ae | Faizan | GREEN | Pallavi Nair | Medium | Delayed | 3 | 3 | 0 | 2024-10-03 | 2025-03-07 | TBD |  | 89% | Signoff shared for IIQ upgrade (uat) FAM - RNS Team is working on upgrading the local environment. IIQ Prod Upgrade- 1 issue is open
113 | RN - 486 | Checkmarx | NW & Sec | Vendor | ADDOF - Checkmarx |  | ADDOF | Ali Amer Alhajri | AAAlhajri@addof.gov.ae | Bibinu Ajith | GREEN | Vignesh | Medium | On Track | 3 | 1 | 2 | 2024-10-21 | 2024-12-12 | 2025-03-14 |  | 90% | Signoff received, DAST scan is pending
117 | RN - 501 | ISO Consulting | IntelliAssure | RNS | International Charity Organization - ICO |  | ICO | Munzer Dinno | munzer.dinno@ico.org.ae | Faizan | GREEN | Ajinkya | Medium | Not started | [7 empty] | 0% | Client needs some bank guarnatee before starting the project. Accounts team and client team working on it, before planning of the kickoff.
118 | RN - 502 | LogRhythm | NW & Sec | Vendor | Tawazun Coucil - LogRhythm |  | Tawazun Council | Mathew Rajesh Dsouza | mdsouza@tawazun.gov.ae | Ishan Arora | GREEN | Vignesh | High | On track | 5 | 0 | 5 | 2025-02-11 | 2025-04-10 | 2025-04-22 |  | 68% | Design & UAT document to be approved by TC. Implementation activites in progress
121 | RN-452 | Forcepoint | NW & Sec | RNS + Vendor | Kerzner International - Forcepoint One | DLP,CASB | Kerzner International | Vikalp Shrivastava | Vikalp.Shrivastava@kerzner.com | Komal | GREEN | Sean Faizal | Medium | On Track | 3 | 0 | 3 | 2025-02-12 | 2025-06-30 |  |  | 8% | CASB Implementation in progress, Pre-Reqs are shared for allocation. Cloud DLP yet to start
127 | RN-508 | Forcepoint | Network Security | RNS | UBL Forcepoint Hardware refresh |  | UBL | Talha | talha.siddiqui@ubl.com.pk | Ishan Arora | GREEN | Ajinkya | Medium | On Track | 3 | 3 | 0 | 2025-01-31 | TBD |  |  | 5% | Racking and mounting activity completed on 25th Feb for UAE region. Following up for additoinal power supply to UAE and appliance delivery to Bahrain
123 | RN-516 | Forcepoint | NW & Sec | RNS | FlyDubai - Forcepoint One |  | Fly Dubai | Aparna | Aparna.T.ext@flydubai.com | Ishan Arora | GREEN | Vignesh | High | On track | 11 | 0 | 11 | 2025-02-07 | 2025-05-11 |  |  | 14% | DLP Implementation in progress.DSPM yet to start
117 | RN-496 | Forcepoint, CyberArk, McAfee, LogRhythm | Network Security | RNS | ADJD - New deployment |  | ADJD | Belal | b.salmeen@adjd.gov.ae | Komal | GREEN | Vignesh | Medium | On Track | 4 | 1 | 4 | 2024-12-12 | 2025-01-20 | 2025-04-24 |  | 42% | LogRhythm and McAfee deployment is in progress. Waiting for customer confirmation to start Forcepoint
125 | RN-474 | Sailpoint | Sailpoint | RNS | Airtel Africa - Phase 3 |  | Airtel | Ashok |  | Sagar Chopra | GREEN | Laxmi | High | On Track | 10 | 8 | 2 | 2025-01-13 08:00 | 2028-03-02 17:00 | -- |  | 3% | Awaiting for Official Kick off from Airtel. IIQ - from application integration perpective we started . Usecase discussion will started post upgrade in Prod . Received the multsite servers for all except one
126 | RN-510 | Palo Alto | Network Security | RNS | Intigral - Palo Alto_Firewall |  | Intigral | Vinayak | vinayak.naik@intigral.net | Ishan Arora | GREEN | Vignesh | Medium | On Track | 3 | 2 | 1 | 2025-01-27 | 2025-02-14 | 2025-04-24 |  | 30% | Configuration of security policies is in progress. Migration planned for 20th April
128 | RN-522 | Picus | Network Security | Vendor | Ajman Bank - Picus |  | Ajman Bank | Fahad Sheikh | fahad.sheikh@ajmanbank.ae | Ishan Arora | GREEN | Ajinkya | Medium | On Track | 1 | 1 | 0 | 2025-01-20 | 2025-04-18 |  |  | 90% | Simulation agents have been setup. Training for attacks have been provided. Working on next session of training for SIEM
130 | RN-524 | Palo Alto | Network Security | RNS | Nextcare_Palo Alto_Tech refresh |  | Nextcare | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Ishan Arora | GREEN | Ajinkya | low | On Track | 1 | 1 | 0 | 2025-04-07 | 2025-04-25 |  |  |  | Kick off to be scheduled next week as Zaher is unavailable
129 | RN-254 | Sailpoint | IntelliDeploy | RNS | Digital 14 (Katim) - SailPoint |  | Digital 14 (Katim) | Maddi | Maddi.Prasad@katim.com | Ishan Arora | GREEN | Pallavi Nair | Low | On Track | 12 | 11 | 1 | 2025-01-01 | 2025-12-31 |  |  | NA
130 | RN-529 | Proofpoint | Network Security | RNS | Protect - Proofpoint Email |  | Protect | Prasad Prabhu | prasad.prabhu@protected.ae | Ishan Arora | GREEN | Ajinkya | Low | Not started
132 | RN-523 | VAPT | IntelliStrike | RNS | Al Buhaira VAPT |  | Al Buhaira | Mohammed Javed | m.javed@albuhaira.com | Ashida | GREEN | Ajinkya | Low | On Track | 2 | 2 | 0 | 2025-02-19 | TBD |  |  | 5% | External N/w and External Website assessments is in progress
133 | RN-265 | VAPT | IntelliStrike | RNS | Al Fardhan Exchange VAPT | Ext Net, Int net, Ext Web, Config Review | Al Fardhan Exchange | Firoz Khan | firoz.khan@alfardangroup.com | Manish Narayanan | GREEN | Sean Faizal | Low | On Track | 2 | 2 | 0 | 2025-02-27 | 2025-04-30 |  |  | 45% | Ext Net - Complete Ext Web - 3 complete. 2 inprogress Int Net - Complete Config - inprogress
134 | New | Sailpoint | SailPoint | RNS | Mashreq Upgrade |  | Mashreq Bank | Nagesh | NageshD@mashreq.com | Sagar Chopra | GREEN | Pallavi Nair | Medium | On Track | 3 | 3 | 0 | 2024-04-07 | 2025-05-22 |  |  | 1% | Waiting for Rushikesh C's access Sandbox upgrade has started
135 | New | Sailpoint | SailPoint | RNS | Mashreq Health Check |  | Mashreq Bank | Nagesh | NageshD@mashreq.com | Sagar Chopra | GREEN | Pallavi Nair | Medium | Not started | [8 empty] | Rajesh wants HC to be performed after upgrade
136 | RN-526 | ISO Consulting | IntelliAssure | RNS | Transmed | ISO/IEC 27001:2022 GAP ANALYSIS | Transmed | Abbas | Abbas.Noureddine@transmed.com | Pradeep | GREEN | Ajinkya | Low | On Track | 1 | 1 | 0 | 2025-03-10 | TBD |  |  | 60% | Gap analysis is complete, team is working on the report
137 | RN-534 | Checkpoint | Network Security | RNS | Cadvil - Checkpoint |  | Cadvil | Deepson | deepson@cadvil.ae | Manish Narayanan | GREEN | Vignesh | Medium | On Track | 3 | 0 | 3 | 2025-03-27 | 2025-04-10 |  |  | 10% | Kickoff completed. License to be resolved and delpyment session to be planned
| RN-468 | Checkmarx | AppSec | Vendor | SIB - Checkmarx | Sourcecode review Solution | Sharjah Islamic Bank | Swapnil Ambre | Swapnil.Ambre@sib.ae | Faizan Javed | GREEN | Sean Faizal | Low | On Track | 1 | 0 | 1 | 2025-02-24 | 2025-05-30 |  |  | 10% | Architecture Document submitted for approval
| RN-525 | VAPT | IntelliStrike | RNS | Nextcare VAPT 2025 | 15 Apps | Nextcare | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Ishan Arora | GREEN | Sean Faizal | Low | On Track | 1 | 0 | 1 | 2025-01-01 | 2025-12-31 |  |  | 8% | 2nd Application assessment is in progress
122 | RN -487 | Carbon Black | NW & Sec | Vendor | Protect - Carbon Black App control |  | Protect | Prasad Prabhu | prasad.prabhu@protected.ae | Ishan Arora | GREEN | Ajinkya | Medium | delayed | 1 | 1 | 0 | 2025-01-10 | 2025-03-21 | 2025-04-25 |  | 10% | Prerequisites are ready and environment setup is complete. Customer needs to revert back to initiate app control server installation
| RN-527 | Crowdstrike | Network Security | RNS + Vendor | Americana Food - Crowdstrike | 6000 user rollout & configuartion | Americana Foods | Rupesh Nimbajirao | rborse@americana-food.com | Ashida Khan | GREEN | Sean Faizal | Low | On Track |  |  |  | 2025-02-10 | 2025-05-15 |  |  | 80% | Configurationand user rollout is in progress: 5500+ complete
| RN-528 | Cofense | Network Security | Vendor | OQ Trading - Cofense | Phishing simulation & Training | OQ Trading | Abhilash Radhadevi | abhilash.radhadevi@oq.com | Manish Narayanan | GREEN | Sean Faizal | Low | On Track |  |  |  | Not started | TBD |  |  | 0% | License yet to be activated due to client availability

## Active Milestones
PROJECT MANAGEMENT LOG TEMPLATE
PROJECT MILESTONE REGISTER
The PROJECT Identification portion of this table will automatically populate to the Financial Data, Deliverables and Performance, and Risk Register tabs within this workbook.
PROJECT DATA |  |  |  |  | MILESTONE DATA
NO. | PROJECT ID | Project Type | PROJECT DATA | PROJECT MANAGER | MILESTONE DESCRIPTION | Milestone Status | PLANNED START DATE | PLANNED/Estimated END DATE | Actual End Date | PO Details | PO Amount | Billing Forecast Month | Biling Status | Invoice Date | Payment Satus | Forecast Revenue | Paid Date | OPEN TASKS | CLOSED TASKS | OPEN ISSUES | CLOSED ISSUES | % Completion | Comments
1 | RN-101 | ForcePoint, FP | Tawazun Industrial Park | Sean Faizal | M2 - 70% Upon completion | Delayed | 2022-05-15 | 2025-03-15 |  |  |  | 2024-05-10 | [9 empty] | 98%
2 | RN-101 | ForcePoint, FP | Tawazun Industrial Park | Sean Faizal | M3 - 10% retention after 1 year support (Quarterly End AMC - Q1, Q2, Q3, Q4) | Delayed | - | TBD |  |  |  | Dependant on M2 | [9 empty] | 98%
3 | RN-101 | ForcePoint, FP | Tawazun Industrial Park | Sean Faizal | M4 - 10% retension after 1 year support (Quarterly End AMC - Q1, Q2, Q3, Q4) | Completed | - |  | 2022-01-30 |  |  | COMPLETE |  |  | Paid | [6 empty] | 98%
4 | RN-101 | ForcePoint, FP | Tawazun Industrial Park | Sean Faizal | M5 - 10% retention after 1 year support (Quarterly End AMC - Q1, Q2, Q3, Q4) | Completed | - |  | 2022-01-30 |  |  | COMPLETE |  |  | Paid | [6 empty] | 98%
5 | RN-101 | ForcePoint, FP | Tawazun Industrial Park | Sean Faizal | M6 - 10% retension after 2 year support (Quarterly End AMC - Q3) | Completed | - |  | 2022-01-30 |  |  | COMPLETE |  |  | Paid | [6 empty] | 98%
6 | RN-239 | Sailpoint | Aldar Phase 2 | Laxmi | M8 - 20% upon Release 4(2 apps) - UAT and Go-Live | Not Started | 2023-03-17 |  |  |  |  | 2023-09-01 | COMPLETE | 2023-09-07 |  | 2023-10-06 |  | 40 | 81 |  |  | 59% | client pre-requisities not ready
7 | RN-273 | SailPoint | QIB-Phase 3 (LPO1) | Pallavi Nair | M1 - Sailpoint API Traffic - 50% advance with PO | Completed |  |  | 2023-08-15 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 20% | project on-hold
8 | RN-273 | SailPoint | QIB-Phase 3 (LPO1) | Pallavi Nair | M2 - Sailpoint API Traffic - 50% after integration | On Hold | [5 empty] | 2024-05-10 | [9 empty] | 0%% | project on-hold
9 | RN-273 | SailPoint | QIB-Phase 3 (LPO2) | Pallavi Nair | M1- SailpointGOVcm&LCM EFMS-50% advance with PO | Completed |  |  | 2023-08-15 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
10 | RN-273 | SailPoint | QIB-Phase 3 (LPO2) | Pallavi Nair | M2 - SailpointGOVcm&LCM EFMS- 50% after integration | On Hold | [5 empty] | TBD | [9 empty] | 0%% | project on-hold
11 | RN-273 | SailPoint | QIB-Phase 3 (LPO3) | Pallavi Nair | M1 - IAM Integration for NewGen - 50% advance with PO | Completed |  |  | 2023-08-15 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
12 | RN-273 | SailPoint | QIB-Phase 3 (LPO3) | Pallavi Nair | M2 - IAM Integration for NewGen API - 50% after integration | On Hold | [5 empty] | TBD | [9 empty] | 0%%
13 | RN-273 | SailPoint | QIB-Phase 3 (LPO4) | Pallavi Nair | M1 - Legal System-IAM Integration- 50% advance with PO | Completed |  |  | 2023-08-15 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
14 | RN-273 | SailPoint | QIB-Phase 3 (LPO4) | Pallavi Nair | M2 - Legal System-IAM Integration- 50% after integration | On Hold | [5 empty] | 2024-05-10 | [9 empty] | 0%%
15 | RN-273 | SailPoint | QIB-Phase 3 (LPO5) | Pallavi Nair | M1 - SAS Compliance - 50% advance with PO | Completed |  |  | 2023-08-15 |  |  | COMPLETE | COMPLETE | 2023-07-06 | Paid | 2023-08-06 | [5 empty] | 100%
16 | RN-273 | SailPoint | QIB-Phase 3 (LPO5) | Pallavi Nair | M2 - SAS Compliance - 50% after integration | On Hold | [5 empty] | TBD | [9 empty] | 0%%
17 | RN-273 | SailPoint | QIB Phase 3 - 40 hrs Governance_09042023_CR | Pallavi Nair | M1 - 30 days (15 Apps + PAM Integration) | Completed |  |  | 2023-08-01 |  |  | 2023-08-01 | COMPLETE | 2023-08-01 |  | 2023-08-31 | [5 empty] | 100%
18 | RN-298 | FP DLP & BJ | Nextcare - FP DLP & BJ | Sean Faizal | M1 - Licenses – 100% To be Invoiced upon Delivery of Licenses | Completed |  |  | 2023-07-12 |  |  | COMPLETE | COMPLETE | 2023-07-12 | Paid | 2023-08-11 | 2023-07-28 |  |  |  |  | 100%
19 | RN-298 | FP DLP & BJ | Nextcare - FP DLP & BJ | Sean Faizal | M2 - 50% To be Invoiced upon Data Classification Consultancy Completion | Completed |  |  | 2023-12-14 |  |  | 2023-12-01 | COMPLETE | 2023-12-14 | [7 empty] | 100%
20 | RN-298 | FP DLP & BJ | Nextcare - FP DLP & BJ | Sean Faizal | M - 3 : 50% To be Invoiced upon DLP Implementation Services Completion | Delayed | 2024-02-10 | 2025-03-30 | 2025-03-30 |  |  | 2024-05-31 | [9 empty] | 55%
21 | RN-304 | Zscaler | Deem Finance | Divya | 100% On Delivery of Licenses within 30 Days | Completed |  |  | 2023-08-04 |  |  | 2023-08-01 | COMPLETE | 2023-08-04 | [7 empty] | 100%
22 | RN-304 | Zscaler | Deem Finance | Divya | 50% of payment in Advance on deployment of Services | Completed |  |  | 2023-12-29 |  |  | 2023-12-01 | COMPLETE | 2023-12-29 | [7 empty] | 100%
23 | RN-304 | Zscaler | Deem Finance | Divya | 50% after sign off | Completed |  |  | 2024-04-22 |  |  | 2024-04-19 | COMPLETE | 2024-04-22 | [7 empty] | 100%
24 | RN-305 | VAPT | ENI_Emirates National Investments - VAPT 35% | Vignesh | M1.External Internal assessment with reporting | Completed | 2023-09-01 | 2023-10-09 | 2024-01-03 |  |  | 2024-01-01 | Complete | 2024-01-03 | [7 empty] | 100%
25 | RN-305 | VAPT | ENI_Emirates National Investments - VAPT 35% | Vignesh | M2. External Internal assessment with reporting | Completed | 2023-09-18 | 2023-10-18 | 2024-01-03 |  |  | 2024-01-01 | Complete | 2024-01-03 | [7 empty] | 100%
26 | RN-305 | VAPT | ENI_Emirates National Investments - VAPT 30% | Vignesh | M3. Retesting and Sign off | Delayed |  | TBD | TBD |  |  | 2024-05-10 | [9 empty] | No response from clientd
27 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | Y3- License cost shall be paid annually for 3 Years within 30 days. Subject to submission of complete documentation (Invoice, License Activation Report, Statement of Account) | Not Started | 2025-08-21 | 2026-08-20 |  |  |  | 2025-08-01 | [9 empty] | 0%
28 | RN-322 | ISO Audit | SAAL_ Maintenance of ISO _ August_2023 | Divya | 100% payment | Completed |  |  | 2023-08-11 |  | 5000 | 2023-08-01 | COMPLETE | 2023-08-11 |  | 2023-09-10
29 | RN-323 | Fortigate FW | Gargas Group - FortiGate Firewall 100F X 2_2023+ FortiAnalyser APL | Divya | 100 PERCENT Payment to be invoiced upon delivery of licenses and hardware Services: | Completed |  |  | 2023-09-04 |  |  | 2023-09-01 | COMPLETE | 2023-09-04
30 | RN-323 | Fortigate FW | Gargas Group - FortiGate Firewall 100F X 2_2023+ FortiAnalyser APL | Divya | PS: 50 PERCENT to be paid in Advance | Completed |  |  | 2023-09-04 |  |  | 2023-09-01 | COMPLETE | 2023-09-04
31 | RN-323 | Fortigate FW | Gargas Group - FortiGate Firewall 100F X 2_2023+ FortiAnalyser APL | Divya | PS: 50 PERCENT To be Paid on Signoff. | On Hold |  |  | 2023-09-04 |  |  | 2023-09-01 | COMPLETE | 2023-09-04 | [7 empty] | payment pending
32 | RN-323 | Fortigate FW | Gargas Group - FortiGate Firewall 100F X 2_2023+ FortiAnalyser APL | Divya | AMC : 50PERCENT to be paid in Advance | Completed |  |  | 2023-09-04 |  |  | 2023-09-01 | COMPLETE | 2023-09-04
33 | RN-323 | Fortigate FW | Gargas Group - FortiGate Firewall 100F X 2_2023+ FortiAnalyser APL | Divya | AMC: 50 PERCENT to be paid on Signoff. | On Hold |  |  | 2024-05-10 |  |  | 2024-05-10 | [9 empty] | payment pending
34 | RN-329 | ISO Consulting | DPW_ISO 27001_Consulting_Q3_2023 | Divya | 50% upon completion of documentation | Completed | [5 empty] | 2024-05-10
35 | RN-329 | ISO Consulting | DPW_ISO 27001_Consulting_Q3_2023 | Divya | Balance 50% upon completion of Internal audit, management | Completed |  |  | 2024-06-24 |  |  | 2024-05-10
36 | RN-96 | Palo-Alto | Nextcare PaloAlto | Rubeena | M1 - 30 days from delivery | Completed | 2022-03-14 | 2022-03-14 |  |  |  | COMPLETE | COMPLETE |  | Paid
37 | RN-96 | Palo-Alto | Nextcare PaloAlto | Rubeena | M2 - Initialization, Implementation, Configuration and Signoff (No Payment Term) | Completed | 2022-04-06 | 2023-07-03 |  |  |  | COMPLETE | COMPLETE |  | Paid
38 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | 1- License Amount | Completed |  |  | 2023-11-15 |  |  | 2023-11-01 | Complete | 2023-11-15 | Paid
39 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Platform Installation for UAT and Production environment(30%) | Completed | 2024-03-04 | 2024-06-28 | 2024-09-20 |  |  | 2024-07-24 | [9 empty] | 100%
40 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Internal UAT testing and acceptance for 24 application(5 Apps will be integrated directly in production)(25%) | Completed | 2024-05-13 | 2024-08-09 | 2024-11-27 |  |  | 2024-08-01 | [9 empty] | 100%
41 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Business owner UAT completion for 29 Apps | Completed | 2024-07-15 | 2024-12-05 | 2024-12-05 |  |  | 2024-10-01 | [9 empty] | 100%
42 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Post Go Live testing(10%) | Completed | 2024-09-23 | 2024-11-29 | 2025-01-02 |  |  | 2024-12-01 | [9 empty] | 100%
43 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Knowledge Transfer (10%) | Delayed | 2024-11-04 | 2025-02-28 |  |  |  | 2025-01-31 | [9 empty] | 0%
44 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M1.YEar1.End of each month | Not Started | 2025-03-01 | 2025-03-31 |  |  |  | 2025-01-01
45 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M2.YEar1.End of each month | Not Started | 2025-04-01 | 2025-04-30 |  |  |  | 2025-02-01
46 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M3.YEar1.End of each month | Not Started | 2025-05-01 | 2025-05-31 |  |  |  | 2025-03-01
47 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M4.YEar1.End of each month | Not Started | 2025-06-01 | 2025-06-30 |  |  |  | 2025-04-01
48 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M5.YEar1.End of each month | Not Started | 2025-07-01 | 2025-07-31 |  |  |  | 2025-05-01
49 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M6.YEar1.End of each month | Not Started | 2025-08-01 | 2025-08-30 |  |  |  | 2025-06-01
50 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M7.YEar1.End of each month | Not Started | 2025-09-01 | 2025-09-30 |  |  |  | 2025-07-01
51 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M8.YEar1.End of each month | Not Started | 2025-10-01 | 2025-10-31 |  |  |  | 2025-08-01
52 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M9.YEar1.End of each month | Not Started | 2025-11-01 | 2025-11-30 |  |  |  | 2025-09-01
53 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M10.YEar1.End of each month | Not Started | 2025-12-01 | 2025-12-31 |  |  |  | 2025-10-01
54 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M11.YEar1.End of each month | Not Started | 2026-01-01 | 2026-01-31 |  |  |  | 2025-11-01
55 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | M12.YEar1.End of each month | Not Started | 2026-02-01 | 2026-02-28 |  |  |  | 2025-12-01
56 | RN-334 | SailPoint | Abu Dhabi Media (AD Media) | Laxmi | Year2 Resource Cost | Not Started | 2026-03-01 | 2026-03-31 |  |  |  | 2026-01-01
57 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 1 : 20 % Project Customer Kick off, Design Workshops, Recruitment Gathering, Gaps Assessment & High-Level Design with HLD Submission (all in scope Apps) | Completed | 2024-02-22 |  | 2024-05-10 |  |  | 2024-05-10 | [9 empty] | Invoiced | project on-hold
58 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 2 : 20% Installation & Base Setup, LCM, Compliance Module | On Hold | 2024-02-20 | 2024-07-29 |  |  |  | 2024-08-16
59 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 3 :25 % Sprint 1: Integration of 2 Core Apps – UAT | On Hold | 2024-05-14 | 2024-06-03 |  |  |  | 2024-06-21
60 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 4 : 25% Sprint 2: SailPoint Integration: 4 Apps UAT | Not Started | 2024-07-30 | 2024-09-08 |  |  |  | 2024-09-20
61 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 5 : 10% OD, Final Go-live, Documentation, Training & Sign-Off | Not Started | 2024-09-09 | 2024-10-30 |  |  |  | 2024-11-15
62 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 6 : SailPoint Technical Admin Training for Two Users | Not Started | 2024-10-15 | 2024-10-30 |  |  |  | 2024-11-15
63 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 7 : Onsite Support :6 months, Offsite Support: 6 months. After completion of each quarter, RNS shall raise invoice | Not Started | 2024-11-01 | 2025-01-31 |  |  | Q1 | 2025-02-07
64 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 7 : Onsite Support :6 months, Offsite Support: 6 months. After completion of each quarter, RNS shall raise invoice | Not Started | 2025-02-01 | 2025-04-30 |  |  | Q2 | 2025-05-02
65 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 7 : Onsite Support :6 months, Offsite Support: 6 months. After completion of each quarter, RNS shall raise invoice | Not Started | 2025-05-01 | 2025-07-31 |  |  | Q3 | 2025-08-01
66 | RN-338 | SailPoint | Doha Bank | Laxmi | Milestone 7 : Onsite Support :6 months, Offsite Support: 6 months. After completion of each quarter, RNS shall raise invoice | Not Started | 2025-08-01 | 2025-10-31 |  |  | Q4 | 2025-11-07
67 | RN-358 | VAPT | DNI_VAPT internal and External Remediation_2023 | Vignesh | Initial Internal Assessment with Reporting = 40% | Completed | 2023-12-12 | 2023-12-20 | 2024-06-07 |  |  | 2024-05-10 | [9 empty] | 100%
68 | RN-358 | VAPT | DNI_VAPT internal and External Remediation_2023 | Vignesh | Initial External Assessment with Reporting = 40% | Completed | 2023-12-06 | 2024-01-05 | 2024-06-07 |  |  | 2024-05-10 | [9 empty] | 100%
69 | RN-358 | VAPT | DNI_VAPT internal and External Remediation_2023 | Vignesh | Retesting & Reporting = 20% | On Track | 2025-03-21 | 2025-04-21 | TBD |  |  | 2024-05-30 | [9 empty] | Follow-up is going on
70 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 1st Year of the Service - Upon utilization of 12 man-days | Completed | 2024-01-08 | 2024-05-28 | 2024-05-28 |  |  | 2024-05-03 | [9 empty] | 100%
71 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 1st Year of the Service - Upon utilization of 12 man-days | Completed | 2024-09-09 | 2025-03-10 | 2025-03-10 |  |  | 2024-05-17 | [9 empty] | Based on client requirement
72 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 1st Year of Service - Upon utilization of 13 man-days | Not Started | 2025-03-10 |  |  |  |  | TBD | [9 empty] | Based on client requirement | 3 days utilesed for the previous reqirement for mobile assessment
73 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 1st Year of the Service - Upon utilization of 13 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
74 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 2nd Year of the Service - Upon utilization of 12 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
75 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 2nd Year of the Service - Upon utilization of 12 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
76 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 2nd Year of Service - Upon utilization of 13 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
77 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 2nd Year of the Service - Upon utilization of 13 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
78 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 3rd Year of the Service - Upon utilization of 12 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
79 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 3rd Year of the Service - Upon utilization of 12 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
80 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 3rd Year of Service - Upon utilization of 13 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
81 | RN-363 | Intellistrike | General Pension and Social Security Authority (GPSSA)_VAPT | Vignesh | 3rd Year of the Service - Upon utilization of 13 man-days | Not Started | [5 empty] | TBD | [9 empty] | Based on client requirement
82 | RN-384 | MS Automation | Authority of Social Contribution - MAAN_Microsoft Automation | Sean Faizal | Analytics Requirement Specification Document (RSD) - Business analysis requirements document | Completed | 2024-02-06 | 2025-01-30 | 2025-01-30 |  |  | 2023-12-01 | COMPLETE | 2023-12-19 | [7 empty] | 90%
83 | RN-384 | MS Automation | Authority of Social Contribution - MAAN_Microsoft Automation | Sean Faizal | RNS Dashboards Prototypes - Prototype of the dashboard. visualizations | Completed | 2024-03-18 |  | 2024-10-18 |  |  | 2023-12-01 | COMPLETE | 2023-12-19 | [7 empty] | 100%
84 | RN-384 | MS Automation | Authority of Social Contribution - MAAN_Microsoft Automation | Sean Faizal | RNS Professional Services: Development of 15-20 Dashboards, Development of 5 Statistical Reports (Excel, PDF, Word) | Completed | 2024-03-18 | 2025-01-30 | 2025-01-30 |  |  | 2023-12-01 | COMPLETE | 2023-12-19 | [7 empty] | 95%
85 | RN-384 | MS Automation | Authority of Social Contribution - MAAN_Microsoft Automation | Sean Faizal | RNS Solution warranty - 90 Days Warranty 1 | On Track | 2025-02-10 | 2025-05-09 |  |  |  | 2023-12-01 | COMPLETE | 2023-12-19 | [7 empty] | 0%
86 | RN-396 | VAPT | Al Ahli Bank_VAPT Dec 23 | Vignesh | 20% after contract sign-off | Completed | 2023-12-25 | 2024-02-01 | 2024-03-06 |  |  | 2024-03-01 | COMPLETE | 2024-03-06 | [7 empty] | 100%
87 | RN-396 | VAPT | Al Ahli Bank_VAPT Dec 23 | Vignesh | 40% after submission and sign-off of final report (Testing 1) | Completed | 2023-12-19 | 2024-07-30 | 2024-08-08 |  |  | 2024-05-10 | [9 empty] | 100%
88 | RN-396 | VAPT | Al Ahli Bank_VAPT Dec 23 | Vignesh | 40% after submission and sign-off of final report (Testing 2) | On Track | 2024-12-23 | 2025-05-01 | [13 empty] | client has to come back when they are ready
89 | RN-420 | Fortigate FW | Gargash_Fortigate FW | Divya | 100% upon hardware delivery | Completed |  |  | 2023-12-27 |  |  | 2023-12-01 | COMPLETE | 2023-12-27
90 | RN-402 | VAPT | Balmer Lawrie - VAPT | Vignesh | External Initial Assessment with Reporting = 40% | Completed | 2024-01-15 | 2024-01-18 | 2024-03-26 |  |  | 2024-03-29 | Complete | 2024-03-26 | [7 empty] | 100%
91 | RN-402 | VAPT | Balmer Lawrie - VAPT | Vignesh | Internal Initial Assessment with Reporting = 40% | Completed | 2024-01-17 | 2024-03-19 | 2024-03-26 |  |  | 2024-03-29 | Complete | 2024-03-26 | [7 empty] | 100%
92 | RN-402 | VAPT | Balmer Lawrie - VAPT | Vignesh | Retesting & Signoff = 20% | Completed | 2024-10-01 | 2025-02-07 | 2025-02-20 |  |  | 2024-05-10 | [9 empty] | 90%
93 | RN-405 | Palo-Alto | Intigral - Palo Alto PS Only | Divya | Services: To be Invoiced upon Sign-Off | Completed |  |  | 2024-08-20 |  |  | 2024-05-03
94 | RN-410 | Zscaler | Seddiqui Holding - Zscaler | Divya | 100% to be invoiced upon delivery of licenses | Completed |  |  | 2024-02-21 |  |  | 2024-02-01 | Complete | 2024-02-22 | [7 empty] | 100%
95 | RN-410 | Zscaler | Seddiqui Holding - Zscaler | Divya | Services & deployment: 50% Advance | Completed |  |  | 2024-02-21 |  |  | 2024-02-01 | Complete | 2024-02-22 | [7 empty] | 100%
96 | RN-410 | Zscaler | Seddiqui Holding - Zscaler | Divya | Services & deployment: 50% on completion | Completed |  | 2024-05-18 | 2024-07-30 |  |  | 2024-05-18 | [9 empty] | 100%
97 | RN-409 | Barracuda WAF | GulF Marine Services_Barracuda WAF | Divya | As per Agreed terms | Completed |  |  | 2024-03-08 |  |  | 2024-02-01 | Complete | 2024-02-09 | [7 empty] | 100%
98 | RN-405 | Palo-Alto | INTIGRAL_PaloAlto_Renewal_PS/AMC_Jan_2024 | Divya | Product: To be invoiced upon delivery of Licenses | Completed | 2024-09-10 | 2024-09-10 | 2024-09-10 | [12 empty] | 100%
99 | RN-405 | Palo-Alto | INTIGRAL_PaloAlto_Renewal_PS/AMC_Jan_2024 | Divya | Services: To be Invoiced upon Sign-Off | Completed | 2024-09-10 | 2024-11-07 | 2024-11-07 |  |  | TBD | [9 empty] | 100%
100 | RN-414 | Force Point, DLP & BJ | Emirates Steel _Protivity _DataSecurity _ESA_DC&DLP_Nov_2023 | Divya | 100% of license to be Invoiced upon delivery of license | Completed |  |  | 2024-02-21 |  |  | 2024-03-13 | Complete | 2024-03-13 | [7 empty] | 100%
101 | RN-414 | Force Point, DLP & BJ | Emirates Steel _Protivity _DataSecurity _ESA_DC&DLP_Nov_2023 | Divya | 50% of Services upon completion of DLP Suite as per scope of work | Completed |  | 2024-12-15 | Jan 31-2025 |  |  | TBD
102 | RN-415 | ISO Consulting | Health at Hand_ISO Consulting and Certification | Divya | 50% payment with the contract signature | Completed |  |  | 2024-02-29 |  |  | 2024-03-29 | COMPLETE | 2024-03-28 | [7 empty] | 75%
103 | RN-415 | ISO Consulting | Health at Hand_ISO Consulting and Certification | Divya | 25% completion on documentation phase | Completed |  | 2024-11-15 | 2024-10-11 |  |  | 2024-06-14 | [9 empty] | 75%
104 | RN-415 | ISO Consulting | Health at Hand_ISO Consulting and Certification | Vignesh | 15% on completion of internal audit | On Track | 2025-03-11 | 2025-04-24 |  |  |  | 2024-06-14
105 | RN-415 | ISO Consulting | Health at Hand_ISO Consulting and Certification | Vignesh | Balance 10% upon successful completion of certification | Not Started | TBD | TBD |  |  |  | 2024-06-30
106 | RN-415 | ISO Consulting | Health at Hand_ISO Consulting and Certification | Vignesh | 2nd year of Service - for maitnenance of ISO & Cert - 100% payment in advance | Not Started | TBD | TBD |  |  |  | 2025-03-01
107 | RN-415 | ISO Consulting | Health at Hand_ISO Consulting and Certification | Vignesh | 3rd year of Service - for maitnenance of ISO & Cert - 100% payment in advance | Not Started | TBD | TBD |  |  |  | 2026-03-01
108 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | license | Completed |  |  | 2023-12-01 |  |  | 2023-12-01 | COMPLETE |  | Paid | [6 empty] | 100%
109 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | 30% to be invoiced Upon Project Kick-off | Completed | 2024-01-30 |  | 2024-01-30 |  |  | 2024-01-01 | COMPLETE |  | Not Received | [6 empty] | 100%
110 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | 30% to be invoiced Upon UAT Testing Completion of 5 Apps UNBILLED | On Hold | 2024-03-24 | 2024-07-30 |  |  |  | 2024-05-01 |  |  | Invoice submitted already | [6 empty] | It is still not started
111 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | 20% to be invoiced Upon UAT Testing Completion of 10 Apps UNBILLED | Not Started | 2024-05-24 | 2024-07-28 |  |  |  | 2024-07-01 | [9 empty] | 0%
112 | RN-185 | SailPoint | Intigral Sailpoint Phase 2 | Laxmi | 20% to be invoiced Upon Project Sign-off | Not Started | 2024-07-29 | 2024-08-06 |  |  |  | 2024-08-01 | [9 empty] | 0%
113 | RN-421 | Darktrace | Seddiqui Holding - Darktrace | Divya | 100% to be invoiced upon delivery of licenses | Completed |  |  | 2024-03-28 |  |  | 2024-03-29 | COMPLETE | 2024-03-28 | [7 empty] | 100%
114 | RN-398 | Rapid 7 MDR | DAMAC OT &T Rapid 7-MDR - Riyadh | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
115 | RN-398 | Rapid 7 MDR | DAMAC OT &T Rapid 7-MDR - Riyadh | Divya | M2 #Deployment & configuration & connectivity to insight platform | Completed |  |  | Dec-27-2024
116 | RN-398 | Rapid 7 MDR | DAMAC OT &T Rapid 7-MDR - Riyadh | Divya | M3 #Go Live monitoring and Sign -off | Completed |  |  | Dec-27-2024
117 | RN-398 | Rapid 7 IVM | DAMAC OT &T Rapid 7-IVM - Riyadh | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
118 | RN-398 | Rapid 7 IVM | DAMAC OT &T Rapid 7-IVM - Riyadh | Divya | M2 # Deployment, policy scans, config live boards | Completed |  |  | Dec-27-2024
119 | RN-398 | Rapid 7 IVM | DAMAC OT &T Rapid 7-IVM - Riyadh | Divya | M3 # HLD and LLD Document - Sign -off | Completed |  |  | Dec-27-2024
120 | RN-398 | Cybereason | DAMAC OT &T Cybereason - Riyadh | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
121 | RN-398 | Cybereason | DAMAC OT &T Cybereason - Riyadh | Divya | M2 # FW config, MDR onboarding, enable protection and sensor deployment | Completed |  |  | Dec-27-2024
122 | RN-398 | Cybereason | DAMAC OT &T Cybereason - Riyadh | Divya | M3 # HLD and LLD Document - Sign -off | Completed |  |  | Dec-27-2024
123 | RN-398 | Forecepoint DLP | DAMAC OT &T Forecepoint DLP - Riyadh | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
124 | RN-398 | Forecepoint DLP | DAMAC OT &T Forecepoint DLP - Riyadh | Divya | M2 # DLP policies in block mode, fine tuning, Documentation and KT | Completed |  |  | Dec-27-2024
125 | RN-398 | Forecepoint DLP | DAMAC OT &T Forecepoint DLP - Riyadh | Divya | M3 # Go Live monitoring and Sign -off | Completed |  |  | Dec-27-2024
126 | RN-398 | Forecepoint Proxy | DAMAC OT &T Forecepoint Proxy - Riyadh | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
127 | RN-398 | Forecepoint Proxy | DAMAC OT &T Forecepoint Proxy - Riyadh | Divya | M2 # Deployment, integration with FP DLP & alert config | Completed |  |  | Dec-27-2024
128 | RN-398 | Forecepoint Proxy | DAMAC OT &T Forecepoint Proxy - Riyadh | Divya | M3 # Documentation, KT and Sign -off | Completed |  |  | Dec-27-2024
129 | RN-398 | VAPT | DAMAC OT &T - VAPT- Riyadh | Divya | M1 # External Assessments | Delayed
130 | RN-398 | VAPT | DAMAC OT &T - VAPT- Riyadh | Divya | M2 # Internal Assessments | Delayed
131 | RN-398 | VAPT | DAMAC OT &T - VAPT- Riyadh | Divya | M3 # Physical Assessments | Delayed
132 | RN-398 | VAPT | DAMAC OT &T - VAPT- Riyadh | Divya | M4 # Config Review and AD Assessment | Delayed
133 | RN-398 | VAPT | DAMAC OT &T - VAPT- Riyadh | Divya | M5 # Retesting of External and Internal, CR and AD | Delayed
134 | RN-398 | VAPT | DAMAC OT &T - VAPT- Riyadh | Divya | M6 # Sign -off | Delayed
135 | RN-398 | IntelliDeploy | DAMAC OT &T - OT&T Resource - Riyadh | Divya | Q1 # Advance | Delayed |  |  | Dec-27-2024
136 | RN-398 | IntelliDeploy | DAMAC OT &T - OT&T Resource - Riyadh | Divya | Q2 # Advance | Delayed |  |  | Dec-27-2024
137 | RN-398 | IntelliDeploy | DAMAC OT &T - OT&T Resource - Riyadh | Divya | Q3 # Advance | Delayed |  |  | Dec-27-2024
138 | RN-398 | IntelliDeploy | DAMAC OT &T - OT&T Resource - Riyadh | Divya | Q4 # Advance | Delayed |  |  | Dec-27-2024
139 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Riyadh | Divya | M1 # Delivery of license and hardware | Completed | [15 empty] | 100%
140 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Riyadh | Divya | M2 # Data gathering, solution design and approval | Completed |  |  | Dec-27-2024
141 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Riyadh | Divya | M3 # Network and Virtual Env readiness, smart polling | Completed |  |  | Dec-27-2024
142 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Riyadh | Divya | M4 # Deployment and UAT sign off | Completed |  |  | Dec-27-2024
143 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Riyadh | Divya | M5 # fine tuning, KT and Project Closure | Completed |  |  | Dec-27-2024
144 | RN-398 | Rapid 7 MDR | DAMAC OT &T Rapid 7-MDR - Damam | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
145 | RN-398 | Rapid 7 MDR | DAMAC OT &T Rapid 7-MDR - Damam | Divya | M2 #Deployment & configuration & connectivity to insight platform | Completed |  |  | Dec-27-2024
146 | RN-398 | Rapid 7 MDR | DAMAC OT &T Rapid 7-MDR - Damam | Divya | M3 #Go Live monitoring and Sign -off | Completed |  |  | Dec-27-2024
147 | RN-398 | Rapid 7 IVM | DAMAC OT &T Rapid 7-IVM - Damam | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
148 | RN-398 | Rapid 7 IVM | DAMAC OT &T Rapid 7-IVM - Damam | Divya | M2 # Deployment, policy scans, config live boards | Completed |  |  | Dec-27-2024
149 | RN-398 | Rapid 7 IVM | DAMAC OT &T Rapid 7-IVM - Damam | Divya | M3 # HLD and LLD Document - Sign -off | Completed |  |  | Dec-27-2024
150 | RN-398 | Cybereason | DAMAC OT &T Cybereason - Damam | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
151 | RN-398 | Cybereason | DAMAC OT &T Cybereason - Damam | Divya | M2 # FW config, MDR onboarding, enable protection and sensor deployment | Completed |  |  | Dec-27-2024
152 | RN-398 | Cybereason | DAMAC OT &T Cybereason - Damam | Divya | M3 # HLD and LLD Document - Sign -off | Completed |  |  | Dec-27-2024
153 | RN-398 | Forecepoint DLP | DAMAC OT &T Forecepoint DLP - Damam | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
154 | RN-398 | Forecepoint DLP | DAMAC OT &T Forecepoint DLP - Damam | Divya | M2 # DLP policies in block mode, fine tuning, Documentation and KT | Completed |  |  | Dec-27-2024
155 | RN-398 | Forecepoint DLP | DAMAC OT &T Forecepoint DLP - Damam | Divya | M3 # Go Live monitoring and Sign -off | Completed |  |  | Dec-27-2024
156 | RN-398 | Forecepoint Proxy | DAMAC OT &T Forecepoint Proxy - Damam | Divya | M1 # Delivery of licenses | Completed |  |  | Dec-27-2024
157 | RN-398 | Forecepoint Proxy | DAMAC OT &T Forecepoint Proxy - Damam | Divya | M2 # Deployment, integration with FP DLP & alert config | Completed |  |  | Dec-27-2024
158 | RN-398 | Forecepoint Proxy | DAMAC OT &T Forecepoint Proxy - Damam | Divya | M3 # Documentation, KT and Sign -off | Completed |  |  | Dec-27-2024
159 | RN-398 | VAPT | DAMAC OT &T - VAPT- Damam | Divya | M1 # External Assessments | Delayed
160 | RN-398 | VAPT | DAMAC OT &T - VAPT- Damam | Divya | M2 # Internal Assessments | Delayed
161 | RN-398 | VAPT | DAMAC OT &T - VAPT- Damam | Divya | M3 # Physical Assessments | Delayed
162 | RN-398 | VAPT | DAMAC OT &T - VAPT- Damam | Divya | M4 # Config Review and AD Assessment | Delayed
163 | RN-398 | VAPT | DAMAC OT &T - VAPT- Damam | Divya | M5 # Retesting of External and Internal, CR and AD | Delayed
164 | RN-398 | VAPT | DAMAC OT &T - VAPT- Damam | Divya | M6 # Sign -off | Delayed
165 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Damam | Divya | M1 # Delivery of license and hardware | Completed | [15 empty] | 100%
166 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Damam | Divya | M2 # Data gathering, solution design and approval | Completed |  |  | Dec-27-2024
167 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Damam | Divya | M3 # Network and Virtual Env readiness, smart polling | Completed |  |  | Dec-27-2024
168 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Damam | Divya | M4 # Deployment and UAT sign off | Completed |  |  | Dec-27-2024
169 | RN-398 | Nozomi NW | DAMAC OT &T - Nozomi NW - Damam | Divya | M5 # fine tuning, KT and Project Closure | Completed |  |  | Dec-27-2024
170 | RN-422 | SailPoint | KalaamAlQureshi_SailPointServices_Dec_2023 | Laxmi | Milestone 1: High Level Design Sign-off - 20% | Completed | 2024-05-08 | 2024-08-13 | 2024-08-13 | [12 empty] | 100%
171 | RN-422 | SailPoint | KalaamAlQureshi_SailPointServices_Dec_2023 | Laxmi | Milestone 2: Installation Sign-off of PROD Environment - 30% | Completed | 2024-05-06 |  | 2024-07-04 | [12 empty] | 100%
172 | RN-422 | SailPoint | KalaamAlQureshi_SailPointServices_Dec_2023 | Laxmi | Milestone 3: UAT Sign-Off for 3 applications - 30% | Delayed | 2024-05-29 | 2025-02-20 | [13 empty] | 80%
173 | RN-422 | SailPoint | KalaamAlQureshi_SailPointServices_Dec_2023 | Laxmi | Milestone 4: Sign-Off for RBAC (3 application) & Final Go-live, Documentation and Handover- 20% | On Track | 2025-05-13 | 2025-06-05 | [13 empty] | 0%
174 | New | Forcepoint | Deem Finance_Forcepoint | Divya | 100% to be invoiced upon delivery of licenses | Completed |  |  | 2024-04-01 |  |  |  | COMPLETE | 2024-04-01 | [7 empty] | 100%
175 | New | Forcepoint | Deem Finance_Forcepoint | Divya | 50% advance | Completed |  |  | 2024-04-01 |  |  |  | COMPLETE | 2024-04-01 | [7 empty] | All the deem finance milestones has been completed except one and invoice is also done
176 | RN-428 | Forcepoint | Deem Finance_Forcepoint | Divya | 50% upon sign off | Completed | 2024-08-10 | 2024-09-10 | 2024-10-06 |  |  | TBD | [9 empty] | this milestone is pending and to be invoiced.. Find the end date
177 | RN-424 | VAPT | Al Nabooda VAPT | Vignesh | External First Assessment with Reporting = 15% | Completed | 2024-05-13 | 2024-05-15 | 2024-06-19 | [12 empty] | 100%
178 | RN-424 | VAPT | Al Nabooda VAPT | Vignesh | First Assessment with Reporting = 30% - | Completed | 2024-05-13 | 2024-05-23 | 2024-06-19 | [12 empty] | 100%
179 | RN-424 | VAPT | Al Nabooda VAPT | Vignesh | External Second Assessment with Reporting = 15% | On Track | 2025-03-03 | 2025-04-15 | [13 empty] | 0%
180 | RN-424 | VAPT | Al Nabooda VAPT | Vignesh | Internal Second Assessment with Reporting = 30% | On Track | 2025-03-10 | 2025-04-15 | [13 empty] | 0%
181 | RN-424 | VAPT | Al Nabooda VAPT | Vignesh | Retesting Signoff=10% | Not Started | TBD | TBD | [13 empty] | 0%
182 | RN-425 | SailPoint | Network International Dubai FAM Upgrade | Laxmi | a. 50% to be invoiced upon Project Kick-off | Completed | 2024-07-04 | 2024-07-04 | 2024-07-04 |  |  | 2024-05-03 | [9 empty] | 100%
183 | RN-425 | SailPoint | Network International Dubai FAM Upgrade | Laxmi | b. 50% to be incoived upon Project Sign-off | On Hold | 2024-07-10 | 2024-11-08 |  |  |  | 2024-06-15 | [9 empty] | 0%
184 | RN-443 | VAPT | LEOS DEvelopment - VAPT | Sean Faizal | Services & Deployement: 50% Advance | Completed | NA |  | 2024-07-20 | [12 empty] | 100%
185 | RN-443 | VAPT | LEOS DEvelopment - VAPT | Sean Faizal | Services & Deployement: 50% on Completion | Delayed | 2024-06-26 | TBD | TBD | [12 empty] | 50%
190 | RN-458 | Blackberry | Tawazun Coucil | Vignesh | To be Invoiced Upon Project Signoff | Completed | 2024-07-30 | 2024-12-25 | 2025-01-16 | [12 empty] | 100%
191 | RN-442 | ISO | Ajman chambers | Vignesh | Stage 1 : 25% - Documentation completion & review | On Track | 2024-06-18 | 2025-04-24 | [13 empty] | 50%
192 | RN-442 | ISO | Ajman chambers | Vignesh | Stage 2 : 25%- Documentation completion & review | On Track | 2024-06-18 | 2025-04-24 | [13 empty] | 50%
193 | RN-442 | ISO | Ajman chambers | Vignesh | Stage 3 : 25% - Completeion of Internal Audit | Not Started | [15 empty] | 0%
194 | RN-442 | ISO | Ajman chambers | Vignesh | Stage 4 : 25% - Completion of Certification Audit | Not Started | [15 empty] | 0%
195 | RN-461 | VAPT | Sobha realty - VAPT | Vignesh | External Initial Assessment with Reporting = 30% | On Track | 2024-07-29 | 2025-05-30 | [13 empty] | 90%
196 | RN-461 | VAPT | Sobha realty - VAPT | Vignesh | Internal Initial Assessment with Reporting = 20% | On Track | 2024-07-29 | 2025-05-30 | [13 empty] | 70%
197 | RN-461 | VAPT | Sobha realty - VAPT | Vignesh | External Second Assessment with Reporting (6 Months from LPO) = 25% | On Track | 2025-02-24 | 2025-05-30 | [13 empty] | 0%
198 | RN-461 | VAPT | Sobha realty - VAPT | Vignesh | Internal Second Assessment with Reporting (6 Months from LPO) = 20% | On Track | 2025-02-24 | 2025-05-30 | [13 empty] | 0%
199 | RN-461 | VAPT | Sobha realty - VAPT | Vignesh | Retesting & Signoff = 5% | On Track | 2025-11-11 | 2025-05-30 | [13 empty] | 0%
200 | RN -445 | Sailpoint | Tawazun Coucil | Bhushan | Milestone 1: SailPoint Upgrade (Version 8.1 to 8.4 P1) UAT | Completed | 2024-08-14 | 2024-09-26 | 2024-09-04 | [12 empty] | 100%
201 | RN -445 | Sailpoint | Tawazun Coucil | Bhushan | Milestone 2: SailPoint Upgrade (Version 8.1 to 8.4 P1) PROD | Completed | 2024-09-27 | 2024-11-07 | 2024-10-01 | [12 empty] | 100%
202 | RN -445 | Sailpoint | Tawazun Coucil | Bhushan | Milestone 3: Workflow Enhancements | Delayed | 2024-11-08 | 2025-02-14 | [13 empty] | 80%
203 | RN-472 | VAPT | DNIR - VAPT | Vignesh | Internal Initial Assessment with Reporting = 70% | Completed | 2024-10-15 | 2024-11-17 | 2025-02-26 | [12 empty] | 100% | waiting for sign-off
204 | RN-472 | VAPT | DNIR - VAPT | Vignesh | Signoff = 30% | Completed | 2024-10-15 | 2024-11-17 | 2025-02-26 | [12 empty] | 100% | waiting for sign-off
205 | RN-434 | ISO | Sharjah Asset management | Vignesh | 50% to be invoiced upon signing the contract | Completed
206 | RN-434 | ISO | Sharjah Asset management | Ajinkya | 25% on completion of documentation phase | On Track | 2024-06-24 | 2025-03-15
207 | RN-434 | ISO | Sharjah Asset management | Ajinkya | 15% on completion of Internal Audit and Management review | Not Started
208 | RN-434 | ISO | Sharjah Asset management | Ajinkya | Balance 10% on successful completion of certification | Not Started
209 | RN-468 | Zscaler | Mashreq Bank - Zero Trust | Sean Faizal | A) i) Year 1: 50% to be invoiced upon contract Signature | Completed | 2024-07-01 | 2024-07-10 | 2024-07-10 | [12 empty] | 100%
210 | RN-468 | Zscaler | Mashreq Bank - Zero Trust | Sean Faizal | A) ii) Year 1: 50% to be invoiced upon rollout of 5000 users, go-live and signoff | On Track | 2024-08-02 | 2025-06-30
211 | RN-468 | Zscaler | Mashreq Bank - Zero Trust | Sean Faizal | A) iii) Year 2 & 3: 100% to be invoiced anually based on licenses renewal | On Track | TBD | 2026 -Jun | TBD
212 | RN-468 | Zscaler | Mashreq Bank - Zero Trust | Sean Faizal | B) i) 30% to be invoiced on contract signature | Completed | 2024-07-01 | 2024-07-10 | 2024-07-10
213 | RN-468 | Zscaler | Mashreq Bank - Zero Trust | Sean Faizal | B ii) 30% upon completion of Pilot Testing and UAT | Completed | 2024-10-15 | 2025-03-10 | 2025-03-10
| RN-468 | Zscaler | Mashreq Bank - Zero Trust | Sean Faizal | B iii) 40% 5000 users rollout, go-live, based on the sign-off | On Track | 2024-10-17 | 2025-06-30
215 | RN-464 | Checkmarx | Emirates Steel Arkan - Checkmarx | Sean Faizal | 100% invoice submission upon delivery of licenses | Completed | 2024-08-19 | 2024-09-30 | 2024-08-19
216 | RN-469 | Qualys | Nextcare Qualys | Sean Faizal | 100% Advance along with the LPO | Completed | 2024-07-31 | 2024-07-31 | 2024-07-31
222 | RN-480 | ISO | Katim - ISO | Vignesh | Milestone 1: GAP Analysis = 15% | Delayed | 2024-10-07 | 2025-04-17 | [13 empty] | 100% | waiting for sign-off
223 | RN-480 | ISO | Katim - ISO | Vignesh | Milestone 2: Documentation Preparation C Documentation Review '= 40% | Delayed | 2024-10-07 | 2025-04-17 | [13 empty] | 100% | waiting for sign-off
224 | RN-480 | ISO | Katim - ISO | Vignesh | Milestone 3: Training, Implementation Assistance C Management System Implementation = 15% | Delayed | 2024-10-07 | 2025-04-17 | [13 empty] | 100% | waiting for sign-off
225 | RN-480 | ISO | Katim - ISO | Vignesh | Milestone 4: Internal Audit C CAR Closure = 20% | Delayed | 2024-10-07 | 2025-04-17 | [13 empty] | 100% | waiting for sign-off
226 | RN-480 | ISO | Katim - ISO | Vignesh | Milestone 5: SDLC Gap Assessment = 10% | Not Started | 2025-01-20 | [14 empty] | 0% | waiting for sign-off
227 | RN-479 | VAPT | Katim - VAPT | Vignesh | Milestone 1: External Initial Assessment with Reporting = 50% | Not Started | 2025-01-20 | [14 empty] | 0%
228 | RN-479 | VAPT | Katim - VAPT | Vignesh | Milestone 2: Internal Initial Assessment with Reporting = 40% | Not Started | 2025-01-20 | [14 empty] | 0%
229 | RN-479 | VAPT | Katim - VAPT | Vignesh | Milestone 3: Retesting C Reporting = 10% | Not Started | 2025-01-20 | [14 empty] | 0%
230 | RN-483 | VAPT | Al Ahli Bank - Source code review | Vignesh | 80% after initial assessment with reporting | Completed | 2025-02-16 | 2025-03-28 | 2025-03-24 | [12 empty] | 0%
231 | RN-483 | VAPT | Al Ahli Bank - Source code review | Vignesh | 20% after Retesting and sign-off. | Not Started | [15 empty] | 0%
232 | RN-482 | SailPoint | SIB | Pallavi Nair | 50% UAT Signoff for IIQ Upgrade (8.1-->8.3p3) | Delayed | 2024-12-09 | 2025-03-05 | 2025-04-09 | [12 empty] | 90% | awaiting sign-off
233 | RN-482 | SailPoint | SIB | Pallavi Nair | 50% Signoff for IIQ Prod Upgrade (8.1-->8.3p3) | Delayed | 2025-01-17 | 2025-03-14 | TBD | [12 empty] | 0%
234 | RN-482 | SailPoint | SIB | Pallavi Nair | 50% UAT Signoff FAM Upgrade (8.2-->8.4p3) | Delayed | 2025-01-22 | 2025-03-31 | TBD | [12 empty] | 0%
235 | RN-482 | SailPoint | SIB | Pallavi Nair | 50% on Sign off FAM Prod Upgrade (8.2→8.4p3) | Delayed | 2025-01-31 | 2025-03-31 | TBD | [12 empty] | 0%
236 | RN-473 | Akamai | TDRA - AKAMAI | Vignesh | Monthly charge 2024 from 1st June 2024 till 31st December 2024 | Completed | 2024-11-01 | 2025-04-01 | 2024-12-31 | [12 empty] | 80%
| RN-473 | Akamai | TDRA - AKAMAI | Vignesh | One time charge | Completed | 2024-11-01 | 2024-11-01
| RN-473 | Akamai | TDRA - AKAMAI | Vignesh | Monthly charge 2025 from 1st Jan 2025 till 31st December 2025 | On Track | 2025-05-01 | 2026-04-30
| RN-473 | Akamai | TDRA - AKAMAI | Vignesh | Monthly charge 2026 from 1st Jan 2026 till 31st December 2026 | Not Started | 2026-05-01 | 2027-04-30
| RN-473 | Akamai | TDRA - AKAMAI | Vignesh | Monthly charge 2027 from 1st Jan 2027 till 31st December 2027 | Not Started | 2027-05-01 | 2028-04-30
238 | RN - 486 | Checkmarx | ADDOF Checkmarx | Vignesh | a.Licenses: 100 % upon delivery of licenses payable within less than 30 days from invoice date | Completed | 2024-11-04 | 2024-11-04 | 2024-12-10 | [12 empty] | 100%
239 | RN - 487 | Checkmarx | ADDOF Checkmarx | Vignesh | b.Services: 100% upon completion of the implementation scope. | Completed | 2024-11-05 | 2024-12-30 | 2024-12-12 | [12 empty] | 100%
240 | RN-490 | Barracuda | Gulf Cement | Vignesh | 100% to be invoiced upon delivery of licenses | Completed | 2024-11-05 | 2024-11-05 | 2025-01-24 | [12 empty] | 100%
241 | RN-490 | Barracuda | Gulf Cement | Vignesh | 50% advance before starting implementation | Completed | 2024-11-21 | 2024-11-22 | 2025-01-24 | [12 empty] | 100%
242 | RN-490 | Barracuda | Gulf Cement | Vignesh | 50% after completion. | Completed | 2024-11-26 | 2025-01-16 | 2025-01-29 | [12 empty] | 95%
243 |  | SOC | MBRSG | Vignesh | 1st Quarterly to be invoiced on 31st December 2024 | completed | 2024-09-30 | 2024-12-31 | 2024-12-31 | [12 empty] | 95%
244 |  | SOC | MBRSG | Vignesh | 2nd Quarterly to be invoiced on 31st March 2025 | Completed | 2025-01-01 | 2025-03-31 | 2025-04-01 | [12 empty] | 0%
245 |  | SOC | MBRSG | Vignesh | 3rd Quarterly to be invoiced on 30th June 2025 | Not Started | 2025-04-01 | 2025-06-30 | [13 empty] | 0%
246 |  | SOC | MBRSG | Vignesh | 4th Quarterly to be invoiced on 30th September 2025 | Not Started | 2025-07-01 | 2025-09-30 | [13 empty] | 0%
248 |  | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | UAT Environment Sign Off for Upgrade (8.1-->8.3p3) = 20% | Not Started | [15 empty] | project on-hold
249 |  | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | PROD & DR Environments Sign Off for Upgrade (8.1-- >8.3p3) = 20% | Not Started | [15 empty] | project on-hold
250 |  | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | Sprint 1: UAT Sign-Off for Sprint 1 applications (4 applications) =15 % | Not Started
251 |  | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | Sprint 2: UAT Sign-Off for Sprint 2 applications (3 applications) =15 % | Not Started
252 |  | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | Sign-Off for RBAC (5 applications) = 15% | Not Started
253 |  | SailPoint | ADCB - Phase 2 - IIQ | Laxmi | Sign-Off for RBAC(4 applications) Final Go-live, Documentation and Handover = 15% | Not Started
254 | RN - 501 | ISO | ICO | Ajinkya | a. 50% to be invoiced upon signing the contract | Not Started
255 | RN - 501 | ISO | ICO | Ajinkya | b. 25% on completion of Documentation phase | Not Started
256 | RN - 501 | ISO | ICO | Ajinkya | c. 15% on completion of Internal Audit and Management Review | Not Started
257 | RN - 501 | ISO | ICO | Ajinkya | d. Balance 10% upon successful completion of Certification. | Not Started
258 | RN - 501 | ISO | ICO | Ajinkya | e. Late Payment: Invoice paid after 30 days 10% penalty will be applied. | Not Started
259 | RN-476 | Checkmarx | MOFA - Checkmarx - Invicti | Divya | 100% upon license delivery | Completed | 2024-09-01 | 2024-11-27 | 2024-11-27
262 | RN-487 | Carbon black | Protect - Application Control vendor | Ajinkya | 100% advance | Completed | 2025-02-03 | 2025-01-31 | 2025-01-31
264 | RN-508 | Forcepoint | UBL Forcepoint Hardware refresh | Ajinkya | a. Services: To be invoiced upon Sign-Off | On track | 2025-02-25 | TBD
266 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2025-01-01 | 2025-01-31 | 2025-02-10
267 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2025-02-01 | 2025-02-28 | 2025-03-18
268 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | On Track | 2025-03-01 | 2025-03-31
269 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-04-01 | 2025-04-30
270 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-05-01 | 2025-05-31
271 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-06-01 | 2025-06-30
272 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-07-01 | 2025-07-31
273 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-08-01 | 2025-08-31
274 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-09-01 | 2025-09-30
275 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-10-01 | 2025-10-31
276 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-11-01 | 2025-11-30
277 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Not Started | 2025-12-01 | 2025-12-31
278 | RN-525 | VAPT | Nextcare VAPT (SOC Renewal) 2025 | Sean Faizal | 100% Advance Payment | Completed | 2025-01-01 | 2025-01-01 | 2025-01-01
279 | RN-468 | Checkmarx | SIB Checkmarx (sourcecode review solution) | Sean Faizal | To be Invoiced 100 %upon delivery of Licenses | Completed | 2025-02-22 |  | 2025-02-12
280 | RN-452 | Forcepoint | Kerzner International - Forcepoint One | Sean Faizal | 100% of Licenses Cost to be paid on license delivery | Completed | 2024-02-28 | 2024-02-28 | 2025-02-28
280 | RN-452 | Forcepoint | Kerzner International - Forcepoint One | Sean Faizal | 100% of PS to be paid along with the LPO | Completed | 2024-02-28 | 2024-02-28 | 2025-02-28
280 | RN-452 | Forcepoint | Kerzner International - Forcepoint One | Sean Faizal | 100% of AMC cost to be paid on 01st Feb 2025 | Completed | 2024-02-28 | 2024-02-28 | 2025-02-28
281 | RN-516 | Forcepoint | Fly Dubai - Forcepoint DLP & DSPM | Vignesh | 50% to be invoiced upon Project Kickoff | On Track | 2025-02-07 | 2025-04-11
282 | RN-516 | Forcepoint | Fly Dubai - Forcepoint DLP & DSPM | Vignesh | 30% to be invoiced upon DSPM implementation C configuration completion | On Track | 2025-02-11 | 2025-04-23
283 | RN-516 | Forcepoint | Fly Dubai - Forcepoint DLP & DSPM | Vignesh | 20% to be invoiced upon DLP implementation C configuration completion | Not Started
284 | RN-516 | Forcepoint | Fly Dubai - Forcepoint DLP & DSPM | Vignesh | AMC: To be invoiced upon Project Sign-off | Not Started
285 | RN - 523 | VAPT | Al Buhaira - VAPT | Ajinkya | 1. External Initial Assessment with Reporting = 40% | In Progress | 2025-03-20 | 2025-04-20
286 | RN-523 | VAPT | Al Buhaira - VAPT | Ajinkya | 2. Internal Initial Assessment with Reporting = 40% | Not Started
287 | RN-523 | VAPT | Al Buhaira - VAPT | Ajinkya | 3. Retesting & Signoff = 20% | Not Started
288 | RN-265 | VAPT | Al Fardan VAPT | Sean Faizal | 90% on completion of external initial assessment | On Track | 2025-02-27 | 2025-03-26
289 | RN-265 | VAPT | Al Fardan VAPT | Sean Faizal | 10% upon completion of retesting | On Track | 2025-04-15 | 2025-04-30
290 | RN-526 | ISO | Transmed - ISO | Ajinkya | 100% on submitting the Gap Analysis Report | On Track | 2025-03-17 | TBD
291 | RN - 515 | Sailpoint | Airtel Phase 3 | Laxmi | Milestone 1: Workshop and Design for 20 Applications (SailPoint) & 20 Applications (ForgeRock) with HLD Submission = 10% | On Track
292 | RN - 515 | Sailpoint | Airtel Phase 3 | Laxmi | Milestone 2: Workshop and Design for 1 Application (FAM), 10 Applications (SailPoint) & 10 Applications (ForgeRock) with HLD Submission = 10% | On Track
293 | RN - 515 | Sailpoint | Airtel Phase 3 | Laxmi | Milestone 3: RBAC (SailPoint) 20 Applications Integration with UAT for target application + SOD (SailPoint) 20 Applications Finalization & Implementation = 20% | Not Started
294 | RN - 515 | Sailpoint | Airtel Phase 3 | Laxmi | Milestone 4: Sprint 1-15 SailPoint Applications Integration and UAT for initial target applications + 15 Forge Rock Applications Integration and UAT for initial target applications = 30% | Not Started
295 | RN - 515 | Sailpoint | Airtel Phase 3 | Laxmi | Milestone 5: Sprint 215 SailPoint Applications Integration and UAT for target applications + 15 ForgeRock Applications Integration and UAT for target applications + 1 FAM Application Integration in 2 environment 13 instances = 30% | Not Started
296 |  | Sailpoint | Airtel Phase 3 - Suppport | Laxmi | Q1 Managed Support | Completed
297 |  | Sailpoint | Airtel Phase 3 - Suppport | Laxmi | Q2 Managed Support | On Track
298 |  | Sailpoint | Airtel Phase 3 - Suppport | Laxmi | Q3 Managed Support | Not Started
299 |  | Sailpoint | Airtel Phase 3 - Suppport | Laxmi | Q4 Managed Support | Not Started
300 | RN-534 | Checkpoint | Cadvil Solutions | Vignesh | 100% to be invoiced upon support renewal completion | completed | 2025-03-17 | 2025-03-17 | 2025-03-17
301 | RN-534 | Checkpoint | Cadvil Solutions | Vignesh | To be invoiced upon Milestone completion | On Track | 2025-03-27 | 2025-04-11
Note on F293: Bhushan Sisode This Support is valid till 3 years

## Managed Services
PROJECT MANAGEMENT LOG TEMPLATE
PROJECT REGISTER
The PROJECT Identification portion of this table will automatically populate to the Financial Data, Deliverables and Performance, and Risk Register tabs within this workbook.
PROJECT DATA |  |  |  |  | CUSTOMER DATA |  |  |  | ACCOUNT DATA |  | TERMS
Sr no | RN ID | Tower | Project |  |  | Client Name | Client SPOC | SPOC email | Account manager |  | Start Date | End Date |  |  |  | Status
1 | RN-208 & 209 | IntelliShield | MBRSG-SOC & Forcepoint |  |  | MBRSG | Anthony Bartolo | anthony.bartolo@mbrsg.ac.ae | Rohit Suresh Save | Ameya | 2024-01-01 | 2024-03-31 | Yr 3 | last wkg day of 2nd month in each Qtr | 2024-02-01 | Complete
2 | RN-208 & 209 | IntelliShield | MBRSG-SOC & Forcepoint |  |  | MBRSG | Anthony Bartolo | anthony.bartolo@mbrsg.ac.ae | Rohit Suresh Save |  | 2024-04-01 | 2024-06-30 | Yr 3 |  | 2024-04-01 | Complete | 2024-04-30
3 | RN-208 & 209 | IntelliShield | MBRSG-SOC & Forcepoint |  |  | MBRSG | Anthony Bartolo | anthony.bartolo@mbrsg.ac.ae | Rohit Suresh Save |  | 2024-07-01 | 2024-08-31 | Yr 3 |  | 2024-07-01
4 | RN-111 | VAPT, IntelliShield | NEXTCARE-SOC |  |  | Nextcare | Zaher Ali | Zaher.ElAli@nextcarehealth.com | Haythem | Ameya | 2023-01-01 | 2024-12-01 | 4yrs | Y3-Q1 (Jan to March 23) |  | Complete |  | Paid
5 | RN-111 | VAPT, IntelliShield | NEXTCARE-SOC |  |  | Nextcare | Zaher Ali | Zaher.ElAli@nextcarehealth.com | Haythem |  |  |  | 4yrs | Y3-Q2(April to June 23) |  | Complete |  | Paid
6 | RN-111 | VAPT, IntelliShield | NEXTCARE-SOC |  |  | Nextcare | Zaher Ali | Zaher.ElAli@nextcarehealth.com | Haythem |  |  |  | 4yrs | Y3-Q3(July to Sep 23) | 2023-07-01 | Complete | 2023-07-03 | Paid | 2023-08-02
| RN-111 | VAPT, IntelliShield | NEXTCARE-SOC |  |  | Nextcare | Zaher Ali | Zaher.ElAli@nextcarehealth.com | Haythem |  |  |  | 4yrs | Y3-Q4( Oct to Dec 23) | 2023-10-01 | Complete
| RN-111 | VAPT, IntelliShield | NEXTCARE-SOC |  |  | Nextcare | Zaher Ali | Zaher.ElAli@nextcarehealth.com | Haythem |  |  |  | 4yrs | Y4-Q1 (Jan to March 24) | 2024-01-01 | Complete
| RN-111 | VAPT, IntelliShield | NEXTCARE-SOC |  |  | Nextcare | Zaher Ali | Zaher.ElAli@nextcarehealth.com | Haythem |  |  |  | 4yrs | Y4-Q2(April to June 24) | 2024-04-01 | Complete | 2024-04-01
| RN-111 | VAPT, IntelliShield | NEXTCARE-SOC |  |  | Nextcare | Zaher Ali | Zaher.ElAli@nextcarehealth.com | Haythem |  |  |  | 4yrs | Y4-Q3(July to Sep 24) | 2024-07-01 | Complete
| RN-111 | VAPT, IntelliShield | NEXTCARE-SOC |  |  | Nextcare | Zaher Ali | Zaher.ElAli@nextcarehealth.com | Haythem |  |  | 2024-12-01 | 4yrs | Y4-Q4( Oct to Dec 24) | 2024-10-01
3 | New | Vendor MS | DWTC - Cybereason |  |  | DWTC |  |  | Ishan | Pallavi Nair | 2024-02-01 | 2025-01-31 | 1 Yr |  | 2024-02-01 | Complete
4 | New | Vendor MS | DAMAC - Rapid 7 MDR |  |  | DAMAC | Rajesh Narayanan | Rajesh.Narayanan@damacgroup.com | Bibinu | Pallavi Nair | 2023-12-20 | 2024-12-19 | 1 Yr |  | 2023-12-01 | Complete
5 | RN-316 | SailPoint & Forgerock | Airtel Support (24/7) for Sailpoint and ForgeRock | 2023-08-04 |  | Airtel Africa | Ashok Muthu | ashok1.muthu@africa.airtel.com | Sagar Chopra | Sandeep | 2023-08-01 | 2024-07-01 |  | Q1 (Aug to Oct 23) | 2023-08-01 | Complete | 2023-08-02 | partially paid - 94K is pending | 2023-09-30
| RN-316 | SailPoint & Forgerock | Airtel Support (24/7) for Sailpoint and ForgeRock |  |  | Airtel Africa | Ashok Muthu | ashok1.muthu@africa.airtel.com | Sagar Chopra |  |  |  |  | Q2 (Nov 23 to Jan 24) | 2023-11-01 | Complete |  | partially paid - 13K is pending
| RN-316 | SailPoint & Forgerock | Airtel Support (24/7) for Sailpoint and ForgeRock |  |  | Airtel Africa | Ashok Muthu | ashok1.muthu@africa.airtel.com | Sagar Chopra |  |  |  |  | Q3 (Feb 24 to Apr 24) | 2024-02-01 | Complete |  | Not Received
| RN-316 | SailPoint & Forgerock | Airtel Support (24/7) for Sailpoint and ForgeRock |  |  | Airtel Africa | Ashok Muthu | ashok1.muthu@africa.airtel.com | Sagar Chopra |  |  | 2024-07-01 |  | Q4 (May 24 to July 24) | 2024-05-01 | Complete
6 | RN-320 | IT Incidents | Nextcare_Managed_APM_&_IT_Incidents |  |  | Nextcare | Tom Badger | Tom.Badger@nextcarehealth.com |  | Sean / Ameya |  |  |  | Q1 (Apr to Jun 24) | 2024-05-01 | Complete
| RN-320 | IT Incidents | Nextcare_Managed_APM_&_IT_Incidents |  |  | Nextcare | Tom Badger | Tom.Badger@nextcarehealth.com |  | Sean |  |  |  | Q2 (Jul 24 to Sep 24) | 2024-08-01 | Not started
| RN-320 | IT Incidents | Nextcare_Managed_APM_&_IT_Incidents |  |  | Nextcare | Tom Badger | Tom.Badger@nextcarehealth.com |  | Sean |  |  |  | Q3 (Oct 24 to Dec 24) | 2024-11-01 | Not started
| RN-320 | IT Incidents | Nextcare_Managed_APM_&_IT_Incidents |  |  | Nextcare | Tom Badger | Tom.Badger@nextcarehealth.com |  | Sean |  |  |  | Q4 (Jan 25 to Mar 25) | 2025-02-01 | Not started
7 | RN-377 | IntelliShield | Western International Group - Nesto_SOC | 2023-10-31 |  | WIG - Nesto | Raveesh P |  |  | Ameya | 2024-03-13 |  | Q1 | Quarterly Advance for the SOC services | 2024-03-01 | Complete | 2024-03-13
| RN-377 | IntelliShield | Western International Group - Nesto_SOC (6 Months) | 2023-10-31 |  | WIG - Nesto | Raveesh P |  |  | Ameya |  | 2024-08-25 | Q2 | Quarterly Advance for the SOC services | 2024-06-01
|  |  | Nextcare SOC Renewal | 2025-01-01 | 2025-12-31

## Closed Milestones
NO. | PROJECT ID | Project Type | PROJECT DATA | PROJECT MANAGER | MILESTONE DESCRIPTION | Milestone Status | PLANNED START DATE | PLANNED/Estimated END DATE | Actual End Date | PO Details | PO Amount | Billing Forecast Month | Biling Status | Invoice Date | Payment Satus | Forecast Revenue | Paid Date | OPEN TASKS | CLOSED TASKS | OPEN ISSUES | CLOSED ISSUES | % Completion
51 | RN-185 | Sailpoint | Intigral - Sailpoint | Vignesh | M1 - 100% upon Licence delivery | Completed |  |  | 2022-11-15 |  |  | COMPLETE | COMPLETE |  | Paid |  | 2023-08-10
52 | RN-185 | Sailpoint | Intigral - Sailpoint | Vignesh | M2 - 20% upon finailazing of phase 2 - HLD Sign-off | Completed | 2022-12-05 |  | 2023-08-01 |  |  | 2023-08-01 | COMPLETE | 2023-08-01
53 | RN-185 | Sailpoint | Intigral - Sailpoint | Vignesh | M3 - 30% upon the finalization of phase 3 & 4 Sprint 1 Sign-off. | Completed | 2023-01-05 |  | 2023-08-01 |  |  | 2023-08-01 | COMPLETE | 2023-08-01
54 | RN-185 | Sailpoint | Intigral - Sailpoint | Vignesh | M4 - 30% upon finailazing of phase 5 | Completed | 2023-01-06 |  | 2023-12-11 |  |  | 2023-12-01 | COMPLETE | 2023-12-11
55 | RN-185 | Sailpoint | Intigral - Sailpoint | Vignesh | M5 - 20% upon finailazing of phase 6 | Completed | 2023-04-13 |  | 2023-12-11 |  |  | 2023-12-11 | Complete | 2023-12-11
85 | RN-229 | Ivanti | MBRSG | Vignesh | M1 - License 100% upon completion | Completed | 2023-01-31 |  | 2023-01-31 |  |  | COMPLETE |  |  | Paid |  |  | 0 | 1 |  |  | 100% | Completed, no action needed
86 | RN-229 | Ivanti | MBRSG | Vignesh | M2 - Implementation - 100% upon completion | Completed | 2023-02-01 |  | 2023-05-01 |  |  | COMPLETE |  |  | Paid |  |  | 0 | 18 |  |  | 100% | Completed, no action needed
87 | RN-231 | VAPT | DWTC VAPT 2022 | Vignesh | M1 - 30% to be invoiced upon Project Kickoff Meeting. | Completed | 2022-12-26 |  | 2022-12-26 |  |  | COMPLETE |  |  | Paid | [7 empty] | Completed, no action needed
88 | RN-231 | VAPT | DWTC VAPT 2022 | Vignesh | M2 - 50% to be Invoiced on External Assessment & Report Submission | Completed | 2022-12-27 |  | 30-May-24 |  |  | 2024-05-15 | [10 empty] | one task is pending post we which we can ask for sign off
89 | RN-231 | VAPT | DWTC VAPT 2022 | Vignesh | M3 -20% to be invoiced upon Sign-off | Completed | 2023-05-16 |  | 30-May-24 |  |  | 2024-05-15 | [10 empty] | configuration and retesting is pending
90 | RN-235 | Cybereason | Amlak Finance-Cybereason(Vendor) | Vignesh | M1-100% upon license delivery | Completed | 2023-02-17 |  | 2023-02-17 |  |  | COMPLETE |  |  | Paid |  |  | 0 | 1 |  |  | 100%
91 | RN-235 | Cybereason | Amlak Finance-Cybereason(Vendor) | Vignesh | M2-50% start of implementation | Completed | 2023-03-01 |  | 2023-05-26 |  |  | COMPLETE |  |  | Paid |  |  | 0 | 7 |  |  | 100%
92 | RN-235 | Cybereason | Amlak Finance-Cybereason(Vendor) | Vignesh | M3- 50% upon project sign off/ Implementation | Completed | 2023-05-01 |  | 2023-09-28 |  |  | 2023-10-01 | Complete |  |  |  |  | 0 | 7 |  |  | 100% | waiting for Sign-off, so that billling can be done for M3 milestone
101 | RN-239 | Sailpoint | Aldar Phase 1 | Vignesh | M1 - License Delivery | Completed | 2023-12-23 |  | 2023-01-20 |  |  | COMPLETE |  |  | Paid |  |  | 0 | 1 |  |  | 100% | Completed, no action needed
102 | RN-239 | Sailpoint | Aldar Phase 1 | Vignesh | M2 - 10% upon services kickoff | Completed | 2023-01-20 |  | 2023-06-18 |  |  | COMPLETE |  | 2023-06-18 | Paid | 2023-07-17 | 2023-07-19 | 0 | 1 |  |  | 100% | Completed, no action needed
103 | RN-239 | Sailpoint | Aldar Phase 1 | Vignesh | M3 - 10% upon design signoff, workshops, requirement gathering, HLD signoff | Completed | 2023-02-03 |  | 2023-06-08 |  |  | COMPLETE |  | 2023-06-14 | Paid | 2023-07-13 | 2023-07-19 | 0 | 16 |  |  | 100% | Completed, no action needed
104 | RN-239 | Sailpoint | Aldar Phase 1 | Vignesh | M4 - 20% base setup and IAM foundation setup | Completed | 2023-02-17 |  | 2023-06-14 |  |  | COMPLETE |  | 2023-06-15 | Paid | 2023-07-14 | 2023-07-19 | 0 | 6 |  |  | 100% | Completed, no action needed
105 | RN-239 | Sailpoint | Aldar Phase 1 | Vignesh | M5 - 20% upon Release 1(3 apps) - UAT and Go-Live | Completed | 2023-03-17 |  | 2024-01-15 |  |  | 2023-09-01 | COMPLETE | 2023-09-07 |  | 2023-10-06 |  | 40 | 81 |  |  | 60%
106 | RN-239 | Sailpoint | Aldar Phase 1 | Vignesh | M6 - 20% upon Release 2(3 apps) - UAT and Go-Live | Completed | 2023-05-01 |  | 2024-01-15 |  |  | 2024-01-01 | COMPLETE | 2024-01-15 |  |  |  | 40 | 81 |  |  | 36%
107 | RN-239 | Sailpoint | Aldar Phase 1 | Vignesh | M7 - 20% upon Release 3(2 apps) - UAT and Go-Live | Completed |  |  | 2024-01-15 |  |  | 2023-09-01 | COMPLETE | 2023-09-07 |  | 2023-10-06 |  | 40 | 81 |  | Out of Scope | 100%
109 | RN-239 | SailPoint | Aldar - CR Sailpont | Vignesh | 50% upon commencement of services | Completed |  |  | 2023-08-09 |  |  | 2023-08-01 | COMPLETE | 2023-08-11 |  | 2023-09-10
110 | RN-239 | SailPoint | Aldar - CR Sailpont | Vignesh | 25% upon completion of JML for manage engine | Completed |  |  | 2023-08-09 |  |  | 2023-08-01 | COMPLETE | 2023-08-11 |  | 2023-09-10
111 | RN-239 | SailPoint | Aldar - CR Sailpont | Vignesh | 25% upon completion of JML for manage engine | Completed |  |  | 2023-10-24 |  |  | 2023-10-01 | COMPLETE | 2023-10-24
112 | RN-240 | Sailpoint | MAF Carrefour-Sailpoint | Vignesh | License-M1 - License Delivery, Professional Service- | Completed | 2022-12-11 |  | 2023-03-01 |  |  | COMPLETE |  | 2023-03-01 | Paid | 2023-03-30 | Paid |  |  |  |  | 100%
113 | RN-240 | Sailpoint | MAF Carrefour-Sailpoint | Vignesh | M2- 100% upon completion of 8.2 upgrade M3- 100% upon completion of role matrix migration M4 100% upon completion PAM intigration | Completed | 2023-06-12 |  | 2023-03-01 |  |  | COMPLETE |  | 2023-03-01 | Paid | 2023-03-30 | Paid | 17 | 2 |  |  | 10%
114 | RN-242 | Mimecast | LM Exchange-User awareness(Vendor) | Vignesh | 30 Days upon completion | Completed | 2022-11-28 |  | 2023-06-26 |  |  | COMPLETE |  |  | Paid |  |  | 0 | 16 |  |  | 100% | paid
115 | RN-242 | training | LM Exchange-User awareness(Vendor) | Vignesh | User Awareness Training | Completed |  |  | 2024-05-15 |  |  | 2024-03-01 | COMPLETE | 22 Mar 24 | [7 empty] | Order is in cancellation
116 | RN-247 | Digital Forencis | Mohebi Logistics | Vignesh | M1 - Project signoff | Completed | 2023-03-29 |  | 2023-08-03 |  |  | COMPLETE |  |  | Paid |  |  | 0 | 1 |  |  | 100% | Completed, no action needed
117 | RN-248 | VAPT | Future Focus Infotech - VAPT | Vignesh | M1- 50% on PO & initiation | Completed | 2023-03-20 |  | 2023-05-22 |  |  | COMPLETE |  | 2023-03-11 | Partially Paid | 2023-04-10 |  | 2 | 4 | Cloud Security Assessment and SE Assessments pending |  | 100% | Completed, no action needed
118 | RN-248 | VAPT | Future Focus Infotech - VAPT | Vignesh | M2- 30% on Report Submission+ Iteration | Completed | 2023-04-24 |  | 2023-10-10 |  |  | 2023-10-01 | Complete | 2023-10-21 |  |  |  | 2 | 7 |  |  | 54% | Get the Sec document shared and get the re-testing done by mid July to get the sign-off (complete both CS assessment and social engg)
119 | RN-248 | VAPT | Future Focus Infotech - VAPT | Vignesh | M3- 20% on Project Sign off | Completed | 2023-07-19 |  | 2023-10-10 |  |  | 2023-10-01 | Complete | 2023-10-21 |  |  |  | 1 | 0 |  |  | 0% | Customer not confirming the re-testing
120 | RN-249 | VAPT | Info Arab Media | Vignesh | M1 - External Assessment & Report Submission: 80% | Completed | 2023-04-04 |  | 2023-09-05 |  |  | 2023-09-01 | COMPLETE | 2023-09-11 |  |  |  | 4 | 0 | Contractual Issue |  | 0% | Vignesh to work with Faizan and get the contractual issue fixed
121 | RN-249 | VAPT | Info Arab Media | Vignesh | M2 - Retesting & Sign off: 20% | Completed | 2023-06-22 |  | 2023-10-23 |  |  | 2023-10-01 | COMPLETE | 2023-10-23 |  |  |  | 3 | 0 | Contractual Issue |  | 0% | Vignesh to work with Faizan and get the contractual issue fixed
143 | RN-270 | Cyclops | LM Exchange-Cyclops (Vendor) | Vignesh | 30 Days upon completion | Completed | 2023-04-25 |  | 2023-05-08 |  |  | 2023-05-01 | COMPLETE | 2023-05-08 | paid | 2023-06-07 |  | 0 | 2 |  |  | 100% paid
159 | RN-277 | Force Point, DLP | Emrill - Forcepoint DLP | Vignesh | M1 - 100% payment after delivery of license | Completed | 2023-02-01 |  | 2023-01-31 |  |  | COMPLETE |  | 2023-01-31 | Partially Paid |  |  | 0 | 0 |  |  | 100% | Completed, no action needed - (103k is to be paid)
160 | RN-277 | Force Point, DLP | Emrill - Forcepoint DLP | Vignesh | M2 - 50% payment of PS upon delivery | Completed | 2023-04-18 |  | 2024-07-01 |  |  | 2024-05-10 | [5 empty] | 19 | 9 |  |  | 51% | Complete the left over work and get the sign-off by mid July
161 | RN-277 | Force Point, DLP | Emrill - Forcepoint DLP | Vignesh | M3 - 50% payment of PS upon delivery | Completed | 2023-04-18 |  | 2024-07-01 |  |  | 2024-05-10 | [5 empty] | 19 | 9 |  |  | 51%
163 | RN-282 | Fortigate | Dubai Sports Council-Fortigate | Vignesh | 60 days after receiving completion | Completed | 2023-05-22 |  | 2023-05-01 |  |  | 2023-06-01 | COMPLETE | 2023-05-01 | Not Received | 2023-08-15 |  | 26 | 1 |  |  | 20%
166 | RN-284 | VAPT | Petronash | Vignesh | M1 - 80% on Initial Assessment & Report Submission | Completed | 2023-05-16 |  | 2023-07-19 |  |  | COMPLETE |  | 2023-07-19 |  | 2023-08-18 |  | 0 | 6 |  |  | 100%
167 | RN-284 | VAPT | Petronash | Vignesh | M2 -20% on Retesting & Signoff | Completed | 2023-07-10 |  | 2023-10-26 |  |  | 2023-10-01 | COMPLETE | 2023-10-26 |  |  |  | 4 | 0 |  |  | 0% | Vignesh to check with customer for the re-testing plan
175 | RN-286 | VAPT | NAFFCO | Vignesh | M1 -50% on External Initial Assessment & Report Submission | Completed | 2023-04-27 |  | 2023-11-22 |  |  | 2023-11-01 | COMPLETE | 2023-11-23 |  |  |  | 13 | 5 |  |  | 23% | Vignesh to work with Abhinav and get the right dates
176 | RN-286 | VAPT | NAFFCO | Vignesh | M2 - 40% on Internal Initial Assessment & Report Submission | Completed | 2023-07-11 |  | 2023-11-22 |  |  | 2023-11-01 | COMPLETE | 2023-11-23 |  |  |  | 4 | 0 |  |  | 0% | Vignesh to work with Abhinav and get the right dates
177 | RN-286 | VAPT | NAFFCO | Vignesh | M3 -10% on Retesting & Signoff | Completed | 2023-08-18 |  | 2024-05-20 |  |  |  |  | 2024-05-20 |  |  |  | 7 | 0 |  |  | 0% | Vignesh to work with Abhinav and get the right dates
180 | RN-291 | SDLC | Saal-SDLC (Consultation Services for Implementation of SDLC) | Vignesh | 50% on completion of Documentation phase | Completed |  |  | 2023-10-20 | SAAL-000813-1 | 23153 | 2023-10-01 | COMPLETE | 2023-10-20
182 | RN-292 | VAPT | SKM | Vignesh | M1 - 40% External Assessment with Reporting | Completed | 2023-06-01 |  | 2024-03-29 |  |  | 2024-03-29 | COMPLETE | 2024-03-29 |  |  |  | 6 | 2 |  |  | 1% | Vignesh to share the planned dates for M1, M2 and M3
183 | RN-292 | VAPT | SKM | Vignesh | M2 - 50% Internal Assessment with Reporting | Completed | 2023-06-12 |  | 2024-03-29 |  |  | 2024-03-29 | COMPLETE | 2024-03-29 |  |  |  | 4 | 0 |  |  | 0% | Vignesh to share the planned dates for M1, M2 and M3
184 | RN-292 | VAPT | SKM | Vignesh | M3 - 10% Retesting & Signoff | Completed | 2023-07-03 |  | 2024-05-29 | [8 empty] | 4 | 0 |  |  | 0% | Vignesh to share the planned dates for M1, M2 and M3
185 | RN-293 | Checkmarx | Airtel Africa | Vignesh | M1 - license delivery | Completed | 2023-04-14 |  | 2023-05-04 |  |  | COMPLETE | COMPLETE | 2023-05-04 | Not Received | 2023-06-03 |  | 0 | 1 |  |  | 100% | Completed, no action needed
186 | RN-296 | VAPT | Gulf Cryo - VAPT | Vignesh | M1 - .50% to be invoiced upon completion of External Initial Assessments with reporting | Completed |  |  | 2023-11-01 | 2313200063 | 28014 | 2023-11-01 | COMPLETE | 2023-11-01
187 | RN-296 | VAPT | Gulf Cryo - VAPT | Vignesh | M2 - 40% to be invoiced upon completion of Internal Initial Assessments with reporting | Completed |  |  | 2023-11-01 | 2313200063 | 22411 | 2023-11-01 | COMPLETE | 2023-11-01
188 | RN-296 | VAPT | Gulf Cryo - VAPT | Vignesh | M3 - 10% to be invoiced upon completion of Retesting & Signoff | Completed |  |  | 2024-01-06 | 2313200063 | 5602.8 | 2023-11-01 | COMPLETE | 2023-11-21 | [8 empty] | CS TO GET THE PAYMENT MILESTONE INFORMATION
221 | RN-314 | VAPT | Damas Jewellery LLC - API Testing | Vignesh | 100% payment | Completed |  |  | 2023-08-03 |  |  | 2023-08-01 | COMPLETE | 2023-08-03 | Paid | 2023-09-02
236 | RN-330 | ISO BCP & RA | ECAE- Audit | Vignesh | IT Function Risk Assessment & 3-year Internal Audit Plan: balance 70% on completion of the project. | Completed |  |  | 2023-12-09 |  |  | 2023-12-01 | COMPLETE | 2023-12-09
239 | RN-37 | VAPT | Fujairah National Group | Vignesh | M1 - Upon Project Signoff | Completed | 2021-08-16 |  | 2024-04-16 |  |  | COMPLETE |  |  | Paid | [6 empty] | 90%
269 | Closed | Email Security | Al Dhafra Insurance CoDark Trace Email Security PSC | Vignesh | Only License Delivery | Completed |  |  | 2023-08-21 |  |  | 2023-08-01 | COMPLETE | 2023-08-21
273 | RN-342 | Vendor Akamai | MAF Bot Manager | Vignesh | PS amount | Completed |  |  | 2024-02-06 |  |  | 2024-02-01 | COMPLETE | 2024-02-06
305 | RN-353 | ForcePoint, FP | Emirates Steel - Forcepoint Proxy - Licenses; Professional Services | Vignesh | 100% upon license delivery | Completed |  |  | 2023-09-01 |  |  | 2023-09-01 | COMPLETE
325 | RN-239 | SailPoint | Aldar Sailpoint_CR_HCM_Oct_2023 | Vignesh | 50% upon commencement of services, | Completed |  |  | 2023-10-24 |  |  | 2023-10-01 | COMPLETE | 2023-10-24
326 | RN-239 | SailPoint | Aldar Sailpoint_CR_HCM_Oct_2023 | Vignesh | 25% upon completion of JML for manage engine | Completed |  |  | 2023-10-24 |  |  | 2023-10-01 | COMPLETE | 2023-10-24
327 | RN-239 | SailPoint | Aldar Sailpoint_CR_HCM_Oct_2023 | Vignesh | 25% on sign off Manage engine integration scope | Completed |  |  | 2023-10-24 |  |  | 2023-10-01 | COMPLETE | 2023-10-24
333 | RN-343 | Logrhythm | ADJD LogRhythm Licenses Renewal & appliance & PS | Vignesh | 100% To be Invoiced upon delivery of Licenses & appliance | Completed |  |  | 2023-10-01 |  |  | 2023-10-01 | Complete
334 | RN-343 | FireEye | ADJD FireEye WEB MPS Licenses & Appliance | Vignesh | 100% To be Invoiced upon delivery of Licenses & appliance | Completed |  |  | 2024-03-15 |  |  | 2023-10-01 | Complete
335 | RN-343 | McAfee | ADJD McAfee Licenses | Vignesh | 100% To be Invoiced upon delivery of Licenses & appliance | Completed |  |  | 2023-10-01 |  |  | 2023-10-01 | Complete
336 | RN-343 | Tenable | ADJD Tenable Licenses | Vignesh | 100% To be Invoiced upon delivery of Licenses & appliance | Completed |  |  | 2023-10-01 |  |  | 2023-10-01 | Complete
337 | RN-343 | CyberArk | ADJD CyberArc Licenses | Vignesh | 100% To be Invoiced upon delivery of Licenses & appliance | Completed |  |  | 2023-10-01 |  |  | 2023-10-01 | Complete
338 | RN-343 | Forcepont | ADJD Forcepoint Licenses | Vignesh | 100% To be Invoiced upon delivery of Licenses & appliance | Completed |  |  | 2023-10-01 |  |  | 2023-10-01 | Complete
353 | VENDOR | Akamai | Americana Akamai AAP | Vignesh | PS Cost | Completed |  |  | 2024-03-24 |  |  | 2024-05-01
355 | RN-239 | SailPoint | Aldar_Sailpoint_PS_CR_Nov_2023 | Vignesh | Configuration of 4 required Enhancements (as per SOW) = 50% | Completed |  |  | 2023-01-17 |  |  | 2024-01-01 | COMPLETE
356 | RN-239 | SailPoint | Aldar_Sailpoint_PS_CR_Nov_2023 | Vignesh | Configurations of the remaining Enhancements (as per SOW) = 50% | Completed |  |  | 2023-01-17 |  |  | 2024-01-01 | COMPLETE
371 | RN-380 | ISO Consulting | OQ Trading_iso27K_aasmt_Q42023 | Vignesh | M1 - 50% to be invoiced upon signing the contract. | Completed |  |  | 2024-03-01 |  |  | 2024-03-01 | COMPLETE | 2024-03-07
372 | RN-380 | ISO Consulting | OQ Trading_iso27K_aasmt_Q42023 | Vignesh | M2 - 25% on completion of Documentation phase | Completed |  |  | 2024-03-01 |  |  | 2024-03-01 | COMPLETE | 2024-03-07
373 | RN-380 | ISO Consulting | OQ Trading_iso27K_aasmt_Q42023 | Vignesh | M3- 15% on completion of Internal Audit and Management Review | Completed |  |  | 2024-03-01 |  |  | 2024-03-01 | COMPLETE | 2024-03-07
374 | RN-380 | ISO Consulting | OQ Trading_iso27K_aasmt_Q42023 | Vignesh | M4- Balance 10% upon successful completion of Certification | Completed |  |  | 2024-03-01 |  |  | 2024-03-01 | COMPLETE | 2024-03-07
395 | RN-405 | Palo-Alto | Intigral - Palo Alto PS Only | Vignesh | To be invoiced upon delivery of Hardware and Licenses | Completed |  |  | 2024-02-19 |  |  | 2024-02-19 | Complete | 2024-02-19
402 | RN-405 | Palo-Alto | INTIGRAL_PaloAlto_Renewal_PS/AMC_Jan_2024 | Vignesh | To be invoiced upon delivery of Hardware and Licenses | Completed |  |  | 2024-01-24 |  |  | 2024-01-24 | Complete | 2024-01-24
420 | RN-411 | Barracuda Email Security | Providence - Barracuda Email Security | Vignesh | 100% along with LPO | Completed |  |  | 2024-03-08 |  |  | 2024-02-01 | Complete | 2024-02-22
439 | VENDOR | Akamai | Sedar Global_Akamai WAF | Vignesh | One time implementation - 50% advance | Completed |  |  | 2024-02-01 |  |  | COMPLETE | COMPLETE
440 | VENDOR | Akamai | Sedar Global_Akamai WAF | Vignesh | One time implementation - 50% upon completion | Completed |  |  | 2024-03-01 |  |  | 2024-03-01 | COMPLETE | 2024-03-01
442 | RN-416 | VAPT | DAMAS 4 APIs VAPT | Vignesh | 50% advance | Completed |  |  | 2024-03-28 |  |  | 2024-03-29 | COMPLETE | 2024-03-28
443 | RN-416 | VAPT | DAMAS 4 APIs VAPT | Vignesh | 50% upon sign off | Completed |  |  | 2024-04-24 |  |  | 2024-03-29 | COMPLETE | 2024-03-28
512 | NO PS | Crowdstrike | Gulf Cryo Crowdstrike | Vignesh | 100% of license to be Invoiced upon delivery of license | Completed |  |  | 2024-04-18 |  |  | TBD
530 |  | Logrythm | ADJD - Logrythm | Vignesh | Product/License: 100% To be Invoiced upon delivery of Licenses | Completed |  |  | 11-0ct-2023
531 |  | Logrythm | ADJD - Logrythm | Vignesh | Appliances 100% on Delivery of the appliances | Completed |  |  | 2024-06-20
532 | RN-347 | Logrythm | ADJD - Logrythm | Vignesh | AMC - To be Invoiced quarterly Payment | Completed | 2024-07-01 | 2024-09-11 | 2024-09-11
520 |  | SolarWinds | Beema insurance SolarWinds | Vignesh | Payment terms – 30 days From Invoice Submission | Completed
14 | RN-104 | Rapid 7 | Abu Dhabi Aviation | Tanaya | Milestone 1: Vulnerability Assessment | Completed | 2022-06-14 |  | 2023-07-31 |  |  | COMPLETE |  |  | Paid | [6 empty] | 95%
15 | RN-104 | Rapid 7 | Abu Dhabi Aviation | Tanaya | Milestone 2: SIEM (M2 pending and upon completion) | Completed | 2022-06-14 |  | 2023-07-31 |  |  | 2023-08-01 | COMPLETE | 2023-08-01 | [7 empty] | 100%
16 | RN-105 | Sailpoint | PHCC(Phase1)Sailpoint | Rubeena | Milestone 1 : 100% to be raised upon delivery of license | Completed | 2022-06-23 |  | 2023-03-01 |  |  | COMPLETE | COMPLETE |  | Paid
17 | RN-105 | Sailpoint | PHCC(Phase1)Sailpoint | Rubeena | Milestone 2 : Kickoff, Infra Workshops, Sailpoint IIQ platform Installation (LCM and CM) | Completed | 2022-06-26 |  | 2023-03-01 |  |  | COMPLETE | COMPLETE |  | Paid
18 | RN-105 | Sailpoint | PHCC(Phase1)Sailpoint | Rubeena | Milestone 3 : Design Workshops, Requirement gathering and HLD 9 apps ( 3 sprints all apps ) | Completed | 2022-07-04 |  | 2023-03-01 |  |  | COMPLETE | COMPLETE |  | Paid
19 | RN-105 | Sailpoint | PHCC(Phase1)Sailpoint | Rubeena | Milestone 4 : Sprint 1: SailPoint Base Setup UAT Sign-off | Completed | 2022-09-12 |  | 2023-03-01 |  |  | COMPLETE | COMPLETE |  | Paid
20 | RN-105 | Sailpoint | PHCC(Phase1)Sailpoint | Rubeena | M5-UAT Sign off on Base Setup of LCM,UAT Sign off on Sprint 2 LCM | Completed | 2022-10-03 |  | 2023-03-01 |  |  | COMPLETE | COMPLETE |  | Paid
21 | RN-105 | Sailpoint | PHCC(Phase1)Sailpoint | Rubeena | M6-AMC POST golive ,Sign off on Final Go-Live/UAT | Completed | NA |  | 2023-03-01 |  |  | COMPLETE | COMPLETE |  | Paid
32 | RN-122 | Sailpoint | ADCB | Tanaya | M1 - Renewal of License upon SOW signoff | Completed | 2021-05-24 |  | 2021-05-24 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
33 | RN-122 | Sailpoint | ADCB | Tanaya | M2 - Platform Upgrade | Completed | 2021-06-15 |  | 2022-11-29 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
34 | RN-122 | Sailpoint | ADCB | Tanaya | M3, M4, M5, M6, M7 - Go-Live/UAT Sign off after 60 days | Completed | 2022-06-06 |  | 2023-01-19 |  |  | 2024-01-01 | COMPLETE | 2024-01-19 | [7 empty] | 88%
35 | RN-122 | Sailpoint | ADCB | Tanaya | M8 - New License Delivery | Completed |  |  | 2023-01-01 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
36 | RN-122 | Sailpoint | ADCB | Tanaya | M9. M12(1-50 Applications)- Sprint 2 Application (4 Apps) - Go-Live/UAT Sign off after 60 days | Completed | 2022-08-03 |  | 2023-01-19 |  |  | 2024-01-01 | COMPLETE | 2024-01-19 | [7 empty] | 46%
56 | RN-186 | Sailpoint | DMT- Sailpoint | Rubeena | M1 - Project Kickoff & License Delivery | Completed | 2022-11-30 |  | 2022-12-05 |  |  | COMPLETE |  |  | Paid
57 | RN-186 | Sailpoint | DMT- Sailpoint | Rubeena | M2 - 10% of Services to be paid upon completion of Design Workshops | Completed | 2022-12-15 |  | 2023-08-11 |  |  | 2023-08-01 | COMPLETE | 2023-08-11
58 | RN-186 | Sailpoint | DMT- Sailpoint | Rubeena | M3 - 10% of Services to be paid upon completion of Design Workshops and Design Document Submission for 5 Applications | Completed | 2023-01-05 |  | 2023-08-11 |  |  | 2023-08-01 | COMPLETE | 2023-08-11
59 | RN-186 | Sailpoint | DMT- Sailpoint | Rubeena | M4 - 15% of Services to be paid upon Go Live of Compliance Manager for Onboard of Oracle HRMS, Active Directory – 5 Domain - Oracle HRMS, - AD : 5 Domain/Instance Impementation of IAM - LCM : 3 Apps, | Completed | 2023-01-15 | 2023-11-23 | 2023-11-23 |  |  | 2023-11-01 | COMPLETE | 2023-11-23
60 | RN-186 | Sailpoint | DMT- Sailpoint | Rubeena | M5 - 15% of Services to be paid upon Go Live of Compliance Manager for Onboard of 5 Applications of Department. | Completed | 2023-02-15 | 2023-11-23 | 2023-11-23 |  |  | 2023-11-01 | COMPLETE | 2023-11-23
61 | RN-186 | Sailpoint | DMT- Sailpoint | Rubeena | M6 - 25% of Services to be paid upon Go Live of Life Cycle Manager (LCM) for Onboard of Oracle HRMS, Active Directory | Completed | 2023-04-15 | 2023-09-29 | 2023-09-29 |  |  | 2023-11-01 | COMPLETE | 2023-11-23
62 | RN-186 | Sailpoint | DMT- Sailpoint | Rubeena | M7 - 25% of Services to be paid upon Go Live of Life Cycle Manager (LCM) for Onboard of 5 Applications | Completed | 2023-05-04 | 2023-11-23 | 2023-11-23 |  |  | 2023-11-01 | COMPLETE | 2023-11-23
155 | RN-274 | IAM | NI External Client Build - IIQ | Rubeena | M1 - To be invoiced upon Project Signoff | Completed | 2023-04-03 |  | 2023-06-19 |  |  | COMPLETE |  |  | Paid
194 | RN-3 | VAPT | Voltas - VAPT | Rubeena | M1 - Upon completion (30 days from completion) | Completed | 2022-01-11 |  | 2022-01-17 |  |  | COMPLETE | COMPLETE |  | Paid
224 | RN-318 | VAPT | Emirates Centrol Cooling System Corp_VAPT_Web & Sec Assessement_Load Testing | Rubeena | M1 - 100% on Project Sign-off | Completed |  |  | 2023-08-07 |  |  | 2023-08-01 | COMPLETE | 2023-08-07
240 | RN-43 | VAPT | Empower - VAPT (Oct 21) | Rubeena | M1 - 75% upon Completion before retest | Completed | 2021-11-11 |  | 2022-06-21 |  |  | COMPLETE | COMPLETE |  | Paid
241 | RN-43 | VAPT | Empower - VAPT (Oct 21) | Rubeena | M2 - 25% upon project signoff | Completed | 2022-03-24 |  | 2022-05-12 |  |  | COMPLETE | COMPLETE |  | Paid
231 | RN-328 | IntelliDeploy | NI_2Month Outsource_Aug_2023 | Samruddhi | First month of outsourcing of Vamshi for Aug 23 | Completed |  |  | 2023-09-05 |  |  | 2023-09-01 | COMPLETE | 2023-09-05
232 | RN-328 | IntelliDeploy | NI_2Month Outsource_Aug_2023 | Samruddhi | Second month of outsourcing of Vamshhi for Sep | Completed |  |  | 2023-10-01 |  |  | 2023-10-01 | COMPLETE
350 | RN-377 | Rapid 7 | WIG - Nesto - Rapid 7 | Samruddhi | Rapid7 Tool – 100% on Delivery - InsightIDR Ultimate Subscription (License cost) | Completed |  |  | 2023-12-01 |  |  | 2023-12-01 | COMPLETE
351 | RN-368 | Solarwinds | Beema Insurance - Solarwinds NMC | Samruddhi | License delivery | Completed |  |  | 2023-11-01 |  |  | 2023-11-01 | Complete | 2023-11-09
352 | RN-368 | Solarwinds | Beema Insurance - Solarwinds NMC | Samruddhi | PS Remote | Completed |  |  | 2023-11-09 |  |  | 2023-11-01 | Complete | 2023-11-09
354 | RN-328 | IntelliDeploy | NI_2Month Outsource_Sep_2023 | Samruddhi | Third month of outsourcing of Vamshhi for Sep | Completed |  |  | 2023-12-01 |  |  | 2023-12-01 | COMPLETE
235 | RN-330 | ISO BCP & RA | ECAE - Audit | Samruddhi | IT Function Risk Assessment & 3-year Internal Audit Plan: 30% on project initiation | Completed |  |  | 2023-10-21 |  |  | 2023-10-01 | COMPLETE | 2023-10-21
309 | RN-359 | FortiNAC & FortiSIM | Property Finder - Fortinet NAC & FortiSIEM | Samruddhi | 30 day from license delivery | Completed |  |  | 2023-10-01 |  |  | 2023-10-01 | Complete
22 | RN-11 | VAPT | Aldar | Tanaya | M1 - 25% on Mobilization and Approved project plan | Completed | 2021-05-10 |  | 2021-05-10 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
23 | RN-11 | VAPT | Aldar | Tanaya | M2 - 45% on submission of Vapt reports | Completed | 2021-04-26 |  | 2023-10-13 |  |  | 2023-10-01 | COMPLETE | [8 empty] | 80%
24 | RN-11 | VAPT | Aldar | Tanaya | M3 - 15% on completion of re-scan review of fixes (Retest report) | Completed | 2021-12-01 |  | 2023-04-27 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
25 | RN-11 | VAPT | Aldar | Tanaya | M4 - 15% on consuming 35 mandays offsite efforts | Completed | 2021-04-01 |  | 2022-02-28 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
38 | RN-175 | Fortinet | National General Insurance | Tanaya | M1 - 100% upon license delivery | Completed | 2022-11-11 |  | 2023-07-07 |  |  | COMPLETE |  |  | Paid | [6 empty] | 50%
39 | RN-175 | Fortinet | National General Insurance | Tanaya | M2 - 50% of PS (Invoice in advanced) | Completed | 2023-12-12 |  | 2023-07-31 |  |  | COMPLETE |  |  | Paid | [6 empty] | 80%
40 | RN-175 | Fortinet | National General Insurance | Tanaya | M5 - 50% upon completion and signoff | Completed | 2023-07-17 |  | 2023-09-06 |  |  | 2023-09-01 | COMPLETE | 2023-09-06 | [7 empty] | 0%
41 | RN-175 | Fortinet | National General Insurance | Tanaya | M3 - 100% upon switch delivery | Completed |  |  | 2023-09-06 |  |  | 2023-09-01 | COMPLETE | 2023-09-06
42 | RN-175 | Fortinet | National General Insurance | Tanaya | Hardware delivery and 50% PS | Completed |  |  | 2023-09-06 |  |  | 2023-09-01 | COMPLETE | 2023-09-06
43 | RN-176 | VAPT | Emirates College | Tanaya | M1 - 100% upon Completion | Completed | 2022-12-20 |  | 2023-08-31 |  |  | COMPLETE |  |  | Paid | [6 empty] | 82%
69 | RN-197 | VAPT, SOC | Emirates Steel | Tanaya | Quarter 1 - 2023 | Completed | 2023-02-21 | 2023-02-01 | 2023-02-01 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
70 | RN-197 | VAPT, SOC | Emirates Steel | Tanaya | Quarter 2 - 2023 | Completed | 2023-05-22 | 2023-05-01 | 2023-05-01 |  |  | COMPLETE |  |  | Paid | [6 empty] | 50%
71 | RN-197 | VAPT, SOC | Emirates Steel | Tanaya | Quarter 3 - 2023 | Completed | 2023-08-01 | 2023-07-03 | 2023-07-03 |  |  | COMPLETE |  | 2023-07-03 | Not Received | 2023-08-02 | [5 empty] | 0%
72 | RN-197 | VAPT, SOC | Emirates Steel | Tanaya | Quarter 4 - 2023 | Completed | 2023-12-06 | 2023-10-01 | 2023-10-01 |  |  | 2023-12-01 | Complete | [8 empty] | 0%
73 | RN-20 | VAPT | Sentinel Capital | Tanaya | M1- 30% Advance | Completed | 2021-08-16 | 2023-07-18 | 2023-07-18 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
74 | RN-20 | VAPT | Sentinel Capital | Tanaya | M2 - 70% on Payment should be Post Dated Cheque along with PO acceptance | Completed | 2021-09-03 | 2023-07-18 | 2023-07-18 |  |  | COMPLETE |  |  | Paid | [6 empty] | 85%
75 | RN-20 | VAPT | Sentinel Capital | Tanaya | M3 - Perquisite verification, Migration, fine tuning, configuration & Knowledge Transfer (No Payment Milestone) | Completed | 2021-06-22 | 2023-07-18 | 2023-07-18 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
168 | RN-285 | Sailpoint | Airtel Africa | Tanaya | Milestone 1 : License Delivery | Completed | 2022-12-30 |  | 2022-12-30 |  |  | COMPLETE | COMPLETE | 2023-02-14 | Not Received | 2023-03-13 | [5 empty] | 100%
169 | RN-285 | Sailpoint | Airtel Africa | Tanaya | Milestone 2:Design Sign Off – SailPoint | Completed | 2023-06-12 |  | 2023-07-10 |  |  | 2023-08-01 | COMPLETE | 2023-08-01 | [7 empty] | 100%
170 | RN-285 | Sailpoint | Airtel Africa | Tanaya | Milestone 3:Design Sign Off – ForgeRock | Completed | 2023-06-15 |  | 2023-07-10 |  |  | 2023-08-01 | COMPLETE | 2023-08-01 | [7 empty] | 100%
171 | RN-285 | Sailpoint | Airtel Africa | Tanaya | Milestone 4: Base Setup & IIQ Foundation Module Setup with 11 Applications | Completed | 2023-03-31 |  | 2023-07-14 |  |  | 2023-08-01 | COMPLETE | 2023-08-01 | [7 empty] | 80%
172 | RN-285 | Sailpoint | Airtel Africa | Tanaya | Milestone 5: Base Setup & FAM Foundation Module Setup with 2 Applications | Completed | 2023-01-20 |  | 2023-07-25 |  |  | 2023-08-01 | COMPLETE | 2023-08-01 | [7 empty] | 33%
173 | RN-285 | Sailpoint | Airtel Africa | Tanaya | Milestone 6: Base Setup &ForgeRock Module Setup with 4 Applications | Completed | 2023-03-31 |  | 2023-07-14 |  |  | 2023-08-01 | COMPLETE | 2023-08-01 | [7 empty] | 50%
174 | RN-285 | Sailpoint | Airtel Africa | Tanaya | Milestone 7: UAT & Go- Live (Remaining 5 Applications) – ForgeRock | Completed | 2023-03-31 |  | 2023-08-14 |  |  | 2023-08-01 | COMPLETE | 2023-08-01 | [7 empty] | 20%
361 | RN-379 | Tenable | DLD_TENABLE | Tanaya | License delivery - Tenable SC and Identity Exp | Completed |  |  | 2023-12-01 |  |  | 2023-12-01 | COMPLETE
362 | RN-379 | Tenable | DLD_TENABLE | Tanaya | PS and AMC Charges (AMC is tracked in AMC tab) | Completed |  |  | 2023-12-01 |  |  | 2023-12-01 | COMPLETE
242 | RN-51 | SailPoint | Mashreq - sailpoint | Tanaya | Project Sign-off - Phase 1 | Completed |  |  | 2023-07-11 |  |  | COMPLETE | COMPLETE | 2023-07-12 | Paid | 2023-08-11 | 2023-08-09
243 | RN-51 | SailPoint | Mashreq - sailpoint | Tanaya | Project Stabilization Sign-off - Phase 1 | Completed |  |  | 2023-07-11 |  |  | COMPLETE | COMPLETE | 2023-07-12 | Paid | 2023-08-11 | 2023-08-09
129 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 1 - April | Completed | 2023-04-03 |  | 2023-05-03 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
130 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 2 - May | Completed | 2023-05-01 |  | 2023-06-14 |  |  | COMPLETE |  | 2023-06-23 | Not Received | 2023-08-07 | [5 empty] | 100%
131 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 3 - Jun | Completed | 2023-06-01 |  | 2023-07-05 |  |  | COMPLETE |  | 2023-07-06 | Not Received | 2023-08-20 | [5 empty] | 0%
132 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 4 - July | Completed | 2023-07-03 |  | 2023-08-10 |  |  | 2023-08-01 | COMPLETE | 2023-08-10 |  | 2023-09-24 | [5 empty] | 0%
133 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 5 - August | Completed | 2023-08-01 |  | 2023-09-15 |  |  | 2023-09-01 | COMPLETE | 2023-09-15 | [7 empty] | 0%
134 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 6 - September | Completed | 2023-09-01 |  | 2023-10-15 |  |  | 2023-10-01 | Complete | [8 empty] | 0%
135 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 7 - October | Completed | 2023-10-01 |  | 2023-11-15 |  |  | 2023-11-01 | Complete | [8 empty] | 0%
136 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 8 - November | Completed | 2023-11-01 |  | 2023-12-18 |  |  | 2023-12-01 | Complete | 2023-12-18 | [7 empty] | 0%
137 | RN-254 | IntelliDeploy | Digital 14 (Katim) - Katim | Tanaya | Month 9- December | Completed | 2023-12-01 |  | 2024-01-16 |  |  | 2024-01-01 | Complete | 2024-01-16 | [7 empty] | 0%
28 | RN-119 | BCP | Transco-BCP | Pallavi Nair | 100% upon completion - Q1 | Completed | 2023-01-31 |  | 2023-02-01 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 44%
29 | RN-119 | BCP | Transco-BCP | Pallavi Nair | 100% upon completion - Q2 | Completed | 2023-01-31 |  | 2023-04-01 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 44%
30 | RN-119 | BCP | Transco-BCP | Pallavi Nair | 100% upon completion - Q3 | Completed | 2023-01-31 |  | 2023-08-01 |  |  | 2023-09-01 | COMPLETE | 2023-09-09 | [7 empty] | 44%
31 | RN-119 | BCP | Transco-BCP | Pallavi Nair | 100% upon completion - Q4 | Cancelled | 2023-01-31 | 2023-12-30 |  |  |  | Cancelled | [9 empty] | 44%
63 | RN-19 | CyberArk | DOH - Cyberark | Pallavi Nair | M1 - KickOff Meeting (No Payment Milestone) | Completed | 2019-08-20 |  | 2019-08-20 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
64 | RN-19 | CyberArk | DOH - Cyberark | Pallavi Nair | M2 - CyberArk License Delivery - 75% Payment | Completed | 2019-09-08 |  | 2019-09-12 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
65 | RN-19 | CyberArk | DOH - Cyberark | Pallavi Nair | M3 - Installation & Configuration - CyberArk & SignOff - 25% Payment | Completed | 2021-02-11 |  | 2023-07-15 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 95%
82 | RN-228/337 | Proofpoint | RTS-Proofpoint | Pallavi Nair | 50% license fee paid upon signing | Completed | 2023-08-28 |  | 2023-09-01 |  |  | 2023-09-01 | COMPLETE |  | Paid
83 | RN-228/337 | Proofpoint | RTS-Proofpoint | Pallavi Nair | 50% license fee paid on project completion | Completed | 2024-01-12 |  | 2024-01-24 |  |  | 2024-01-01 | COMPLETE | 2024-01-24
84 | RN-228/337 | Proofpoint | RTS-Proofpoint | Pallavi Nair | Sign off on Prof Services | Completed | 2024-01-12 |  | 2024-01-24 |  |  | 2024-01-01 | COMPLETE | 2024-01-24
98 | RN-238 | VAPT | Seddiqi Holding-VAPT | Pallavi Nair | M1-50% - to be paid to the supplier on completion of Web Application Assessment (VAPT) + Network Architecture & Security Review + iPad Application Security Assessment | Completed | 2023-04-11 |  | 2023-09-06 |  |  | 2023-09-01 | Complete | 2023-09-06 |  |  |  | 3 web apps with reporting competed, Seddiqi holding to share the URLs of the remaining 2 apps iPad security assessment not started | 3 Web apps assessments and reporting completed Network Architecture and Security Review assessment and reporting completed. | seddiqi team to give URL of last 2 web apps |  | 56%
99 | RN-238 | VAPT | Seddiqi Holding-VAPT | Pallavi Nair | M2-30% - to be paid to the supplier on completion of Social Media, Brand Monitoring & Protection Services & Internal Network VAPT | Completed | 2023-05-22 |  | 2023-11-20 |  |  | 2023-11-01 | COMPLETE | 2023-11-20 |  |  |  | Social Media, Brand Monitoring & Protection Services Reporting & Internal Network VAPT assessment(Linux servers and Database) and reporting | Internal Network VAPT assessment(Poc) |  |  | 75%
100 | RN-238 | VAPT | Seddiqi Holding-VAPT | Pallavi Nair | M3-20 % - to be paid to the supplier on completion of project sign off | Completed | 2023-07-18 |  | 2023-11-20 |  |  | 2023-11-01 | COMPLETE | 2023-11-20 | [7 empty] | 40%
139 | RN-258 | Peplink | Arcadia School-Checkpoint Implementation | Pallavi Nair | 100% on 30 days from delivery | Completed | 2023-04-12 |  | 2023-06-01 |  |  | COMPLETE | COMPLETE |  | Paid |  | 2023-07-10 |  |  | Invoice raised, payment not received |  | 0.5%
140 | RN-259 | Checkpoint | Arcadia School-Checkpoint Implementation | Pallavi Nair | 100% on 30 days from delivery | Completed | 2023-04-12 |  | 2023-06-01 |  |  | COMPLETE | COMPLETE |  | Paid |  | 2023-07-10 |  |  | Invoice raised, payment not received |  | 0.5%
141 | RN-260 | Rapid 7 | Damac-Rapid 7 | Pallavi Nair | 100% Upon completion | Completed | 2023-04-10 |  | 2023-05-31 |  |  | COMPLETE | COMPLETE |  | Paid |  |  | Phase 4 - Final Project Documentation. | Phase 1, 2 and 3 completed |  |  | 95%
142 | RN-27 | Albatha | Albatha-ISO20000 | Pallavi Nair | 100 % upon completion of service delivery ( 60 days credit ) | Completed | 2023-05-09 |  | 2023-06-21 |  |  | COMPLETE | COMPLETE |  | Paid |  | 2023-07-17 |  |  | Awaiting sign off from the client |  | 100%
156 | RN-276 | PAM | Damas - Arcon (Vendor PS) | Pallavi Nair | M1: LICENSE+ | Completed | 2023-04-10 |  | 31may23 |  |  | COMPLETE |  |  | Paid
157 | RN-276 | PAM | Damas - Arcon (Vendor PS) | Pallavi Nair | M2: 50% IMPL upon license delivery | Completed | 2023-04-10 |  | 31may23 |  |  | COMPLETE |  |  | Paid
158 | RN-276 | PAM | Damas - Arcon (Vendor PS) | Pallavi Nair | M3: 50% Implementation upon completion | Completed | 2023-04-10 |  | 31may23 |  |  | 2024-05-10 |  |  | pending | [6 empty] | awaiting sign-off from the client, JP to meet client to ask for signoff
162 | RN-279 | Cybereason | Damas-Cybereason EDR (Vendor PS) | Pallavi Nair | M1 - 100% on 30 days from license delivery | Completed | 2023-04-29 |  | 2023-05-30 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
164 | RN-283 | Manage Engine (Vendor PS) | RAK Customs-Manage Engine | Pallavi Nair | M1 - 50% upon license delivery | Completed | 2023-05-15 |  | 2023-05-23 |  |  | COMPLETE | COMPLETE | [6 empty] | License delivered, invoice raised, payment not yet received |  | 100%
165 | RN-283 | Manage Engine (Vendor PS) | RAK Customs-Manage Engine | Pallavi Nair | M2 - 50% upon Project sign off as per LPO | Completed | 2023-05-15 |  | 2023-11-09 |  |  | 2023-11-01 | COMPLETE | 2023-11-09 |  |  |  | Prerequisites validation, Service desk workshop, Implementation | Kickoff completed, |  |  | 0.5%
204 | RN-307 | Cybereason | DWTC - Cybereason | Pallavi Nair | Product/License: 100% to be invoiced upon delivery of licenses paid | Completed | 2024-08-23 |  | 2024-08-23 |  |  | COMPLETE | COMPLETE |  | Paid
205 | RN-307 | Cybereason | DWTC - Cybereason | Pallavi Nair | Services: 100% to be invoiced upon Project Completion | Completed | 2023-11-07 |  | 2023-11-01 |  |  | 2023-11-01 | Complete
218 | RN-313 | Checkpoint | Al Dhafra Insurance Co PSC - Firewall Upgrade _14 NOS | Pallavi Nair | Advance 25% with the PO | Completed | 2023-07-26 |  | 2023-07-26 |  |  | 2023-07-01 | COMPLETE | 2023-07-26 | Paid | 2023-08-25 | 2023-08-10
219 | RN-313 | Checkpoint | Al Dhafra Insurance Co PSC - Firewall Upgrade _14 NOS | Pallavi Nair | upon delivery of the hardware | Completed | 2023-08-17 |  | 2023-08-17 |  |  | 2023-08-01 | COMPLETE | 2023-08-17
220 | RN-313 | Checkpoint | Al Dhafra Insurance Co PSC - Firewall Upgrade _14 NOS | Pallavi Nair | On completion of Project with 3 year license | Completed | 2023-08-01 |  | 2024-12-23 |  |  | 2023-12-01 | COMPLETE
271 | RN-341 | Cybereason | Waha Health - CyberReason PS - 4 Days | Pallavi Nair | Health Bay Day Surgery Center LLC. | Completed | 2023-09-21 |  | 2023-09-21 |  |  | 2023-09-01 | COMPLETE | 2023-09-21
272 | RN-341 | Cybereason | Waha Health - CyberReason PS - 4 Days | Pallavi Nair | WPI Health Investments LLC. | Completed | 2023-09-21 |  | 2023-09-21 |  |  | 2023-10-01 | COMPLETE | 2023-09-21
274 | RN-350 | Cybereason | MOFAIC Cybereason | Pallavi Nair | M2 - Upon Sign-off | Completed | 2023-12-27 |  | 2023-09-21 |  |  | 2023-09-01 | Complete | 2023-09-21
304 | RN-333 | Office Relocation | Apex Fund Services | Pallavi Nair | 100% payment | Completed | 2023-08-14 |  | 2023-10-09 |  |  | 2023-10-01 | COMPLETE
386 | RN-378 | Managed Services | MBRSG_Securonix | Pallavi Nair | Qtrly payments - last working day of second month in each Qtr | Completed | 2024-01-24 |  | 2024-01-24 |  |  | 2024-01-23 | COMPLETE
387 | RN-378 | Managed Services | MBRSG_Securonix | Pallavi Nair | Qtrly payments - last working day of second month in each Qtr | Completed | 2024-04-24 |  | 2024-04-24 |  |  | 2024-04-24 | COMPLETE
388 | RN-378 | Managed Services | MBRSG_Securonix | Pallavi Nair | Qtrly payments - last working day of second month in each Qtr | Completed | 2024-07-24 |  | 2024-07-24
389 | RN-378 | Managed Services | MBRSG_Securonix | Pallavi Nair | Qtrly payments - last working day of second month in each Qtr | Completed | 2024-10-24 | 2024-10-24 | 2024-10-24
538 | RN-459 | CyberArk | ZMI CyberArk | Pallavi Nair | 100% to be invoiced upon delivery of licenses | Completed | 2024-05-24 |  | 2024-05-24
539 | RN-459 | CyberArk | ZMI CyberArk | Pallavi Nair | 50% on formal kickoff | Completed | 2024-07-24 | 2024-07-30 | 2024-07-30
540 | RN-459 | CyberArk | ZMI CyberArk | Pallavi Nair | 50% on completion. | Completed | 2024-07-24 | 2024-10-31 | 2024-10-31
244 | RN-6 | VAPT | Al Jazeira | Pallavi Nair | 100% upon completion | Completed | 2022-08-26 |  | 2023-07-10 |  |  | COMPLETE | COMPLETE |  | Paid |  |  |  |  | Sign-off received |  | 100%
222 | RN-317 | VAPT | Ajman Chamber of Commerce & Industry | Pallavi Nair | 80% Assessemnt with reporting | Completed | 2023-08-07 |  | 2023-12-01 |  |  | 2023-12-01 | COMPLETE
223 | RN-317 | VAPT | Ajman Chamber of Commerce & Industry | Pallavi Nair | 20% after Resting and signoff | Completed | 2023-12-07 |  | 2023-12-01 |  |  | 2023-12-01 | COMPLETE
270 | RN-341 | Cybereason | Waha Health - CyberReason PS - 4 Days | Pallavi Nair | Orchid Reproductive and Andrology Services FZ LLC. | Completed | 2023-09-21 |  | 2023-09-21 |  |  | 2023-09-01 | COMPLETE | 2023-09-21
20 | RN-18 | IAM | DOH - Sailpoint | Pallavi Nair | M1 - KickOff Meeting | Completed | 2019-08-15 |  | 2019-08-15 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
21 | RN-18 | IAM | DOH - Sailpoint | Pallavi Nair | M2 - SailPoint License Delivery | Completed | 2019-09-08 |  | 2019-09-12 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
22 | RN-18 | IAM | DOH - Sailpoint | Pallavi Nair | M3 - Installation & Configuration - SailPoint IIQ (No Payment Milestone) | Completed | 2020-06-21 |  | 2023-09-17 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 85%
23 | RN-18 | IAM | DOH - Sailpoint | Pallavi Nair | M4 - Installation & Configuration - SailPoint SIQ/FAM (No Payment Milestone) | Completed | 2021-07-15 |  | 2023-08-04 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 37%
74 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | Y1 - License cost shall be paid annually for 3 Years within 30 days. Subject to submission of complete documentation (Invoice, License Activation Report, Statement of Account) | Completed | 2023-08-21 |  | 2023-09-08 |  |  | 2023-09-01 | Complete | 2023-09-06
75 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | Y12 - License cost shall be paid annually for 3 Years within 30 days. Subject to submission of complete documentation (Invoice, License Activation Report, Statement of Account) | Completed | 2024-08-21 | 2025-08-20 | 2025-08-20 |  |  | 2024-08-01
77 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | 30% of the total cost for the Professional Services shall be paid within 30 days upon completion of the project kick off, subject to acceptance of the same by concerned Project Manager from ADNEC. | Completed | 2023-08-25 |  | 2023-09-04 |  |  | 2023-09-01 | Complete | 2023-09-08
78 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | 50% of the total cost for the Professional Services shall be paid within 30 days upon completion of the configuration, testing, and go live of the project, subject to acceptance of the same by concerned Project Manager from ADNEC | Completed | 2023-10-30 | 2024-12-06 | 2024-12-06 |  |  | 2024-05-10
79 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | 20% of the total cost for the Professional Services shall be paid within 30 days upon completion of the snag points, if any, (to be rectified), subject to acceptance of the same by concerned Project Manager from ADNEC | Completed | 2024-07-30 | 2024-12-06 | 2024-12-06 |  |  | 2024-05-10
80 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | 100% of the total cost for the training shall be paid upon completion of training. | Completed | 2024-07-01 | 2024-12-06 | 2024-12-06 |  |  | 2024-07-01
81 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | RNS Onsite Engineer for 3 Months, Monthly invoices from resources deployed - 1M | Completed | 2024-05-27 |  | 2024-05-27 |  |  | 2024-05-10
82 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | RNS Onsite Engineer for 3 Months, Monthly invoices from resources deployed - 2M | Completed | 2024-06-27 |  | 2024-06-27 |  |  | 2024-06-10
83 | RN-308 | CyberArc | ADNEC CyberArc | Pallavi Nair | RNS Onsite Engineer for 3 Months, Monthly invoices from resources deployed - 3 M | Completed | 2024-07-27 |  | 2024-07-27 |  |  | 2024-07-01
101 | RN-78 | Sailpoint | Dubai Land Department | Pallavi Nair | M1 - Completion of the First Stage: purchasing a license with support for one year | Completed | 2021-12-06 | 2021-12-06 | 2021-12-06 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
102 | RN-78 | Sailpoint | Dubai Land Department | Pallavi Nair | M2 - Completion of the Second Stage: Main paramount of CM Module -Identity Governance with First Party Approval | Completed | 2022-05-13 | 2023-07-31 | 2023-07-31 |  |  | COMPLETE |  |  | Paid | [6 empty] | 90%
103 | RN-78 | Sailpoint | Dubai Land Department | Pallavi Nair | M3 - Completion of the Third Stage: Main paramount of FAM Unit - Data approved by the First Party | Completed | 2022-05-13 | 2023-05-09 | 2023-05-09 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
104 | RN-78 | Sailpoint | Dubai Land Department | Pallavi Nair | M4 - Completion of the Fourth Stage: training of employees and handing over the project with the approval of the First Party | Completed | 2022-06-13 | 2023-04-24 | 2023-04-24 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
167 | RN-365 | SailPoint | NIJordan_SailPoint_Sept_2023 | Pallavi Nair | 50% to be invoiced upon Completion of Application Integration – 5 Qty | Completed | 2023-11-02 |  | 2024-05-23 |  |  | 2024-05-03 | [9 empty] | Receeived conditional Signoff
168 | RN-369 | SailPoint | NIJordan_SailPoint_Sept_2023 | Pallavi Nair | 50% to be invoiced upon Completion of Workflow Development as per SOW | Completed | 2024-02-21 |  | 2024-05-23 |  |  | 2024-05-09 | [9 empty] | Receeived conditional Signoff
169 | RN-361 | SailPoint | Mashreq Sailpoint Phase 2 | Laxmi | 40% upon completion of Helix & CDP in PROD with Configuration Changes for existing 27 applications | Completed | 2024-04-01 | 2024-06-30 | 2024-09-20 |  |  | 2024-05-31 | Paid | Received the payment
170 | RN-361 | SailPoint | Mashreq Sailpoint Phase 2 | Laxmi | 100% upon completion of IIQ Upgrade in UAT Environment | Completed | 2024-03-05 |  | 2024-04-15 |  |  | 2024-04-05 | COMPLETE | 2024-04-15
171 | RN-361 | SailPoint | Mashreq Sailpoint Phase 2 | Laxmi | 100% upon completion of Prod Upgrade & Go-Live/Sign Off | Completed | 2024-03-11 |  | 2024-05-03 |  |  | 2024-05-03 | [9 empty] | 100%
172 | RN-371 | SailPoint | AXA_Gulf Insurance Group – SailPoint CR (7 CRs) | Laxmi | 50% to be invoiced upon LPO | Completed |  |  | 2023-12-07 |  |  | 2023-12-01 | COMPLETE | 2023-12-07
173 | RN-371 | SailPoint | AXA_Gulf Insurance Group – SailPoint CR (7 CRs) | Laxmi | 50% to be invoiced upon Sign-off | Completed |  |  | 2023-12-07 |  |  | 2023-12-01 | COMPLETE | 2023-12-07
174 | RN-366 | SailPoint | NISailPoint_SouthAfrica_Sept_2023 | Pallavi Nair | Invoice upon License Delivery | Completed | 2024-01-01 |  | 2024-01-01 |  |  | 2024-01-01 | COMPLETE
175 | RN-366 | SailPoint | NISailPoint_SouthAfrica_Sept_2023 | Pallavi Nair | 30% to be Invoiced upon Completion of Milestone 1: Design & Base Setup for NI - SA for UAT / Prod | Completed | 2023-12-21 |  | 2024-01-01 |  |  | 2024-01-01 | COMPLETE
176 | RN-366 | SailPoint | NISailPoint_SouthAfrica_Sept_2023 | Pallavi Nair | 40% to be Invoiced upon Completion of Milestone 2: UAT & Go- Live (Sprint 1) - SailPoint IIQ - 2 Application | Completed | 2024-03-04 | 2024-08-02 | 2024-08-08 |  |  | 2024-05-03 | [9 empty] | Dependency on firewal opening which is not yet opened - PGC is working with client - we can invoice and PGC will get the conditional sign-off after fw rule is open and code is migrated to prod
177 | RN-366 | SailPoint | NISailPoint_SouthAfrica_Sept_2023 | Pallavi Nair | 30% to be Invoiced upon Completion of Milestone 3: UAT & Go- Live (Sprint 2) - SailPoint IIQ - 3 Application | Completed | 2024-03-14 | 2024-08-02 | 2024-08-08 |  |  | 2024-05-06 | [9 empty] | Dependency on firewal opening which is not yet opened - PGC is working with client - we can invoice and PGC will get the conditional sign-off after fw rule is open and code is migrated to prod
178 | RN-375 | CyberArc | ADEK - CyberArc | Pallavi Nair | Licenses - 03 Feb 23 to 02 Feb 26 | Completed | 2023-12-01 |  | 2023-12-01 |  |  | 2023-12-01 | COMPLETE
179 | RN-375 | CyberArc | ADEK - CyberArc | Pallavi Nair | Optional additional Licenses - Qty 5 | Completed | 2024-03-19 | 2024-10-21 | 2024-10-21 |  |  | TBD
180 | RN-375 | CyberArc | ADEK - CyberArc | Pallavi Nair | To be Invoiced upon Design Sign-off 25% | Completed | 2024-04-02 |  | 2024-04-22 |  |  | 2024-04-19 | COMPLETE | 2024-04-02
181 | RN-375 | CyberArc | ADEK - CyberArc | Pallavi Nair | To be Invoiced upon Configuration, Rollout and UAT Sign-off - 50% | Completed | 2024-06-06 |  | 2024-06-11 |  |  | 2024-05-03
182 | RN-375 | CyberArc | ADEK - CyberArc | Pallavi Nair | To be Invoiced upon Documentation and Handover Sign off - 25% | Completed | 2024-06-06 | 2024-12-13 | 2024-12-13 |  |  | 2024-05-10
198 | RN-382 | CyberArc | OQ Trading_ PAM | Pallavi Nair | Product/License: 100% to be invoiced upon delivery of licenses | Completed | 2024-01-16 |  | 2024-01-16 |  |  | 2024-01-01 | COMPLETE | 2024-01-16
199 | RN-382 | CyberArc | OQ Trading_ PAM | Pallavi Nair | Services: 50% at the start of implementation | Completed | 2024-03-01 |  | 2024-03-26 |  |  | 2024-03-29 | COMPLETE | 2024-03-29
200 | RN-382 | CyberArc | OQ Trading_ PAM | Pallavi Nair | Services: 50% at the remaining on signoff | Completed | 2024-06-20 | 2024-08-09 | 2024-08-09 |  |  | 2024-06-20
201 | RN-383 | SailPoint | NI Egypt Sailpoint | Pallavi Nair | Milestone 1 : UAT Sign-Off of 7 Enhancements -20% | Completed | 2024-03-11 |  | 2024-04-22 |  |  | 2024-04-26 | COMPLETE | 2024-04-23
202 | RN-383 | SailPoint | NI Egypt Sailpoint | Pallavi Nair | Milestone 2: UAT Sign-Off of Phase 2.1 -03 Applications completed-100% | Completed | 2024-03-11 |  | 2024-04-30 |  |  | 2024-05-24
203 | RN-383 | SailPoint | NI Egypt Sailpoint | Pallavi Nair | Milestone 3: UAT Sign-Off of Phase 2.2 -4 Applications -30% | Completed | 2024-04-22 | 2024-12-11 | 2024-12-11 |  |  | 2024-06-21 | [9 empty] | Customers has not shared the full details of apps to kick start the work
204 | RN-383 | SailPoint | NI Egypt Sailpoint | Pallavi Nair | Milestone 4: UAT Sign-Off of Phase 2.2 - Remaining 4 Applications & Final Go-live, Documentation and Handover-30% " | Completed | 2024-05-01 | 2024-12-11 | 2024-12-11 |  |  | 2024-06-21 | [9 empty] | Customers has not shared the full details of apps to kick start the work
220 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-01-01 | 2024-01-31 | 2024-02-14 |  |  | 2024-04-01 | Complete | 2024-04-23
221 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-02-01 | 2024-02-29 | 2024-03-11 |  |  | 2024-04-01 | Complete | 2024-04-23
222 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-03-01 | 2024-03-31 | 2024-04-04 |  |  | 2024-04-01 | Complete | 2024-04-23
223 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-04-01 | 2024-04-30 | 2024-05-08 |  |  | 2024-04-01 | Complete | 2024-04-23
224 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-05-01 | 2024-05-30 | 2024-06-06 |  |  | 2024-05-01
225 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-06-01 | 2024-06-30 | 2024-07-01 |  |  | 2024-06-01
226 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-07-01 | 2024-07-31 | 2024-08-01 |  |  | 2024-07-01
227 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-08-02 | 2024-08-31 | 2024-09-09 |  |  | 2024-08-01
228 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-09-01 | 2024-09-30 | 2024-10-03 |  |  | 2024-09-01
229 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-10-01 | 2024-10-31 | 2024-11-05 |  |  | 2024-11-01
230 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-11-01 | 2024-11-30 | 2024-12-12 |  |  | 2024-12-01
231 | RN-254 | SailPoint | Digital 14 (Katim)_Resource Deployment | Pallavi Nair | Monthly Signoff | Completed | 2024-12-01 | 2024-12-31 |  |  |  | 2025-01-01
378 | New | BeyondTrust | Nextcare - BeyondTrust | Pallavi Nair | 100% invoice with the LPO | Completed | 2024-08-16 | 2024-08-16 | 2024-08-16
39 | RN-25 | Rapid 7, SOC, VAPT | Gulf Drug | Tanaya | Quarterly advance Payment - August 2022 (M1) + License and one time installation | Cancelled | [5 empty] | Invoiced, on hold |  | 2022-10-01 | Not Received | 2022-10-30
40 | RN-25 | Rapid 7, SOC, VAPT | Gulf Drug | Tanaya | Quarterly advance Payment - November 2022 (M2) | Cancelled | [5 empty] | Invoiced, on hold |  | 2023-01-18 | Not Received | 2023-02-17
41 | RN-25 | Rapid 7, SOC, VAPT | Gulf Drug | Tanaya | Quarterly advance Payment - Feb 2023 (M3) | Cancelled | [5 empty] | On Hold
42 | RN-25 | Rapid 7, SOC, VAPT | Gulf Drug | Tanaya | Quarterly advance Payment - May 2023 (M4) | Cancelled | [5 empty] | On Hold
58 | RN-288 | VAPT | Damas - API Testing | Tanaya | Within 30 days from Invoice | Completed | 2023-06-01 |  | 2023-08-09 |  |  | COMPLETE |  | 2023-06-08 | Paid | 2023-07-08 | 2023-08-07 |  |  |  |  | 100%
65 | RN-300 | Opswat | MOFA - Opswat implementation by Forcespot | Tanaya | M1-20-Sep-23 | Completed |  |  | 2023-10-18 |  |  | 2023-09-01 | COMPLETE
66 | RN-300 | Opswat | MOFA - Opswat implementation by Forcespot | Tanaya | M2-10-April-24 | Completed |  |  | 2023-10-18 |  |  | 2024-05-10
67 | RN-300 | Opswat | MOFA - Opswat implementation by Forcespot | Tanaya | M3-30-March-2025 | Completed |  |  | 2023-10-18 |  |  | 2025-03-01
84 | RN-312 | F5 Networks | F5 Networks - Emirates Steel | Tanaya | M1 - 90% upon activation of licenses (Licenses will be activated by 15th Sep) | Completed |  |  | 2023-09-21 |  |  | 2023-09-01 | Complete | 2023-09-21
85 | RN-312 | F5 Networks | F5 Networks - Emirates Steel | Tanaya | M2 - 10% upon Project Sign-off | Completed |  |  | 2024-04-05 |  |  | 2024-04-05 | Complete
96 | RN-7 & RN118 | Rapid 7 & VAPT | Ajman Chambers | Tanaya | M1 - 10% of contract value (Provide bank gaurantee) | Completed | 2022-10-11 |  | 2022-10-11 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
97 | RN-7 & RN118 | Rapid 7 & VAPT | Ajman Chambers | Tanaya | M2-25% of contract value after completion of Phase 1 (VAPT) | Completed | 2022-08-12 |  | 2023-07-17 |  |  | COMPLETE |  | 2023-07-17 | Not Received | 2023-08-16 | [5 empty] | 70%
98 | RN-7 & RN118 | Rapid 7 & VAPT | Ajman Chambers | Tanaya | M3- 25% of contract value after completion of Phase 2 (Rapid 7) | Completed | 2022-09-21 |  | 2023-11-01 |  |  | 2023-11-01 | Complete | [8 empty] | 85%
99 | RN-7 & RN118 | Rapid 7 & VAPT | Ajman Chambers | Tanaya | M4-30% of contract value based on Documentation & KT | Completed | 2022-10-31 |  | 2023-11-01 |  |  | 2023-11-01 | Complete | [8 empty] | 50%
100 | RN-7 & RN118 | Rapid 7 & VAPT | Ajman Chambers | Tanaya | M5- 10% of contract value upon completion of sign off and completion of 90 days post sign off | Completed | 2023-08-11 |  | 2023-11-01 |  |  | 2023-11-01 | Complete | [8 empty] | 60%
105 | RN-82 | VAPT | Cube Payments | Tanaya | M1 - Upon acceptance - 25% Payment (Submission of project plan for the year) | Completed | 2022-03-01 |  | 2023-03-01 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
106 | RN-82 | VAPT | Cube Payments | Tanaya | M2- Activation on PT (25% payment) | Completed | 2023-02-01 |  | 2022-08-24 |  |  | COMPLETE |  | 2022-08-24 | Paid | [6 empty] | 50%
107 | RN-82 | VAPT | Cube Payments | Tanaya | Y3 M3- Audited Report - 50% Payment | Completed |  |  | 2023-08-08 |  |  | 2023-08-01 | COMPLETE | 2023-08-08 |  | 2023-09-07
108 | RN-82 | VAPT | Cube Payments | Vignesh | Y4 M1 - Upon acceptance - 25% Payment (Submission of project plan for the year) | Delayed | [5 empty] | On Hold | [9 empty] | Legal case filed
109 | RN-82 | VAPT | Cube Payments | Vignesh | Y4M2 - Activation on PT (25% payment) | Delayed | [5 empty] | On Hold | [9 empty] | Legal case filed
110 | RN-82 | VAPT | Cube Payments | Vignesh | Y4 M3 - Audited Report - 50% Payment | Delayed | [5 empty] | On Hold | [9 empty] | Legal case filed
111 | RN-82 | VAPT | Cube Payments | Vignesh | Y5 M1 - Upon acceptance - 25% Payment (Submission of project plan for the year) | Delayed | [5 empty] | On Hold | [9 empty] | Legal case filed
112 | RN-82 | VAPT | Cube Payments | Vignesh | Y5M2 - Activation on PT (25% payment) | Delayed | [5 empty] | On Hold | [9 empty] | Legal case filed
113 | RN-82 | VAPT | Cube Payments | Vignesh | Y5 M3 - Audited Report - 50% Payment | Delayed | [5 empty] | On Hold | [9 empty] | Legal case filed
195 | RN-395 | VAPT | Gulf Cement Company_VAPT | Vignesh | External Initial Assessment with Reporting = 40% | Completed |  |  | 2024-02-16 |  |  | 2024-02-01 | COMPLETE | 2024-02-16
196 | RN-395 | VAPT | Gulf Cement Company_VAPT | Vignesh | Internal Initial Assessment with Reporting + source code review =50% | Completed |  |  | 2024-02-16 |  |  | 2024-02-01 | COMPLETE | 2024-02-16
197 | RN-395 | VAPT | Gulf Cement Company_VAPT | Vignesh | Retesting & Signoff = 10% | Completed |  | 2024-10-30 | 2024-11-25 |  |  | 2024-05-03
331 | RN-447 | VAPT | Gulf cryo- VAPT | Vignesh | External Initial Assessment with Reporting = 60% | Completed | 2024-07-10 | 2024-10-07 | 2024-10-09
332 | RN-447 | VAPT | Gulf cryo- VAPT | Vignesh | Internal Initial Assessment with Reporting = 30% | Completed | 2024-07-10 | 2024-10-07 | 2024-10-09
333 | RN-447 | VAPT | Gulf cryo- VAPT | Vignesh | Retesting & Signoff = 10% | Completed | 2024-12-09 | 2025-01-15 | 2024-12-23
338 |  | Zscaler | AMICO | Vignesh | Product/License: 100% to be invoiced upon delivery of licenses | Completed |  |  | 2024-06-30
339 | New | Zscaler | AMICO | Vignesh | -Kick-off call, Info Gathering & Design Finalization – 20% | Completed | 2024-07-01 | TBD | 2024-11-27
340 | New | Zscaler | AMICO | Vignesh | Implementation and configuration of ZIA Traffic Forwarding, Authentication and Provisioning, ZIA Policies, ZIA SSL Enablement, ZIA Reporting, ZIA Test Cases – 60% | Completed | 2024-07-01 | TBD | 2024-11-27
341 | RN-444 | Zscaler | [5 empty] | 2024-08-30
342 | RN-444 | Zscaler | AMICO | Vignesh | -Production User rollout & Project Signoff Rollout for the pilot users (10) – 20% | Completed | 2024-07-01 | TBD | 2024-11-27
347 | RN-460 | VAPT | SWSC - VAPT | Vignesh | External initial Assessment with Reporting = 40% | Completed | 2024-07-29 | 2025-01-24 | 2024-10-07
348 | RN-460 | VAPT | SWSC - VAPT | Vignesh | Internal Initial Assessment with Reporting = 40% | Completed | 2024-07-29 | 2025-01-31 | 2024-10-07
349 | RN-460 | VAPT | SWSC - VAPT | Vignesh | Optional – Remediation = 10% | Completed |  | 2025-02-07 | 2024-11-11
350 | RN-460 | VAPT | SWSC - VAPT | Vignesh | Retesting & Signoff = 10% | Completed |  | 2025-01-14 | 2024-12-27
412 | RN-496 | Net Sec | ADJD - Forcepoint, LogRhythm, Mcafee, CyberArk | Vignesh | 100% upon license delivery | Completed | 2024-11-04 | 2024-11-04 | 2024-11-04
413 | RN-496 | Net Sec | ADJD - AMC | Vignesh | Quarterly Invoice | On Track | 2024-10-14 | 2025-10-13
27 | RN-22 | Sailpoint | DIB - Sailpoint | Laxmi | M1 - 60% To be Invoiced on Delivery of Licenses | Completed | TBD | 2022-01-17 | 2024-10-23 |  |  | COMPLETE | COMPLETE |  | Paid
28 | RN-22 | Sailpoint | DIB - Sailpoint | Laxmi | M2 - 10% To be Invoiced on Project Kick-Off | Completed | 2022-01-17 | 2022-01-17 | 2024-10-23 |  |  | COMPLETE | COMPLETE |  | Paid
29 | RN-22 | Sailpoint | DIB - Sailpoint | Laxmi | M3 - 10% To be Invoiced on Resource Mobilization | Completed | 2022-01-31 | 2022-06-17 | 2024-10-23 |  |  | COMPLETE | COMPLETE |  | Paid
30 | RN-22 | Sailpoint | DIB - Sailpoint | Laxmi | M4 - 10% on UAT Testing | Completed | 2022-04-28 | 2024-09-15 | 2024-10-23 |  |  | 2024-05-10
31 | RN-22 | Sailpoint | DIB - Sailpoint | Laxmi | M5 - 10% on Sign-Off | Completed | 2022-06-30 | 2024-09-15 | 2024-12-07 |  |  | 2024-05-15
32 | RN-228/337 | Proofpoint | RTS-Proofpoint | Divya | Licenses: 90 days net from the license's delivery; Licenses needs to be activated only on 01st Feb 2023 | Completed | NA |  | 2023-02-01 |  |  | COMPLETE | COMPLETE | 2023-02-01 | Not Received | 2023-05-02
46 | RN-257 | Sailpoint | AXA-Sailpoint DEC CR | Laxmi | M1 - 100% upon deliver | Completed | 2022-12-06 |  | 2023-01-04 |  |  | COMPLETE |  |  | Paid |  |  | 9 | 4 |  |  | conditional sign-off received
187 | RN-381 | SailPoint | EDC_Emirates Driving Company_Sailpoint | Laxmi | M1 - 25% advance along with LPO - Installation & Base Setup | Completed |  |  | 2023-12-12 |  |  | 2023-12-01 | COMPLETE | 2023-12-12
188 | RN-381 | SailPoint | EDC_Emirates Driving Company_Sailpoint | Laxmi | M2 - 35% after completion of configuration of JML & Sprint 1 application (4 apps) - CM, LCM & PM | Completed |  |  | 2024-05-10 |  |  | 2024-05-10
189 | RN-381 | SailPoint | EDC_Emirates Driving Company_Sailpoint | Laxmi | M3 - 40% on Project Sign Off - RBAC Implementation | Completed | 2024-05-25 | 2024-06-30 | 2024-08-02 |  |  | 2024-05-24
190 | RN-371 | SailPoint | AXA_Gulf Insurance Group – SailPoint Upgrade 8.1 to 8.3p3(Now) & 8.4(Once it is stabilized) - Separate project | Laxmi | M1 - IIQ Upgrade to 8.3p in UAT Environment – 50% | Completed | 2023-12-21 |  | 2023-12-11 |  |  | 2023-12-01 | COMPLETE | 2023-12-11
191 | RN-371 | SailPoint | AXA_Gulf Insurance Group – SailPoint Upgrade 8.1 to 8.3p3(Now) & 8.4(Once it is stabilized)- Separate project | Laxmi | M2 - Prod Upgrade to 8.3p & Go-Live/Sign Off – 50 % | Completed | 2024-01-09 |  | 2024-02-29 |  |  | 2024-02-01 | COMPLETE | 2024-02-29
245 | RN-340 | Sailpoint | Airtel Africa Phase 2 | Laxmi | Milestone 8:Design Sign Off - Sailpoint IIQ & ForgeRock 40% | Completed | 2023-09-21 |  | 2024-06-09 |  |  | 2024-06-06 | [9 empty] | Sign-off has been initiated
246 | RN-340 | Sailpoint | Airtel Africa Phase 2 | Laxmi | Milestone 9: UAT & Go- Live (Sprint 6) - SailPoint IIQ 15% | Completed | 2023-12-15 | 2024-06-21 | 2024-06-21 |  |  | 2024-07-24 | [9 empty] | 15 apps go-live to be completed by 21 June
247 | RN-340 | Sailpoint | Airtel Africa Phase 2 | Laxmi | Milestone 10: UAT & Go- Live (Sprint 7) - SailPoint IIQ 15% | Completed | 2024-03-25 | 2024-09-02 | 2024-09-02 |  |  | 2024-08-06
248 | RN-340 | Sailpoint | Airtel Africa Phase 2 | Laxmi | Milestone 11: UAT & Go- Live (Sprint 9) - ForgeRock 15% | Completed | 2023-09-26 | 2024-06-28 | 2024-06-28 |  |  | 2024-07-24 | [9 empty] | 15 apps go-live to be completed by 28 June
249 | RN-340 | Sailpoint | Airtel Africa Phase 2 | Laxmi | Milestone 12: UAT & Go- Live (Sprint 10) - ForgeRock 15% | Completed | 2024-02-12 | 2024-09-03 | 2024-09-03 |  |  | 2024-08-24 | [9 empty] | Pending on management for the update
250 | RN-239 | Sailpoint | Aldar Sailpoint_CR_4Enhancements | Laxmi | 50% on completion of any of the 2 enhancements | Completed | 2024-03-01 |  | 2024-04-25 |  |  | 2024-04-15 | COMPLETE | 2024-04-05 | [7 empty] | payment received
251 | RN-239 | Sailpoint | Aldar Sailpoint_CR_4Enhancements | Laxmi | 50% on completion of pending 2 enhancements | Completed | 2024-04-15 |  | 2024-06-10 |  |  | 2024-05-15 | [9 empty] | It will be completed before the planned end date
400 | RN-485 | CyberArk | Presidential Flights | Laxmi | a. to be invoiced 50% on Kickoff | Completed | 2024-10-07 | 2024-11-06 | 2024-11-06 | [12 empty] | 100%
401 | RN-485 | CyberArk | Presidential Flights | Laxmi | b. 50% Sign off | Completed | 2024-10-07 | 2024-12-11 | 2024-12-11 | [12 empty] | 100%
1 | RN--23 | ForcePoint, FP | DLD- Bolden James & Forcepoint | Sean Faizal | M1 - License delivery | Completed | 2021-03-11 |  | 2021-03-31 |  |  | COMPLETE | COMPLETE |  | Paid
2 | RN--23 | ForcePoint, FP | DLD- Bolden James & Forcepoint | Sean Faizal | M2 - Install, Config, Migration & Signoff (No Payment Milestone) | Completed | 2021-03-14 |  | 2021-05-09 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | This can be closed, as KD confirmed
3 | RN-101 | ForcePoint, FP | Tawazun Industrial Park | Sean Faizal | M1 - 20% upon license delivery | Completed | 2022-05-15 |  | 2022-08-31 |  |  | COMPLETE |  |  | Paid | [6 empty] | 100%
9 | RN-102 | VAPT | ALDAR ACADAMICS & ADNOC SCHOOLS | Sean Faizal | M1- 30% - External test & Report acceptance for Aldar Academics | Completed | 2022-09-13 |  | 2023-06-23 |  |  | COMPLETE | COMPLETE | 2023-06-23 | Not Received | 2023-07-22 |  | social Engg |  | Dependency on on ALDAR team |  | 75%
10 | RN-102 | VAPT | ALDAR ACADAMICS & ADNOC SCHOOLS | Sean Faizal | M2- 30% - External test and report accpetance for ADNOC schools | Completed | 2022-10-05 |  | 2023-06-23 |  |  | COMPLETE | COMPLETE | 2023-06-23 | Not Received | 2023-07-22 |  | social Engg |  | Dependency on on ALDAR team |  | 75%
11 | RN-102 | VAPT | ALDAR ACADAMICS & ADNOC SCHOOLS | Sean Faizal | M3- 15% - Internal test report and acceptance for Aldar Academics | Completed | 2022-10-20 |  | 2023-06-23 |  |  | COMPLETE | COMPLETE | 2023-06-23 | Not Received | 2023-07-22 | [5 empty] | 100%
12 | RN-102 | VAPT | ALDAR ACADAMICS & ADNOC SCHOOLS | Sean Faizal | M4- 15% - Internal test report and acceptance for ADNOC schools | Completed | 2022-10-26 |  | 2023-06-23 |  |  | COMPLETE | COMPLETE | 2023-06-23 | Not Received | 2023-07-22 | [5 empty] | 100%
13 | RN-102 | VAPT | ALDAR ACADAMICS & ADNOC SCHOOLS | Sean Faizal | M5- 10% - Retest and report approval for Aldar and ADNOC | Completed | 2022-12-05 |  | 2024-02-05 |  |  | 2024-02-01 | COMPLETE | 2024-02-05 | [5 empty] | in remediation |  | 0%
14 | RN-112 | FireEye | Mashreq | Sean Faizal | M1 - 60% upon product delivery -60 days | Completed | 2022-08-01 |  | 2023-07-07 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
15 | RN-112 | FireEye | Mashreq | Sean Faizal | M2- 40% completion - 60days | Completed | 2022-06-12 |  | 2023-07-07 |  |  | COMPLETE | COMPLETE | 2023-07-07 | Paid | 2023-08-06 | 2023-07-18 |  |  |  |  | 90%
16 | RN-122 | Sailpoint | ADCB - PH2 | Laxmi | M10 and M11, M12 - M12(51-100 Applications) - Sprint 3 Applications (4 Apps) - Go-live/UAT Sign off after 60 days | Delayed | 2022-10-08 | 2023-11-08 |  |  |  | TBD | [9 empty] | 16%
17 | RN-177 | VAPT | ATOM INSURANCE | Sean Faizal | M1 - 50% external Assessment and Report | Completed | 2023-03-15 |  | 2023-06-06 |  |  | COMPLETE | COMPLETE |  | Paid |  |  | NA | NA | NA | NA | 100%
18 | RN-177 | VAPT | ATOM INSURANCE | Sean Faizal | M2: 40% internal assesment and report | Completed | 2023-03-23 |  | 2023-06-06 |  |  | COMPLETE | COMPLETE | 2023-06-06 | Paid | 2023-07-05 | 2023-07-14 | NA | NA | NA | NA | 100%
19 | RN-177 | VAPT | ATOM INSURANCE | Sean Faizal | M3: 10% retesting and signoff | Completed | 2023-05-01 |  | 2023-12-18 |  |  | 2023-12-01 | COMPLETE | 2023-12-18 |  |  |  | Retesting |  | In remediation |  | 0%
24 | RN-191 | ForcePoint, FP | ALDAR | Sean Faizal | M1- Licenses: 100 % of licenses within 30 days from Issuance | Completed | 2023-01-17 | 2023-01-17 | 2023-01-17 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
25 | RN-191 | ForcePoint, FP | ALDAR | Sean Faizal | M2-Services: 50% of Services upon acceptance of project plan and commencement date | Completed | 2023-01-06 | 2023-08-13 | 2023-08-13 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 70%
26 | RN-191 | ForcePoint, FP | ALDAR | Sean Faizal | M3-50% of Services upon sign off and go-live | Completed | 2023-01-23 | 2024-12-10 | 2024-12-10 |  |  | 2024-01-01 | COMPLETE | 2024-01-16 | [7 empty] | 50%
33 | RN-236 | Zscaler | Mashreq | Sean Faizal | 80% upon License Delivery | Completed | 2022-12-31 |  | 2022-12-31 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
34 | RN-236 | Zscaler | Mashreq | Sean Faizal | 20 % Upon PS completion | Completed | 2023-01-03 |  | 2023-07-07 |  |  | COMPLETE | COMPLETE | 2023-07-07 | Paid | 2023-08-06 | 2023-07-18 |  |  |  |  | 90%
35 | RN-237 | VAPT | INTERPLAST | Sean Faizal | M1: External Assessment & Report Submission : 40% | Completed | 2023-03-27 |  | 2023-12-29 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
36 | RN-237 | VAPT | INTERPLAST | Sean Faizal | M2 : Internal Assessment & Report Submission : 50% | Completed | 2023-03-28 |  | 2023-12-29 |  |  | 2023-12-01 | COMPLETE | 2023-12-29 | [7 empty] | 70%
37 | RN-237 | VAPT | INTERPLAST | Sean Faizal | M3: Retesting & Signoff : 10% | Completed | 2023-04-25 |  | 2024-05-31 |  |  | 2024-05-31 | [9 empty] | 0%
43 | RN-252 | VAPT | EPC_2023 | Sean Faizal | 50% External Web Application assessment. | Completed | 2023-05-02 | 2024-10-31 | 2024-10-29 |  |  | 2024-06-14 | [9 empty] | platform is completed, web application 03 out 05 iterations has been completed
44 | RN-252 | VAPT | EPC_2023 | Sean Faizal | 50% External Platform Assessment | Completed | 2023-04-25 |  | 2023-11-23 |  |  | 2023-11-01 | COMPLETE | 2023-11-23 | [7 empty] | 0% | one invoice is done
45 | RN-253 | Checkpoint | AL ZAHRA | Sean Faizal | M1: 100% on project | Completed | NA |  | 2023-06-08 |  |  | COMPLETE | COMPLETE | 2023-06-08 | Paid | 2023-07-07 | 2023-07-18 |  |  |  |  | 100%
60 | RN-297 | Proofpoint | House of Shipping | Sean Faizal | License delivery | Completed |  |  | 2023-06-16 |  |  | COMPLETE | COMPLETE | 2023-06-16 | Paid | 2023-07-15
61 | RN-297 | Proofpoint | House of Shipping | Sean Faizal | Professional Services | Completed |  |  | 2023-06-16 |  |  | COMPLETE | COMPLETE | 2023-06-16 | Paid | 2023-07-15
114 | RN-89 | ForcePoint, FP | AJMAN BANK | Sean Faizal | M1 - Software : 100% on Delivery | Completed | 2022-01-27 |  | 2022-01-27 |  |  | COMPLETE | COMPLETE |  | Paid | [6 empty] | 100%
115 | RN-89 | ForcePoint, FP | AJMAN BANK | Sean Faizal | M2 - DLP + Boldon James (No Payment Milestone) a. M1 - 50% of Services to be invoiced after your confirmation b. Remaining to be invoiced in 2 Milestones of 25% each. M2 – 25% upon Completion of Full roll out of policy c. M3 – 25% upon Sign-off | Completed | 2022-01-27 |  | 2024-04-25 |  |  | NA | [9 empty] | 80%
116 | RN-89 | ForcePoint, FP | AJMAN BANK | Sean Faizal | M3 - Data Classification Consultancy (No Payment Milestone) | Completed | 2022-03-29 |  | 2024-04-25 |  |  | NA | [9 empty] | 100%
117 | RN-89 | ForcePoint, FP | AJMAN BANK | Sean Faizal | M4 - Professional Services : 100% on Signoff AMC : To be Invoiced Annually on Signoff | Completed | 2024-05-10 |  | 2024-05-10 |  |  | 2024-04-26 | COMPLETE | 2024-04-25 | [7 empty] | 38%
149 | RN-356 | Fortinet | Theodor Wille Intertrade FZE_Fortinet Q2 | Sean Faizal | a. Product/License: 100% to be invoiced upon delivery | Completed |  |  | 2023-10-05 |  |  | 2023-10-01 | COMPLETE | 2023-10-05
150 | RN-356 | Fortinet | Theodor Wille Intertrade FZE_Fortinet Q2 | Sean Faizal | b. Services: 50% in advance 50% upon completion dubaiGerman implementation | Completed |  |  | 2023-10-05 |  |  | 2023-10-01 | COMPLETE | 2023-10-05
151 | RN-356 | Fortinet | Theodor Wille Intertrade FZE_Fortinet Q2 | Sean Faizal | C. Services: 50% in advance 50% upon completion German implementation | Completed |  |  | 2023-12-18 |  |  | 2023-12-01 | COMPLETE | 2023-12-18
326 | RN-436 | Tenable.sc | Addof | Sean Faizal | a. 50% to be invoiced in advance | Completed | TBD | TBD | 2024-07-10
327 | RN-436 | Tenable.sc | Addof | Sean Faizal | B. 50% to be invoiced on completioon of implementation | Completed | 2024-06-21 | 2024-09-15 | 2024-09-15
323 | RN-435 | CheckPoint | CWT Logistics | Sean Faizal | a. 50% to be invoiced in advance | Completed | TBD | TBD | 2024-06-10
324 | RN-435 | CheckPoint | CWT Logistics | Sean Faizal | B. 50% to be invoiced on completioon of implementation | Completed | TBD | TBD | 2024-08-19
325 | RN-427 | Fortigate | MBRSG | Sean Faizal | 100% Upon delivery of hardware and liscenses | Completed | 2024-07-10 | 2024-07-10 | 2024-07-13
328 | RN-440 | Nazomi | AD Louvre | Sean Faizal | 100% on delivery of hardware | Completed | 2024-07-10 | 2024-07-10 | 2024-07-10
219 | RN-397 | Forcepoint, RBI | DIB_Forcepoint RBI | Sean Faizal | 100% to be invoiced upon delivery of licenses | Completed |  |  | 2024-02-01 |  |  | 2024-02-01 | Complete | 2024-02-21
212 | RN-401 | SailPoint | Mashreq Sailpoint CR - Dec 23 | Sean Faizal | Payment terms to be agreed mutually | Completed |  |  | 2024-02-16 |  |  | 2024-02-01 | Complete | 2024-02-16
206 | RN-390 | Fortigate | Tawajun Economic Counsil_Fortigate Tech Refresh | Sean Faizal | Hardware delivery | Completed |  |  | 2024-02-23 |  |  | 2024-02-01 | COMPLETE | 2024-02-26
207 | RN-390 | Fortigate | Tawajun Economic Counsil_Fortigate Tech Refresh | Sean Faizal | PS Installation and configuration | Completed |  |  | 2024-05-10 |  |  | 2024-05-15
94 | RN-331 | Checkmarx | Tawajun Industrial Park - Checkmarx 3 man days PS | Sean Faizal | License delivery | Completed |  |  | 2023-05-19 |  |  | 2023-05-01 | COMPLETE | 2023-05-19 | Paid
95 | RN-331 | Checkmarx | Tawajun Industrial Park - Checkmarx 3 man days PS | Sean Faizal | Adoption of Checkmarx solution - 3 man days | Completed |  |  | 2024-02-21 |  |  | 2024-02-01 | COMPLETE | 2024-02-21
59 | RN-289 | VAPT | EMPOWER_2023 (Nov 22) | Sean Faizal | 30 Days upon completion | Completed | 2023-06-07 |  | 2024-05-10 |  |  | 2023-08-01 | COMPLETE | 2023-08-08 | [7 empty] | 20% | Every task is complete , sean is working to get the formal sign-off so that we can invoice
|  | SailPoint | Mashreq - Fieldglass | Pallavi Nair | Milestone 1- IAM -Field glass integration to enable contractors Joiners , Movers , Leavers - 60 % | Completed | 2024-11-25 | 2024-12-09 | 2024-12-09
|  | SailPoint | Mashreq - Fieldglass | Pallavi Nair | Milestone 2- IAM -Field glass integration to enable Field glass automated user life cycle management - 40 % | Completed | 2024-11-25 | 2025-01-22 | 2025-01-22
| RN - 481 | SailPoint | ZAND Bank | Ajinkya | Milestone 1 : 100% on signoff | Completed | 2024-10-01 | 2024-11-13 | 2024-12-11
217 | RN - 470 | Sailpoint | ADCB - SAP SuccessFactor and IAM Enhancement | Ajinkya | Milestone 1 : Design Workshop & Design Documentation Submission - 10% | Completed | 2024-09-13 | 2024-10-30 | 2024-10-30
218 | RN - 470 | Sailpoint | ADCB - SAP SuccessFactor and IAM Enhancement | Ajinkya | Milestone 2 : SAP Success Factor Application Integration (UAT) - 25% | Completed | 2024-10-03 | 2024-11-04 | 2024-11-28
219 | RN - 470 | Sailpoint | ADCB - SAP SuccessFactor and IAM Enhancement | Ajinkya | Milestone 3 : Workflow Enhancement and Exchange UAT - 25% | Completed | 2024-10-28 | 2024-11-04 | 2024-11-28
220 | RN - 470 | Sailpoint | ADCB - SAP SuccessFactor and IAM Enhancement | Ajinkya | Milestone 4: SAP Success factor Application Integration PROD - 20% | Completed | 2024-10-29 |  | 2025-02-06
221 | RN - 470 | Sailpoint | ADCB - SAP SuccessFactor and IAM Enhancement | Ajinkya | Milestone 5: Workflow Enhancement and Exchange PROD - 20% | Completed | 2024-10-30 |  | 2025-02-06
260 | RN-502 | LogRhythm | Tawazun - LogRhythm | Ajinkya | a. Licenses & Services: 100% to be invoiced upon License & Hardware Delivery | completed | 2025-01-02 | 2025-01-10 | 2025-01-20
263 | RN-508 | Forcepoint | UBL Forcepoint Hardware refresh | Ajinkya | a. Hardware: To be invoiced upon Hardware Delivery in UAE | Completed | 2025-01-15 | 2025-01-30 | 2025-01-30
265 | RN-522 | Picus Security | Ajman Bank - Picus Security | Ajinkya | a. Licenses: To be invoiced upon License Delivery | Completed | 2024-12-30 | 2024-12-30 | 2024-12-30
237 | RN - 478 | Audit | Intigral GRC | Ajinkya | To be Invoiced upon receipt of LPO | Completed | 2024-09-11 | 2024-09-11 | 2024-09-11 | [12 empty] | 100%
247 | RN - 499 | Net Sec | Nextcare Palo Alto_Oman | Ajinkya | 100% upon license delivery | Completed | 2024-11-27 |  | 2024-12-09 | [12 empty] | 100%
| RN-446 | SailPoint | MAshreq Bank sailpoint- phase 3 | Pallavi Nair | R1 Go Live and Stabilisation Signoff - 30% | Completed | 2024-07-25 | 2025-01-22 | 2025-01-22
| RN-446 | SailPoint | MAshreq Bank sailpoint- phase 3 | Pallavi Nair | R2 Go Live and Stabilisation Signoff - 25% | Completed | 2024-12-16 | 2025-02-04 | 2024-12-10
| RN-446 | SailPoint | MAshreq Bank sailpoint- phase 3 | Pallavi Nair | R3 Go Live and Stabilisation Signoff - 25% | Completed | 2024-12-16 | 2025-01-22 | 2025-01-22
| RN-446 | SailPoint | MAshreq Bank sailpoint- phase 3 | Pallavi Nair | Final Payment on Delivery Closure Report Sign Off - 20% | Completed | 2024-12-16 | 2025-04-18 | 2025-04-04
Note on Q25: CS Rao: Pending due to contract signagture
Note on Q26: CS Rao: Pending due to contract signagture
Note on F89: CS Rao: Update teh milestones as per the data given by Rekha in slack
Note on D161: CS Rao: 10% given as Performance Guarantee - 99999
Note on D200: CS Rao: 10% given as Performance Guarantee - 99999
Note on P253: CS Rao: Lincense duration issue
Note on P254: CS Rao: License duration issue

## License renewal
72 | New | Opswat | NW & Sec | 2024-06-24 | RNS | Mashreq Opswat | License renewal | Mashreq Bank |  |  | GREEN | Vignesh | Low | Completed |  |  | License delivery, need to confirm with Sean on whether it is a renewal License delivered to customer on 28th Jun
14 | RN-xxx | EDR | IVM |  |  | DAMAAC Properties | Liscense Renewal | DAMAAC |  | Bibinu Ajith | GREEN | Sean Faizal |  | Not Started |  | 0%
26 | VENDOR | Akamai | NW & Sec | Vendor | Americana Akamai AAP |  | Americana |  | Faizan Javed | GREEN |  | Medium | On Track |  | 2024-05-01
61 | New |  |  |  | AAE_ Crowdstrike EDR Renewal

## AMC Register (hidden)
PROJECT MANAGEMENT LOG TEMPLATE
PROJECT REGISTER
The PROJECT Identification portion of this table will automatically populate to the Financial Data, Deliverables and Performance, and Risk Register tabs within this workbook.
PROJECT DATA | [11 empty] | ACCOUNT DATA |  | PROJECT MANAGEMENT
NO. | PROJECT ID | Statius | Status | Project Type | PROJECT NAME | Type of Payment | Suppot By | Start Date | CUSTOMER NAME | CUSTOMER SPOC NAME | CUSTOMER SPOC EMAIL | ACCOUNT MANAGER NAME | ACCOUNT HEALTH | INTERNAL PROJECT MANAGER | Status | Scope & Support Model | SLAs | Total Health Checks | HC Completed | HC Due | Open Health Checks | Closed Health Checks | No. Incident Tickets | Open Incident Tickets | Closed Incident Tickets | START DATE | END DATE | Payment for | Term | Billing Forecast Month | Biling Status | Invoice Date | Billing Amount | Payment Satus | Forecast Revenue | Paid Date
1 | RN-146 | check count of HC |  | Checkpoint | Intigral Middle East-Checkpoint |  | RNS |  | Intigral Middle East | Selva | Selva.Rathinam@intigral.net | Ishan Arora | GREEN | Pallavi Nair | On Track | 1 HC and 7 Incidents |  | 2 |  |  | 1 | 1 | 7 | 0 | 0 | 2023-02-20 | 2024-02-19 |  |  |  | Complete |  |  | Paid
2 | RN-165 | date check |  | Barracuda | Al Dhaffra - Barracuda WAF |  | RNS |  | Al Dhaffra Insurance | Alaa Saad | alaa.saad@aldhafrainsurance.ae | Bibinu | GREEN | Pallavi Nair | On Track |  |  | 2 |  |  | 1 | 1 | 4 | 0 | 0 | 2021-06-30 | 2024-06-29 |  |  |  | Complete |  | 33500 | Paid
3 | RN-169 | add it |  | Solarwinds | MBRHE Solarwinds |  | RNS |  | MBRHE | Mohammad Amjad | mamjad@mbrhe.ae | Ishan Arora | GREEN | Pallavi Nair | On Track | 4 HCs and 6 Incidnets |  | 4 |  |  | 1 | 1 | 6 | 0 | 1 | 2023-03-31 | 2024-03-31 |  |  |  | Complete |  |  | Paid
4 | RN-183 | check count of HC, inc |  | Solarwinds | PIH - Solarwinds |  | RNS |  | Power International Holding | Ahmad Nabeel | a.nabeel@powerholding-intl.com | Brejesh | GREEN | Pallavi Nair | On Track | HC and Inc ticket info to be checked |  | 4 |  |  | 2 | 2 | 10 | 0 | 6 | 2022-12-28 | 2023-12-27 |  |  |  | Complete |  | 10000 | Not Paid
5 | RN-187 | check count of HC, inc |  | Paloalto | MBRHE-PaloAlto |  | RNS |  | MBRHE | Mohammad Amjad | mamjad@mbrhe.ae | Ishan Arora | GREEN | Pallavi Nair | On Track | 12 PM HCs and 8 Incidnets for 3 yrs |  | 2 |  |  | 1 | 1 | 4 | 1 | 1 | 2021-03-25 | 2024-03-24 |  |  |  | Complete |  | 36245.65 | Paid
6 | RN-218 | date check |  | ivanti | OQ Trading - Ivanti |  | RNS |  | OQ Trading | Aathif Niyas | mohamed.aathif@oq.com | Ranjith George | GREEN | Pallavi Nair | On Track |  |  | 4 |  |  | 3 | 1 | 6 | 0 | 0 | 2023-01-11 | 2024-01-11 |  |  |  | Complete |  | 12738.46 | Paid
7 | RN-220 | check count of HC, inc |  | Solarwinds | Qterminals-Solarwinds |  | RNS |  | Qterminals | Akbar Puzhakkalakath | apuzhakkalakth@QTerminals.com | Brejesh | GREEN | Pallavi Nair | On Track | Unlimited incident support. Billing on Qtrly - 12 invoices. Two invoices will be due. PGC to check with acct mgr on the support tickets |  | 4 |  |  | 2 | 2 | 8 | 0 | 1 | 2021-03-10 | 2024-03-09 |  |  |  | 2023-08-01 |  | 39000
8 | New | To be discussed with Nitesh |  | Sailpoint | ADCB-Sailpoint |  |  | 2023-08-04 | ADCB |  |  | Sagar Chopra |  | Pallavi Nair | On Track | 8 Incidents | [9 empty] | 2023-08-04 | 2024-12-31 | [5 empty] | 36800
10 | RN-265 | Talk to Sean |  | Forcepoint Cloud Migration | Aldar-Forcepoint Cloud Migration |  | RNS | Linked with RN-191 | Aldar |  |  | Bibinu |  | Pallavi Nair | On Track | 6 Break Down Calls / Incident Support (Every Year) • 2 Preventive Maintenance Support (Every Year) |  | 2 |  |  |  |  | 6 |  |  | 2022-12-28 | 2023-12-27 |  |  |  | No seprate invoice needed. Part of Services
| New | New AMC | Started | Forcepoint | Aldar Properties PJSC_Dec 23 |  | RNS | 2023-12-06 |  |  |  | Bibinu |  | Sean Faizal | On Track | 6 Incidents for 15 months | [6 empty] | 6 |  |  | 2023-12-28 | 2025-03-27 | [5 empty] | 573534
11 | RN-267 | AMC not started. Check wth dates with Bibinu |  | Sailpoint | DOH-Sailpoint |  | RNS |  | DOH |  |  | Bibinu |  | Pallavi Nair | On Track | 1 HC and 7 Incidents per year | [9 empty] | 2023-01-01 | 2024-06-28 |  | Y2 | 2023-06-01 | Complete | 2023-06-12
12 | RN-268 | AMC not started. Check wth dates with Nitesh |  | Sailpoint | QIB-Sailpoint |  | RNS |  | QIB |  |  | Brejesh |  | Pallavi Nair | On Track | 1 HC and 9 Incidents per year |  | 1 |  |  |  |  | 7 |  |  | 2021-09-26 | 2024-09-25
13 | New | PROJECT IS YET TO BE CLOSED, No of tickets to be checked by Pallavi |  | Fortinet | FortiGate Firewall 100F X 2_2023+ FortiAnalyser APL |  | RNS |  | Gargash Group | Bilal Lodhia |  | Ranjit George Mathew |  | Pallavi Nair | Not Started | 3 Years from PS Sign-off. AMC cost is included in the PS |  | 2 |  |  |  |  | 4
14 | RN-164 |  |  | ForcePoint, FP | UBL - Forcepoint Web Security |  | RNS |  | UBL - UAE, Bahrain & Qatar | Talha Ahmed Seddiqi | talha.siddiqui@ubl.com.pk | Ishan Arora | GREEN | Pallavi Nair | On Track |  |  | 4 |  |  | 3 | 1 | 4 | 0 | 4 | 2023-03-22 | 2024-03-21 |  |  |  | Complete |  |  | Paid
15 | RN-213 |  |  | Forcepoint DLP Boldenjames | Intigral-Forcepoint and Boldonjames |  | RNS |  | Intigral Middle East | Selva | Selva.Rathinam@intigral.net | Ishan Arora | GREEN | Pallavi Nair | On Track |  |  | 2 |  |  | 1 | 1 | 4 | 1 | 2 | 2023-02-21 | 2024-02-20 |  |  |  | Complete |  |  | Paid
16 | RN-149 |  |  | Fortigate | MOFAIC Fortigate |  | RNS |  | MOFAIC |  |  | Bibinu | GREEN | Pallavi Nair | Completed |  |  | 2 | Y1 - H1 & H2 |  | 1 | 1 | 4 |  |  | 2021-12-13 | 2022-12-12 |  |  | 2022-12-01 | Complete |  | 8227.44 | Paid
| RN-149 |  |  | Fortigate | MOFAIC Fortigate |  |  |  | MOFAIC |  |  | Bibinu | GREEN | Pallavi Nair | Completed |  |  | 2 | Y2 - H1 & H2 |  | 1 | 1 | 4 |  |  | 2022-12-13 | 2023-12-12 |  |  | 2023-09-01 | Complete | 2023-09-13 | 8227.44
| RN-149 |  |  | Fortigate | MOFAIC Fortigate |  |  |  | MOFAIC |  |  | Bibinu | GREEN | Pallavi Nair | On Track |  |  | 2 |  | Y3 - H1 & H2 | 1 | 1 | 4 |  |  | 2023-12-13 | 2024-12-12 |  |  | 2024-12-01 |  |  | 8227.44
17 | RN-151 |  |  | ivanti | Sharjah Islamic Bank-Ivanti |  | RNS |  | SIB |  |  | Ishan Arora | GREEN | Pallavi Nair | Completed |  |  |  | H123 |  |  | 0 | 1.5 | 0 |  | 2023-03-16 | 2024-03-15 |  |  |  | Complete |  | 1932 | Paid
| RN-151 |  |  | ivanti | Sharjah Islamic Bank-Ivanti |  |  |  | SIB |  |  | Ishan Arora | GREEN | Pallavi Nair | On Track |  |  |  | H2 23 |  |  | 0 | 1.5 | 0 |  | 2023-03-16 | 2024-03-15 |  |  | 2023-08-01 |  |  | 1932
18 | RN-157 |  |  | Sailpoint | Axa-Sailpoint |  | RNS |  | AXA | Niyaj Khan | Niyaj.khan.ext@gig-gulf.com | Sagar Chopra | GREEN | Pallavi Nair | On Track | 8 Incidents | [6 empty] | 8 |  |  | 2022-11-05 | 2023-11-04 |  |  | 2022-12-01 | Complete |  | 38640 | Paid
19 | RN-159 |  |  | Desktops,Printers and Firewall | Apex Fund Services Dubai |  | RNS |  | Apex Fund Services Dubai | Sadashiv Chavan | sadashiv.chavan@apexgroup.com | Rohit Suresh Save | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  | 1 | 0 | 18 | 0 | 5 | 2022-12-13 | 2023-12-12 |  |  | 2023-10-01 |  |  | 3333.75
20 | RN-160 |  |  | Desktops,Printers and Firewall | Apex Fund Services Abu Dhabi |  | RNS |  | Apex Fund Services Abu Dhabi | Sadashiv Chavan | sadashiv.chavan@apexgroup.com | Rohit Suresh Save | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  | 1 | 0 | 18 | 0 | 9 | 2022-12-13 | 2023-12-12 |  |  | 2023-10-01 |  |  | 3333.75
21 | RN-166 |  |  | Fortigate | Al Dhaffra - Fortigate Firewall + FortiAnalyzer |  | RNS |  | Al Dhaffra Insurance | Alaa Saad | alaa.saad@aldhafrainsurance.ae | Bibinu | GREEN | Pallavi Nair | On Track |  |  | 2 |  |  | 1 | 1 | 4 | 0 | 0 | 2021-06-30 | 2024-06-29 |  |  |  | Complete |  | 18500 | Paid
22 | RN-182 | Renewed on 24 Nov 23 |  | CyberArc | Oman / Sukoon Insurance - Cyberark | License cost | RNS |  | Oman / Sukoon Insurance | Jameel Ahamed | Jameel.Ahamed@sukoon.com | Ishan Arora | GREEN | Pallavi Nair | On Track |  |  | 2 |  |  |  |  | 6 |  |  | 2023-11-24 | 2024-11-23 |  |  | 2023-11-01 |  |  | 55790
| RN-182 | Renewed on 24 Nov 23 |  | CyberArc | Oman / Sukoon Insurance - Cyberark | AMC cost | RNS |  | Oman / Sukoon Insurance | Jameel Ahamed | Jameel.Ahamed@sukoon.com | Ishan Arora | GREEN | Pallavi Nair | On Track |  |  | 2 |  |  |  |  | 6 |  |  | 2023-11-24 | 2024-11-23 |  |  | 2023-11-01 |  |  | 11040
23 | RN-196 |  |  | Solarwinds | Dukhan Bank -Solarwinds |  | RNS |  | Dukhan Bank | Imran Ansari | imran@dukhanbank.com | Brejesh | GREEN | Pallavi Nair | On Track |  |  | 4 |  |  | 3 | 1 | 2 | 0 | 2 | 2022-11-12 | 2023-11-12 |  |  |  | Complete |  | 11500 | Paid
24 | RN-201 |  |  | McAfee | ADAA - Mcafee |  | RNS |  | ADAA | Mariam Mohamed | Mariam.Alhammadi@adaa.gov.ae | Haythem | GREEN | Pallavi Nair | On Track |  |  | 4 |  |  | 3 | 1 | 6 | 1 | 0 | 2023-01-01 | 2023-12-31 |  |  |  | Complete |  | 12492.5 | Paid
24 | RN-214 | AMC Renewed in Dec 23 | Started | FP, ForcePoint | Alef Education - Forcepoint DLP |  | RNS | 2023-12-13 | Alef Education | Srikant | srikant.dasondhi@alefeducation.com | Bibinu | GREEN | Pallavi Nair | On Track | 2 HCs and 4 Incidents |  | 2 |  |  |  |  | 4 |  |  | 2023-12-14 | 2024-12-13 | [5 empty] | 231999
26 | RN-204 | Proposal to be checked |  | McAfee | Mashreq - McAfee |  | RNS |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Track |  |  | 2 |  |  |  |  | 12 |  |  | 2023-06-28 | 2024-06-27 |  |  |  | Complete |  | 38640 | Paid
27 | RN-225 | Proposal to be checked |  | Zscaler | Mashreq - zscaler |  | RNS |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Hold |  |  | 2 |  |  |  |  | 8 |  |  | 2023-01-01 | 2023-12-31 |  |  |  | Complete |  | 43000 | Paid
28 | RN-148 | Proposal to be checked |  | ivanti | Ajman Bank PJSC - ivanti |  | RNS |  | Ajman Bank PJSC | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | RED | Sean Faizal | On Track | 2 HCs and 4 Incidents |  | 2 |  |  | 2 | 0 |  |  |  | 2022-01-14 | 2023-01-14 |  |  |  | Complete |  | 32780 | Paid
29 | RN-210 | Proposal to be checked |  | ForcePoint-DLP | Ajman Bank - ForcePoint-DLP |  | RNS |  | Ajman Bank | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | RED | Sean Faizal | On Hold |  |  | 4 |  |  | 4 | 0 |  |  |  | 2021-12-28 | 2025-02-27 |  |  |  | Complete
30 | RN-192 |  |  | ForcePoint, Web Security | DIB - Forceoint |  | RNS |  | DIB | Mohammed Jibran Afzal | mohammed.jibran@dib.ae | Sagar Chopra | GREEN | Sean Faizal | On Track | Forcepoint - 12 INC, 4 HCS WEB SECURITY - Unlimited INCs, 4 HCs 1 Jan 23 to 31 Dec 23 |  | 4 |  |  | 2 | 2 | 12 for FP & Unlimited for Web Sec |  |  | 2023-01-01 | 2023-12-31 |  |  |  | Complete |  | 326000 | Paid
31 | RN-193 |  |  | Tripwire | DIB - Tripwire |  | RNS |  | DIB | Mohammed Jibran Afzal | mohammed.jibran@dib.ae | Sagar Chopra | GREEN | Sean Faizal | On Track | 8 Incidents only, no preventive HCs | [6 empty] | 8 |  |  | 2023-01-01 | 2023-12-31 |  |  |  | Complete |  | 29440 | Paid
32 | RN-302 |  |  | Sailpoint | DIB - Sailpoint (Onsite Deployment - Niraj) |  | RNS |  | DIB | NA | NA | Sagar Chopra | AMBER | Sean Faizal | Completed | [10 empty] | 2023-05-28 | 2023-06-28 |  |  | 2023-07-01 | Complete |  | 30912 | Not Received | 2023-08-13
| RN-302 |  |  | Sailpoint | DIB - Sailpoint (Onsite Deployment - Niraj) |  |  |  | DIB | NA | NA | Sagar Chopra | AMBER | Sean Faizal | Completed | [10 empty] | 2023-06-28 | 2023-07-28 |  |  | 2023-08-01 | Complete | 2023-08-18 | 30912
| RN-302 |  |  | Sailpoint | DIB - Sailpoint (Onsite Deployment - Niraj) |  |  |  | DIB | NA | NA | Sagar Chopra | AMBER | Sean Faizal | Completed | [10 empty] | 2023-07-28 | 2023-08-28 |  |  | 2023-10-01 |  |  | 30912
| RN-302 |  |  | Sailpoint | DIB - Sailpoint (Onsite Deployment - Niraj) |  |  |  | DIB | NA | NA | Sagar Chopra | AMBER | Sean Faizal | Completed | [10 empty] | 2023-08-28 | 2023-09-28 |  |  | 2023-10-01 |  |  | 30912
| RN-302 |  |  | Sailpoint | DIB - Sailpoint (Onsite Deployment - Niraj) |  |  |  | DIB | NA | NA | Sagar Chopra | AMBER | Sean Faizal | On Track | [10 empty] | 2023-09-28 | 2023-10-28 |  |  | 2023-11-01 |  |  | 30912
| RN-302 |  |  | Sailpoint | DIB - Sailpoint (Onsite Deployment - Niraj) |  |  |  | DIB | NA | NA | Sagar Chopra | AMBER | Sean Faizal | Not Started | [10 empty] | 2023-10-28 | 2023-11-28 |  |  | 2023-12-01 |  |  | 30912
33 | RN-200 |  |  | ALL PRODUCTS | DLD CONSOLIDATED (Barracuda-WAF&LB, ARCON, PALO-ALTO,IBM,NETCRUNCH,FORTINET) |  | RNS |  | DLD | Rambhul Singh | rambhul.singh@dubailand.gov.ae | Sagar Chopra | GREEN | Sean Faizal | Delayed |  |  | 24 |  |  | 11 | 9 |  |  |  | 2022-12-26 | 2023-12-26 |  |  | 2023-03-01 | Complete |  |  | Paid
| RN-200 |  |  | ALL PRODUCTS | DLD CONSOLIDATED (Barracuda-WAF&LB, ARCON, PALO-ALTO,IBM,NETCRUNCH,FORTINET) |  |  |  | DLD | Rambhul Singh | rambhul.singh@dubailand.gov.ae | Sagar Chopra | GREEN | Sean Faizal | Delayed |  |  | 24 |  |  | 11 | 9 |  |  |  | 2022-12-26 | 2023-12-26 |  |  | 2023-06-30 | Complete |  | 97363.08 | Not Received
| RN-200 |  |  | ALL PRODUCTS | DLD CONSOLIDATED (Barracuda-WAF&LB, ARCON, PALO-ALTO,IBM,NETCRUNCH,FORTINET) |  |  |  | DLD | Rambhul Singh | rambhul.singh@dubailand.gov.ae | Sagar Chopra | GREEN | Sean Faizal | Delayed |  |  | 24 |  |  | 11 | 9 |  |  |  | 2022-12-26 | 2023-12-26 |  |  | 2023-10-01 |  |  | 97363.08
| RN-200 |  |  | ALL PRODUCTS | DLD CONSOLIDATED (Barracuda-WAF&LB, ARCON, PALO-ALTO,IBM,NETCRUNCH,FORTINET) |  |  |  | DLD | Rambhul Singh | rambhul.singh@dubailand.gov.ae | Sagar Chopra | GREEN | Sean Faizal | Delayed |  |  | 24 |  |  | 11 | 9 |  |  |  | 2022-12-26 | 2023-12-26 |  |  | 2023-12-30 |  |  | 97363.08
34 | RN-121 | Renewed in Dec 23 |  | Tripwire | Mashreq - Tripwiire |  | RNS |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Track | 4 HCs and unlimited incident support | 4 HCs and unlimited incident support | 4 | [7 empty] | 2024-01-01 | 2024-12-31 | [5 empty] | 275000
35 | RN-264 |  |  | Opswat | Mashreq - Opswat |  | Vendor |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Hold |  |  | 2 |  |  |  |  | 6 |  |  | 2023-08-23 | 2024-08-22 |  |  |  | Complete |  | 33120 | Paid
36 | RN-225 |  |  | Zscaler | Mashreq - zscaler |  |  |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Hold |  |  | 2 |  |  |  |  | 8 |  |  | 2024-01-01 | 2024-12-31 |  |  | 2024-01-01 |  |  | 43000
| RN-225 |  |  | Zscaler | Mashreq - zscaler |  |  |  | Mashreq | Ramesh Ponram | RameshPo@mashreq.com | Sagar Chopra | GREEN | Sean Faizal | On Hold |  |  | 2 |  |  |  |  | 8 |  |  | 2025-01-01 | 2025-12-31 |  |  | 2025-01-01 |  |  | 43000
37 | RN-120 |  |  | Sailpoint | Tawazun Economic Council |  | RNS | 2023-05-16 | Tawazun economic Council | Mathew Rajesh |  | Ishan Arora | GREEN | Sean Faizal | On Track | AMC including 4 onsite visits | [6 empty] | 4 |  |  | 2023-05-16 | 2024-05-15 |  |  | 2023-12-01 | Complete |  | 15546
38 | RN-211 |  |  | Tripwire | Ajman Bank Tripwire |  | RNS |  | Ajman Bank | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | RED | Sean Faizal | On Track | 4 HCs and unlimited incidents |  | 4 |  |  | 3 | 1 | Unlimited |  |  | 2023-03-01 | 2024-02-29 |  |  |  | Complete |  |  | Paid
39 | RN-142 |  |  | McAfee | Ajman Bank McAfee |  | RNS |  | Ajman Bank | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | RED | Sean Faizal | On Track | 2 HCs and 8 incident |  | 2 |  |  | 1 | 1 | 8 |  |  | 2022-12-18 | 2023-12-17 |  |  |  | Complete |  |  | Paid
| RN-142 | Start from 18 Dec 23 |  | McAfee | Ajman Bank McAfee |  | RNS |  | Ajman Bank | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | RED | Sean Faizal | On Track | Licenses and Support - 4 HCs and 6 Incidnets |  | 2 |  |  | 1 | 1 | 8 |  |  | 2023-12-18 | 2024-12-31 |  |  | 2023-12-01 |  |  | 144732
40 | RN-148 |  |  | ivanti | Ajman Bank PJSC - ivanti |  |  |  | Ajman Bank PJSC | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | RED | Sean Faizal | On Track | 2 HCs and 4 Incidents |  | 2 |  |  | 2 | 0 |  |  |  | 2023-01-15 | 2024-01-14 |  |  | 2024-01-01 |  |  | 32780
| RN-148 |  |  | ivanti | Ajman Bank PJSC - ivanti |  |  |  | Ajman Bank PJSC | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | RED | Sean Faizal | On Track | 2 HCs and 4 Incidents |  | 2 |  |  | 2 | 0 |  |  |  | 2024-01-14 | 2025-01-14 |  |  | 2025-01-01 |  |  | 32780
41 | RN-144 |  |  | Tripwire | Emirates Airlines - Tripwire | Enterprise Support | RNS |  | Emirates Airlines | Durgesh Kumar | durgeshkumar.saraswat@dnata.com | Ishan Arora | GREEN | Sean Faizal | On Track | 2 HCs and 4 Incidents |  | 2 |  |  |  |  | 4 |  |  | 2023-11-14 | 2024-11-13 |  |  | 2023-11-01 |  |  | 75640
| RN-144 |  |  | Tripwire | Emirates Airlines - Tripwire | AMC cost | RNS |  | Emirates Airlines | Durgesh Kumar | durgeshkumar.saraswat@dnata.com | Ishan Arora | GREEN | Sean Faizal | On Track | 2 HCs and 4 Incidents |  | 2 |  |  |  |  | 4 |  |  | 2023-11-14 | 2024-11-13 |  |  | 2023-11-01 |  |  | 7360
42 | RN-217 |  |  | ForcePoint, FP | Emrill - Forcepoint DLP and BJM |  | RNS |  | Emrill | Atif Riaz | Atif.Riaz@emrill.com | Rohit Suresh Save | AMBER | Pallavi Nair | On Track |  |  | 2 |  |  | 2 | 0 | 4 | 0 | 1 | 2021-12-23 | 2024-12-22 |  |  |  | Complete |  | 26496 | Paid
43 | RN-280 |  |  | Tenable | DMT - Tenable |  | RNS |  | DMT | Reshma Bharathan | Reshma.Bharathan@dmt.gov.ae | Bibinu | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  | 1 | 0 | 8 | 0 | 2 | 2022-12-22 | 2023-12-22 |  |  |  | Complete |  | 20000 | Paid
44 | RN - 272 |  |  | Checkpoint | Brandfolio-Checkpoint |  | RNS |  | Brandfolio | Jacob John | jacob@brand-foliollc.com | Ranjith George | GREEN | Pallavi Nair | On Track |  |  | 2 |  |  | 1 | 1 | 4 | 0 | 1 | 2023-03-28 | 2024-03-27 |  |  |  | Complete |  | 5041 | Paid
45 | RN-255 |  |  | Proofpoint | EPC-Proofpoint |  | RNS |  | EPC | Jinson Papachan | jinson@epc.ae | Ranjith George | GREEN | Pallavi Nair | On Track |  |  | 4 |  |  | 3 | 1 | Remote incident support | 0 | 0 | 2023-02-09 | 2024-02-08 |  |  |  | Complete | 2023-07-19 | 5888 |  | 2023-08-18
46 | RN-162 |  |  | Checkpoint | Al Shirawi / Global Shipping and Logistics - Checkpoint |  | RNS |  | Al Shirawi / Global Shipping and Logistics | Uma Sanker | uma.sanker@alshirawi.ae | Sagar Chopra | GREEN | Pallavi Nair | On Track | Create a new contract in Zoho. 4 Incidents, 2 HCs. Old Project is RN-162 |  | 2 |  |  |  |  | 4 |  |  | 2023-06-15 | 2024-06-14 |  |  |  | Complete | 2023-08-21 | 82950 |  | 2023-09-20
47 | RN-221 |  |  | Lepide | Human Resource Authority-Lepide |  | Vendor |  | HRA | Anas | Anas.Shahi@hra.gov.ae | Haythem | RED | Pallavi Nair | Delayed |  |  | 4 |  |  | 4 | 0 | NA |  |  | 2020-10-26 | 2023-10-21 |  |  |  | Complete |  | 16560 | Paid
48 | RN-145 | Started after PS |  | Checkpoint | Arcadia School - Checkpoint |  | RNS |  | Arcadia School | Uma Sankar | uma.sanker@alshirawi.ae | Ishan Arora |  | Pallavi Nair | On Track |  |  | 1 |  |  |  |  | 3 |  |  | 2023-10-06 | 2024-10-05 |  |  |  | Complete
49 | RN-269 |  |  | Sailpoint | PHCC-Sailpoint |  | RNS |  | PHCC |  |  |  |  | Pallavi Nair | On Track | 1 HC per year, 7 incidents |  | 1 |  |  |  |  | 7 |  |  | 2023-03-01 | 2026-02-28 |  |  | 2023-03-01 | Complete | 2023-03-08
50 | RN-256 |  |  | Sailpoint | SIB-100 HR Support |  | RNS |  | SIB | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | Completed | [10 empty] | 2022-10-13 | 2023-01-13 |  |  | 2022-10-01 | COMPLETE |  | 4856.25 | Paid
| RN-256 |  |  | Sailpoint | SIB-100 HR Support |  |  |  | SIB | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | Completed | [10 empty] | 2023-01-14 | 2023-04-14 |  |  | 2023-02-01 | COMPLETE |  | 4856.25 | Paid
| RN-256 |  |  | Sailpoint | SIB-100 HR Support |  |  |  | SIB | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | Completed | [10 empty] | 2023-04-17 | 2023-07-16 |  |  | 2023-04-01 | COMPLETE |  | 4856.25 | Paid
| RN-256 |  |  | Sailpoint | SIB-100 HR Support |  |  |  | SIB | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | Completed | [10 empty] | 2023-07-19 | 2023-10-20 |  |  | 2023-07-01 | COMPLETE | 2023-07-06 | 4856.25 | Not Received | 2023-08-05
51 | RN-281 |  |  | Fortigate | Support-Dubai Sports Council (DSC) - FortiGate |  | RNS | [6 empty] | Vignesh | On Track | 2 HCs and 2 Incidents in a year |  | 2 |  |  |  |  | 2 |  |  | 2023-08-01 | 2024-07-31 |  |  |  | COMPLETE
52 | RN-269 |  |  | Sailpoint | PHCC-Sailpoint |  |  |  | PHCC |  |  |  |  | Pallavi Nair | On Track | 1 HC per year, 7 incidents |  | 1 |  |  |  |  | 7 |  |  | 2023-03-01 | 2026-02-28 |  |  | 2024-03-01 |  |  | 6000
| RN-269 |  |  | Sailpoint | PHCC-Sailpoint |  |  |  | PHCC |  |  |  |  | Pallavi Nair | On Track | 1 HC per year, 7 incidents |  | 1 |  |  |  |  | 7 |  |  | 2023-03-01 | 2026-02-28 |  |  | 2025-03-01 |  |  | 6000
53 | RN-205 / 332 |  |  | Sailpoint | QAPCO-Sailpoint |  | RNS |  | QAPCO |  |  | Brejesh |  | Vignesh | On Track | 6 incidents and 1 HC in a year |  | 1 |  |  |  |  | 6 |  |  | 2023-08-21 | 2024-08-20 | Q1 |  | 2023-10-01 | COMPLETE | 2023-10-18 | 11981
| RN-205 / 332 |  |  | Sailpoint | QAPCO-Sailpoint |  | RNS |  | QAPCO |  |  | Brejesh |  | Vignesh | On Track | 6 incidents and 1 HC in a year |  | 1 |  |  |  |  | 6 |  |  | 2023-08-21 | 2024-08-20 | Q2 |  | 2023-11-01 | COMPLETE | 2023-11-08 | 11981
| RN-205 / 332 |  |  | Sailpoint | QAPCO-Sailpoint |  | RNS |  | QAPCO |  |  | Brejesh |  | Vignesh | On Track | 6 incidents and 1 HC in a year |  | 1 |  |  |  |  | 6 |  |  | 2023-08-21 | 2024-08-20 | Q3 |  | 2024-02-01 |  |  | 11981
| RN-205 / 332 |  |  | Sailpoint | QAPCO-Sailpoint |  | RNS |  | QAPCO |  |  | Brejesh |  | Vignesh | On Track | 6 incidents and 1 HC in a year |  | 1 |  |  |  |  | 6 |  |  | 2023-08-21 | 2024-08-20 | Q4 |  | 2024-05-01 |  |  | 11981
54 | RN-215 |  |  | CyberArc | Damac-Cyberark |  | RNS |  | Damac | Rajesh Narayan | Rajesh.Narayanan@damacgroup.com | Bibinu | RED | Pallavi Nair | Not Started | 2 HC and 4 Incidents |  | 2 |  |  | 4 | 0 | 4 |  |  | 2023-05-12 | 2024-05-11 |  |  |  | Complete
55 | RN-311 |  |  | Sailpoint | SIB new 100 hr support |  | RNS |  |  | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | On Track | Q1 (July) | [9 empty] | 2023-07-01 | 2023-09-01 |  |  | 2023-07-01 | COMPLETE | 2023-07-12 | 4856.25 |  | 2023-08-11
| RN-311 |  |  | Sailpoint | SIB new 100 hr support |  |  |  |  | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | On Track | Q2 | [9 empty] | 2023-10-01 | 2023-12-01 |  |  | 2023-10-01 | COMPLETE |  | 4856.25
| RN-311 |  |  | Sailpoint | SIB new 100 hr support |  |  |  |  | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | On Track | Q3 | [9 empty] | 2024-01-01 | 2024-03-01 |  |  | 2024-01-01 | COMPLETE |  | 4856.25
| RN-311 |  |  | Sailpoint | SIB new 100 hr support |  |  |  |  | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | On Track | Q4 | [9 empty] | 2024-04-01 | 2024-06-01 |  |  | 2024-04-01 |  |  | 4856.25
56 | RN-243 |  |  | Ivanti SD | Tawajun Industrial Park - Mindware |  | Vendor |  |  |  |  | Ishan |  | Sean Faizal | On Track | RNS-AMC : Local Support - Professional Service (5 Man Days/40 hours excluding quarterly health Check-up) and 4 Quarterly Health Checks |  | 2 (Mindware - 3 man days) and 2 (RNS - 5 man days) | [7 empty] | 2023-03-16 | 2024-03-15 | Q1 |  | 2023-08-01 | Complete | 2023-08-14 | 2625
57 | RN-243 |  |  | Ivanti SD | Tawajun Industrial Park - Mindware | [6 empty] | Ishan |  | Sean Faizal | On Track | RNS-AMC : Local Support - Professional Service (5 Man Days/40 hours excluding quarterly health Check-up) and 4 Quarterly Health Checks |  | 2 (Mindware - 3 man days) and 2 (RNS - 5 man days) | [7 empty] | 2023-03-16 | 2024-03-15 | Q2 |  | 2023-09-01 |  |  | 2625
| RN-243 |  |  | Ivanti SD | Tawajun Industrial Park - Mindware | [6 empty] | Ishan |  | Sean Faizal | On Track | RNS-AMC : Local Support - Professional Service (5 Man Days/40 hours excluding quarterly health Check-up) and 4 Quarterly Health Checks |  | 2 (Mindware - 3 man days) and 2 (RNS - 5 man days) | [7 empty] | 2023-03-16 | 2024-03-15 | Q3 |  | 2023-12-01 |  |  | 2625
| RN-243 |  |  | Ivanti SD | Tawajun Industrial Park - Mindware | [6 empty] | Ishan |  | Sean Faizal | On Track | RNS-AMC : Local Support - Professional Service (5 Man Days/40 hours excluding quarterly health Check-up) and 4 Quarterly Health Checks |  | 2 (Mindware - 3 man days) and 2 (RNS - 5 man days) | [7 empty] | 2023-03-16 | 2024-03-15 | Q4 |  | 2024-03-01 |  |  | 2625
58 | RN-216 |  |  | Cybereason | MOFAIC Cybereason |  | RNS |  | MOFAIC |  |  | Bibinu |  | Pallavi Nair | On Track | 1HC per Qtr, 2 Incidents per Qtr |  | 4 |  |  |  |  | 8 |  |  | 2022-12-15 | 2023-12-14 |  |  |  | COMPLETE
59 | RN-199 |  |  | Checkpoint | Support-Al Shirawi (Oasis Investment) - Checkpoint |  | RNS |  |  | Uma Sanker | uma.sanker@alshirawi.ae | Sagar Chopra | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  |  |  | 3 |  |  | 2022-11-28 | 2023-11-27
60 | RN-161 |  |  | Tenable | Support-Department of Finance (DOF) - Tenable |  | RNS |  |  |  |  | Bibinu |  | Pallavi Nair |  | 10 calls | [9 empty] | 2023-05-09 | 2024-05-08 |  |  |  | COMPLETE
61 | RN-245 |  |  | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  |  |  | Pallavi Nair | Completed | Major patches and service pack upgrades will be taken care as part of preventive maintenance |  | 4 HCs & 4 Inc (1 Yr) | [7 empty] | 2023-08-03 | 2024-08-02 | Licnese | 2023-08-03 | 2023-08-01 | Complete | 2023-08-07 | 138077.75
| RN-245 |  |  | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  |  |  | Pallavi Nair | Completed | Major patches and service pack upgrades will be taken care as part of preventive maintenance |  | 1 |  | Aug to Oct 23 |  |  | 1 |  |  | 2023-08-03 | 2024-08-02 | Q1 Support | Aug to Oct 23 | 2023-08-01 | Complete | 2023-08-07 | 17860
| RN-245 |  |  | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  |  |  | Pallavi Nair | Completed | Major patches and service pack upgrades will be taken care as part of preventive maintenance |  | 1 |  | Nov to Jan 24 |  |  | 1 |  |  | 2023-08-03 | 2024-08-02 | Q2 Support | Nov to Jan 24 | 2023-11-01 | Complete | 2024-02-14 | 2898
| RN-245 |  |  | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  |  |  | Pallavi Nair | Not Started | Major patches and service pack upgrades will be taken care as part of preventive maintenance |  | 1 |  | Feb to Apr 24 |  |  | 1 |  |  | 2023-08-03 | 2024-08-02 | Q3 Support | Feb to Apr 24 | 2024-02-01 |  |  | 17860
| RN-245 |  |  | ForcePoint, FP | Al Hilal - Forcepoint |  | RNS |  | Al Hilal Bank | Eyas Subaih |  |  |  | Pallavi Nair | Not Started | Major patches and service pack upgrades will be taken care as part of preventive maintenance |  | 1 |  | May to July 24 |  |  | 1 |  |  | 2023-08-03 | 2024-08-02 | Q4 Support | May to July 24 | 2024-05-01 |  |  | 17860
62 | RN-315 |  |  | Checkpoint | CheckPoint_GSL DIC Renewals_Aug_2023 |  | RNS | 2023-07-31 | Oasis (Global Shipping Ltd) |  |  | Sagar Chopra |  | Pallavi Nair | On Track | 6 annual tickets including 4 Incident Response tickets (9 by 6 support hours – excluding Fridays) and 2 General health check/preventive maintenance tickets, unlimited telephonic and email support, unlimited remote support 1 Total |  | 2 |  |  |  |  | 4 |  |  | 2023-06-15 | 2024-06-14 |  |  | 2023-08-01 | Complete | 2023-08-17 | 186289.07
63 | RN-327 |  |  | Tenable | Tawajun Economic Counsil - Tenable License |  | RNS |  | Tawajun Economic Counsil |  |  | Sagar Chopra |  | Sean Faizal | Completed | License delivery | [14 empty] | Complete |  | 226320 | Paid
| RN-327 |  |  | Tenable | Tawajun Economic Counsil - HC |  |  |  | Tawajun Economic Counsil |  |  | Sagar Chopra |  | Sean Faizal | On Track | 1HC - 1 Man day to be delivered by 19 Jul 23 |  | 1 | [7 empty] | 2023-04-20 | 2023-07-19 |  |  | 2023-07-01 | Complete | 2023-07-19 | 1840
| RN-327 |  |  | Tenable | Tawajun Economic Counsil - HC |  |  |  | Tawajun Economic Counsil |  |  | Sagar Chopra |  | Sean Faizal | On Track | 1HC - 1 Man day to be delivered by 19 Oct 23 |  | 1 | [8 empty] | 2023-10-19 |  |  | 2023-10-01 |  |  | 1840
| RN-327 |  |  | Tenable | Tawajun Economic Counsil - HC |  |  |  | Tawajun Economic Counsil |  |  | Sagar Chopra |  | Sean Faizal |  | 1HC - 1 Man day to be delivered by 19 Jan 24 |  | 1 | [8 empty] | 2024-01-19 |  |  | 2024-01-01 |  |  | 1840
| RN-327 |  |  | Tenable | Tawajun Economic Counsil - HC |  |  |  | Tawajun Economic Counsil |  |  | Sagar Chopra |  | Sean Faizal |  | 1HC - 1 Man day to be delivered by 19 Apr 24 |  | 1 | [8 empty] | 2024-04-19 |  |  | 2024-04-01 |  |  | 1840
64 | RN-241 |  |  | Sailpoint | MAF Carrefour-Sailpoint |  | RNS |  | MAF Carrefour |  |  | Bibinu |  | Vignesh | Completed | 10 Incidents per Yr, 1 HC for Qtr |  | 1 |  |  |  |  | 2.5 |  |  | 2023-02-15 | 2024-05-14 | Q1 23 |  | 2023-02-01 | Complete |  | 76114.49
| RN-241 |  |  | Sailpoint | MAF Carrefour-Sailpoint |  |  |  | MAF Carrefour |  |  | Bibinu |  | Vignesh | Completed | 10 Incidents per Qtr, 1 HC for Qtr |  | 1 |  |  |  |  | 2.5 |  |  | 2023-05-15 | 2024-08-14 | Q2 23 |  | 2023-05-01 | Complete |  | 76114.49
| RN-241 |  |  | Sailpoint | MAF Carrefour-Sailpoint |  |  |  | MAF Carrefour |  |  | Bibinu |  | Vignesh | On Track | 10 Incidents per Qtr, 1 HC for Qtr |  | 1 |  |  |  |  | 2.5 |  |  | 2023-08-15 | 2024-11-14 | Q3 23 |  | 2023-08-01 | Complete | 2023-08-18 | 76114.49
| RN-241 |  |  | Sailpoint | MAF Carrefour-Sailpoint |  |  |  | MAF Carrefour |  |  | Bibinu |  | Vignesh | On Track | 10 Incidents per Qtr, 1 HC for Qtr |  | 1 |  |  |  |  | 2.5 |  |  | 2024-11-14 | 2024-02-14 | Q4 23 |  | 2023-11-01 | Complete |  | 76114.49
65 | RN-319 |  |  | Checkpoint | Oasis Investment -AMC Checkpoint |  | RNS | 2023-07-04 | Oasis Investment |  |  | Sagar Chopra |  | Pallavi Nair | On Track | 4 annual tickets including 3 Incident Response tickets (9 by 6 support hours – excluding Fridays) and 1 General health check/preventive maintenance tickets, unlimited telephonic and email support, unlimited remote support |  | 1 |  |  |  |  | 3 |  |  | 2023-06-15 | 2024-06-14 |  |  | 2023-08-01 | Complete | 2023-08-17 | 82950
66 | RN-325 |  |  | Checkpoint | Support-Al Dhaffra-Checkpoint (Al Dhafra Firewall Upgrade _14 NOS) |  | RNS |  | Al Dhafra Insurance Co PSC |  |  | Ranjith |  | Pallavi Nair | On Track | 1 Preventive + 6 Incidents / year |  | 1 |  |  |  |  | 6 |  |  | 2023-08-31 | 2024-08-30 | Y1 23 |  | 2024-02-01 |  |  | 7350
| RN-325 |  |  | Checkpoint | Support-Al Dhaffra-Checkpoint (Al Dhafra Firewall Upgrade _14 NOS) |  |  |  | Al Dhafra Insurance Co PSC |  |  | Ranjith |  | Pallavi Nair | Not Started | 1 Preventive + 6 Incidents / year |  | 1 |  |  |  |  | 6 |  |  | 2024-08-31 | 2025-08-30 | Y2 23 |  | 2025-02-01 |  |  | 7350
| RN-325 |  |  | Checkpoint | Support-Al Dhaffra-Checkpoint (Al Dhafra Firewall Upgrade _14 NOS) |  |  |  | Al Dhafra Insurance Co PSC |  |  | Ranjith |  | Pallavi Nair | Not Started | 1 Preventive + 6 Incidents / year |  | 1 |  |  |  |  | 6 |  |  | 2025-08-31 | 2026-08-30 | Y3 23 |  | 2026-02-01 |  |  | 7531.65
| RN-223 |  |  | Thales | DPP - Thales |  | Vendor |  | Dubai Police Procecution | Imran | Imran@dxbpp.gov.ae 0554040282 |  |  | Vignesh |  | 1 HC and 3 incidnets in 1 year Customer : (Imran@dxbpp.gov.ae) Phone number : 0554040282 |  | 1 |  |  |  |  | 3 |  |  | 2023-08-12 | 2024-08-11
67 | RN-343 |  |  | FP & Others | ADJD_ MacAfee renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year | Priority Level 1 (P1) - 2 / 24 Hrs (Response / Resolution) Priority Level 2 (P2) - 8 / 48 Hrs - 24x7x365 Priority Level 3 (P3) - 24 / 48 Hrs - 9x5 | 4 |  |  |  |  | 18 |  |  | Q1 : 12 Sep 23 Q2 : 12 Dec 23 Q3 : 12 Mar 24 Q4 : 12 Jun 24 | Q1 : 11 Dec 23 Q2 : 11 Mar 24 Q3 : 11 Jun 24 Q4 : 11 Sep 24 |  |  | Dec 23 Mar 24 Jun 24 Sep 24 |  |  | 2625 each Qtr
68 | RN-344 |  |  | FP & Others | ADJD_ CyberArk renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year | Priority Level 1 (P1) - 2 / 24 Hrs (Response / Resolution) Priority Level 2 (P2) - 8 / 48 Hrs Priority Level 3 (P3) - 24 / 48 Hrs | 4 |  |  |  |  | 18 |  |  | Q1 : 12 Sep 23 Q2 : 12 Dec 23 Q3 : 12 Mar 24 Q4 : 12 Jun 24 | Q1 : 11 Dec 23 Q2 : 11 Mar 24 Q3 : 11 Jun 24 Q4 : 11 Sep 24 |  |  | Dec 23 Mar 24 Jun 24 Sep 24 |  |  | 2625 each Qtr
69 | RN-345 |  |  | FP & Others | ADJD_ ForcePoint renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year | Priority Level 1 (P1) - 2 / 24 Hrs (Response / Resolution) Priority Level 2 (P2) - 8 / 48 Hrs Priority Level 3 (P3) - 24 / 48 Hrs | 4 |  |  |  |  | 18 |  |  | Q1 : 12 Sep 23 Q2 : 12 Dec 23 Q3 : 12 Mar 24 Q4 : 12 Jun 24 | Q1 : 11 Dec 23 Q2 : 11 Mar 24 Q3 : 11 Jun 24 Q4 : 11 Sep 24 |  |  | Dec 23 Mar 24 Jun 24 Sep 24 |  |  | 2625 each Qtr
70 | RN-347 |  |  | FP & Others | ADJD_ LogRhythm renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year | Priority Level 1 (P1) - 2 / 24 Hrs (Response / Resolution) Priority Level 2 (P2) - 8 / 48 Hrs Priority Level 3 (P3) - 24 / 48 Hrs | 4 |  |  |  |  | 18 |  |  | Q1 : 12 Sep 23 Q2 : 12 Dec 23 Q3 : 12 Mar 24 Q4 : 12 Jun 24 | Q1 : 11 Dec 23 Q2 : 11 Mar 24 Q3 : 11 Jun 24 Q4 : 11 Sep 24 |  |  | Dec 23 Mar 24 Jun 24 Sep 24 |  |  | 2625 each Qtr
71 | RN-346 |  |  | FP & Others | ADJD_ FireEye renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year | Priority Level 1 (P1) - 2 / 24 Hrs (Response / Resolution) Priority Level 2 (P2) - 8 / 48 Hrs Priority Level 3 (P3) - 24 / 48 Hrs | 4 |  |  |  |  | 18 |  |  | Q1 : 12 Sep 23 Q2 : 12 Dec 23 Q3 : 12 Mar 24 Q4 : 12 Jun 24 | Q1 : 11 Dec 23 Q2 : 11 Mar 24 Q3 : 11 Jun 24 Q4 : 11 Sep 24 |  |  | Dec 23 Mar 24 Jun 24 Sep 24 |  |  | 2625 each Qtr
72 | RN-348 |  |  | FP & Others | ADJD_ Tenable renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | On Track | 18 Incidents & 4 HC per year | Priority Level 1 (P1) - 2 / 24 Hrs (Response / Resolution) Priority Level 2 (P2) - 8 / 48 Hrs Priority Level 3 (P3) - 24 / 48 Hrs | 4 |  |  |  |  | 18 |  |  | Q1 : 12 Sep 23 Q2 : 12 Dec 23 Q3 : 12 Mar 24 Q4 : 12 Jun 24 | Q1 : 11 Dec 23 Q2 : 11 Mar 24 Q3 : 11 Jun 24 Q4 : 11 Sep 24 |  |  | Dec 23 Mar 24 Jun 24 Sep 24 |  |  | 2625 each Qtr
73 | RN-352 |  |  | Fortinet | NGI Fortinet_Fortinet AMC |  | RNS | [6 empty] | Vignesh |  | 4 HCs and 10 Incidents | [9 empty] | 2023-10-03 | 2024-10-02 |  |  | 2023-09-01 | Complete | 2023-09-28 | 7728
| RN-352 |  |  | Fortinet | NGI Fortinet_Fortinet AMC |  | RNS | [6 empty] | Vignesh |  | 4 HCs and 10 Incidents | [9 empty] | 2023-10-02 | 2024-10-01 |  |  | 2023-10-01 | Complete |  | 7728
74 | RN-302 |  |  | Sailpoint | DIB Sailpoint - AMC along with PS |  | RNS |  | DIB | Shinu |  | Ishan |  | Sean | in Progress | 1 HC and 5 incidents | [9 empty] | 2022-12-30 | 2023-12-29
75 | RN-364 |  |  | McAfee | Cadvil Solutions_EDR & EPP_2023 | 100% Payment to be invoiced upon delivery of licenses and hardware | RNS | 2023-10-03 |  |  |  | Ranjith |  | Vignesh |  | 45 Licenses | [9 empty] | 2023-10-11 | 2024-10-10 |  |  | 2023-10-01 | Complete | 2023-10-17 | 16194
| RN-364 |  |  | McAfee | Cadvil Solutions_EDR & EPP_2023 | 50% to be paid in Advance & 50% to be paid on Signoff | RNS | 2023-10-03 |  |  |  | Ranjith |  | Vignesh |  | 1 HC and 3 Incidents |  | 1 |  |  |  |  | 3 |  |  | 2023-10-11 | 2024-10-10 |  |  | 2023-10-01 | Complete | 2023-10-17 | 2264.5
| RN-364 | Once 1 HC and 3 INCs are complete, this milestone can be invoiced |  | McAfee | Cadvil Solutions_EDR & EPP_2023 | 50% to be paid in Advance & 50% to be paid on Signoff | RNS | 2023-10-03 |  |  |  | Ranjith |  | Vignesh | [11 empty] | 2023-10-11 | 2024-10-10 | [5 empty] | 2264.5
76 | RN-335 | Alshirawi Checkpoint FW, Will start after PS is complete |  | Checkpoint | Support-Arcadia-Checkpoint (13 Dec 22 - 12 Dec 23) |  | RNS |  | Arcadia School |  |  |  |  | Pallavi Nair |  | 1 HC and 3 Incidents | [9 empty] | 2022-12-13 | 2023-12-12
77 | New | Will start from 28 Dec 23 |  | Checkpoint | Global Shipping & Logistics |  | RNS | 2023-10-17 | Global Shipping & Lgs |  |  | Ishan |  | Pallavi Nair |  | 1HC and 3 Incidents | [9 empty] | 2023-12-28 | 2024-12-27 |  |  | 2023-12-01 |  |  | 38108.5
78 | RN-278 | 30 PS Days, not started |  | Logrythm | Nextcare Logrhythm |  | Vendor |  | Nextcare | Zaher from Nextcare Vendor - Hady Madkour | Zaher.ElAli@nextcarehealth.com hady.madkour@logrhythm.com | Ishan Arora |  | Pallavi Nair |  | Task based PS - total 30 man days
79 | RN-374 | AMC Started on 19 Oct |  | Opswat | MOFA Opswat |  |  |  | MoFA
80 | New | New AMC |  | Checkpoint | AlShirawi - Checkpoint DIC & AlQuoz |  | RNS |  | Al Shirawi Eqpt Co |  |  |  |  | Pallavi Nair |  | Premium support for 1800 applicance - Qty 2 | [9 empty] | 2023-10-03 | 2024-10-02 |  |  | 2023-11-01 |  |  | 83300
81 | New | Will start after PS is complete |  | Solarwinds | Beema Insurance - Solarwinds NMC |  | RNS |  | Wasif Khan |  |  |  |  | Samruddhi |  | 4 HCs and unlimited incident support |  | 4 |  |  |  |  | Unlimited | [6 empty] | 2023-11-01 | Complete | 2023-11-09 | 5798
82 | RN-283 |  |  | Manage Engine | RAK Customs Manage Engine |  | Vendor | 2023-10-01 |  |  |  | Ishan Arora |  | Pallavi Nair |  | 8 incidents | [6 empty] | 8 |  |  | 2023-10-10 | 2024-10-09
83 | New |  |  | Checkpoint | Arcadia School - Checkpoint : 6400 appliance (project) |  | RNS
84 | New | 3 Yrs contract, will start once the PS is complete |  | MS Automation | Microsoft Automation _ November 2023_MAAN |  | AMC | 2023-11-22 | Authority of Social Contribution - MAAN | Yaqoob Yousef Al Awadhi |  | Haytham |  | Vignesh |  | YR 1 | [16 empty] | 60000
| New |  |  |  | Microsoft Automation _ November 2023_MAAN |  |  | 2023-11-22 | Authority of Social Contribution - MAAN | Yaqoob Yousef Al Awadhi |  | Haytham |  | Vignesh |  | YR 2 | [16 empty] | 60000
| New |  |  |  | Microsoft Automation _ November 2023_MAAN |  |  | 2023-11-22 | Authority of Social Contribution - MAAN | Yaqoob Yousef Al Awadhi |  | Haytham |  | Vignesh |  | YR 3 | [16 empty] | 60000
85 | New | Lic + AMC + PS AMC will start once PS is complete |  | Tenable | Tenable_VM_Sept_2023 |  | RNS | 2023-11-22 | Dubai Land Dept | Abdulla Yalooq |  | Ishan |  | Sean
86 | New | AMC will start from 23 Dec 23 |  | Delinea | Intigral_Delinea AMC |  | Vendor | 2023-12-13 | Intigral Middle East | Binu | Binu.Mathew@intigral.net | Ishan Arora |  | Sean Faizal |  | 4 HC and 4 Incidents | [9 empty] | 2023-12-23 | 2024-12-22 | [5 empty] | 28310
85 | New | AMC will start once HW is setup |  | Fortigate | Gargash_Fortigate FW AMC | 100% invoiced uploand HW delivery | RNS | 2023-12-22 |  |  |  | Ranjith |  | Pallavi |  | 1 Incident | [16 empty] | 2000
| New | will start once PS is complete |  | Not Started | CyberArc | OQ Trading - CyberArc | 100% on PS Sign off | RNS | 2023-12-05 | OQ Trading |  |  | Rohit Save |  | Sean Faizal |  | 2 HCs and 6 Incidents |  | 2 |  |  |  |  | 6 | [9 empty] | 13248
82 | New | Will start after PS is complete |  | CyberArc | ADEK - CyberArc | End of Y1 Q1 | RNS |  | ADEK |  |  | Haytham |  | Vignesh |  | Unlimited support | [11 empty] | Y1 Q1 |  |  |  |  | 4883.33
| New |  |  | CyberArc | ADEK - CyberArc | End of Y1 Q2 | [21 empty] | Y1 Q2 |  |  |  |  | 4883.33
| New |  |  | CyberArc | ADEK - CyberArc | End of Y1 Q3 | [21 empty] | Y1 Q3 |  |  |  |  | 4883.33
| New |  |  | CyberArc | ADEK - CyberArc | End of Y1 Q4 | [21 empty] | Y1 Q4 |  |  |  |  | 4883.33
| New |  |  | CyberArc | ADEK - CyberArc | Y2 -4 Qtrs | [21 empty] | Y2 - 4 Qtrs |  |  |  |  | 19533.32
| New |  |  | CyberArc | ADEK - CyberArc | Y3 - 4 Qtrs | [21 empty] | Y3 - 4 Qtrs |  |  |  |  | 19533.32
| NEW | Proposal to be checked |  | Forcepoint | Tawajun Industrial Park - ForcePoint | [8 empty] | Sean
| NEW | Proposal to be checked |  | Blackberry | Tawazun Economic Council- ref LPO 10964 | [8 empty] | Sean
| NEW | PO is yet to be received |  | Sailpoint | DIB Sailpoint - AMC (Yet to Start) |  | RNS |  | DIB | Shinu |  | Ishan |  | Sean | Not Started | Not started
| NEW | PO is yet to be received |  | Trendmicro | CBD_Trendmicro_AMC Renewal_Q3_2023 |  | RNS | 2023-10-03 |  |  | Shihab Packer | Faizan |  | Pallavi Nair
| RN-157 | AMC Renewal will start from 05 Nov 23 |  | Sailpoint | GULF INSURANCE GROUP (GULF) B S C DUBAI BRANCH_SailPoint_Renewal 23-24_Nov_2023 | SailPoint License Renewal 2023-2024 | RNS | 2023-10-03 |  |  |  | Ishan |  | Pallavi Nair |  | 1000 Licenses | [9 empty] | 2023-11-05 | 2024-11-04 |  |  | 2023-11-01 |  |  | 75600
| RN-157 | AMC Renewal will start from 05 Nov 23 |  | Sailpoint | GULF INSURANCE GROUP (GULF) B S C DUBAI BRANCH_SailPoint_Renewal 23-24_Nov_2023 | SailPoint License Annual Maintenance and Support 2023-2024 | RNS | 2023-10-03 |  |  |  | Ishan |  | Pallavi Nair |  | 8 Incidents | [9 empty] | 2023-11-05 | 2024-11-04 |  |  | 2023-11-01 |  |  | 36800
| NEW | Will start after PS is complete |  | Sailpoint | Aldar Properties PJSC_SP_RW_AMC_Sep_2023 |  | RNS | 2023-10-03 |  |  |  | Bibinu |  | Vignesh |  | 5 Incident support
| RN-283 | Will start after PS is complete |  | Manage Engine | RAK Customs Manage Engine |  | Vendor | 2023-10-01 |  |  |  | Ishan Arora |  | Pallavi Nair |  | 8 incidents | [6 empty] | 8
| New | PO is yet to be received |  | Sailpoint | Doha Bank | [8 empty] | Pallavi Nair
14 | New | Will start after PS is complete |  | Cybereason | Waha Health - CyberReason - AMC |  | RNS | [6 empty] | Pallavi Nair | Not Started |  |  | 2 |  |  |  |  | 4 | [9 empty] | 6624
61 | NEW | Will start after PS is complete |  | Opswat | Support MOFA - Opswat - Vendor PS & RNS AMC | [6 empty] | Bibinu |  | Tanaya | Not Started | Y1 |  | 4 |  |  |  |  | 2 | [9 empty] | 12266.64
| NEW | Will start after PS is complete |  | Opswat | Support MOFA - Opswat - Vendor PS & RNS AMC | [6 empty] | Bibinu |  | Tanaya | Not Started | Y2 |  | 4 |  |  |  |  | 2 | [9 empty] | 12266.64
| NEW | Will start after PS is complete |  | Opswat | Support MOFA - Opswat - Vendor PS & RNS AMC | [6 empty] | Bibinu |  | Tanaya | Not Started | Y3 |  | 4 |  |  |  |  | 2 | [9 empty] | 12266.64
66 | New | Will start after PS is complete |  | Checkpoint | Firewall Upgrade _14 NOS 1st support after 6 months |  |  |  | Al Dhafra Insurance Co PSC | Alaa Saad |  | Ranjit George Mathew |  | Tanaya | Not Started | 21 tickets - 1 HC and 6 Incidents for 3 years |  | 1 |  |  |  |  | 6 | [9 empty] | 7350
| New | Will start after PS is complete |  | Checkpoint | Firewall Upgrade _14 NOS 2nd year support after 18 months |  |  |  | Al Dhafra Insurance Co PSC | Alaa Saad |  | Ranjit George Mathew |  | Tanaya | Not Started | 21 tickets - 1 HC and 6 Incidents |  | 1 |  |  |  |  | 6 | [9 empty] | 7350
| New | Will start after PS is complete |  | Checkpoint | Firewall Upgrade _14 NOS 3nd Year support after 30 months |  |  |  | Al Dhafra Insurance Co PSC | Alaa Saad |  | Ranjit George Mathew |  | Tanaya | Not Started | 21 tickets - 1 HC and 6 Incidents |  | 1 |  |  |  |  | 6 | [9 empty] | 7351.65
| RN-266 | Will start after PS is complete |  | Sailpoint | DMT Sailpoint |  | RNS | From Go Live for 1 year | DMT |  |  | Ishan |  | Pallavi Nair | Not Started | 7 Incidents and 1 HC : Post Go Live AMC charges will be billed as part of the project milestones | [16 empty] | 34886.4
| NEW | Will start after PS is complete |  |  | RTS - Proofpoint | [8 empty] | Pallavi Nair |  | Remote support - 1yr Qtrly payment | [16 empty] | 4665.50 per qtr
| RN-278 | Support not started - PO also not received |  | Logrythm | NW & Sec |  | Vendor |  | Nextcare | Zaher from Nextcare Vendor - Hady Madkour | Zaher.ElAli@nextcarehealth.com hady.madkour@logrhythm.com | Ishan Arora |  | Pallavi Nair
| NEW | Will start after PS is complete |  | CyberArc | ADEK - CyberArc |  | RNS |  | ADEK |  |  | Haytham |  | Vignesh | Not Started | 3 Yrs Support, Qtrly invoicing, unlimited support
| NEW | Will start from 22 Dec 23 |  | Tenable | DMT Tenalble |  | RNS |  | DMT |  |  | Bibinu |  | Pallavi Nair | Not Started | 19 months support | [9 empty] | 2023-12-22 | 2025-01-01
NEW
| RN-262 |  |  |  | DAS Project (IT Support)
| RN-306 |  |  |  | Support-Value Add Services (Non Billable)
| RN-321 |  |  |  | Support effort spent on KT, Pre Sales, Certifications, Trainings, Shadowing etc.,.
| RN-336 |  |  |  | Leave Tracker
| RN-354 |  |  |  | Government Holidays
| RN-355 |  |  |  | ForgeRock Practice Development
Note on T7: CS Rao: as per contract - 1 HC
Note on B10: CS Rao: check with Brijesh for the tech proposal
Note on B11: CS Rao: Manasi to check and confirm the start date
Note on C13: CS Rao: Manasi to share the completed involice info
Note on C14: CS Rao: contract yet to be signed. Manasi to cross check
Note on C18: CS Rao:Project team can track HC and incidnets. Invoicing will be planned by KD

## Resource Utilization (hidden)
RESOURCE DATA
PROJECT DATA |  |  |  | UTILIZATION
|  |  |  | 2023-07-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01
NO. | PROJECT ID | PROJECT NAME | STATUS | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32 | Wk33 | Wk34 | Wk35 | Wk36 | Wk37 | Wk38 | Wk39 | Wk40 | Wk41 | Wk42 | Wk43 | Wk44 | Wk45 | Wk46 | Wk47 | Wk48 | Wk49 | Wk50 | Wk51 | Wk52 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22
1 | RN-82 | CUBE - VAPT - 2022 | On Hold
42 | RN-3 | Voltas | 1
2 | RN-78 | DLD SAILPOINT | Completed
34 | RN-309 | Mall of Qatar | 12
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
3 | RN-37 | FNG - VAPT | On Track
3 | RN-101 | TIP - Forcepoint, BJ and DLP | Delayed
11 | RN-25 | NW & Sec | Tanaya
10 | RN--23 | NW & Sec | Rubeena
25 | RN-228/337 | RTS
36 | RN-37 | Fujairah National Group | 2
43 | RN-242 | LM Exchange | 16
4 | RN-237 | INTERPLAST - VAPT 2023 | Completed
4 | RN-252 | EPC-VAPT_2023 | On Hold
7 | RN-318 | IntelliStrike | Rubeena
6 | RN-112 | MASHREQ - FireEye | On Hold
29 | RN-238 | Seddiqi Holding | 4
7 | RN-298 | Nextcare - FP DLP & Data classification | Delayed
37 | RN-353 | Emirates Steel | 1
40 | RN-416 | DAMAAC | 1
8 | RN-301 | Nextcare_Akamai_AAP & DSA | On Hold
35 | RN-380 | OQ Trading
11 | RN-320 | Nextcare_Managed_APM_&_IT_Incidents | On Hold
14 | RN-314 | IntelliStrike | #REF!
13 | RN-296 | Gulf Cryo - VAPT | Completed
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
34 | RN-425 | NI UAE -Sailpoint FAM Upgrade | Delayed
12 | RN-397 | DIB - Forcepoint RBI | Completed
#REF! | #REF! | #REF! | #REF!
55 | RN-329 | DP World
53 | RN-237 | INTERPLAST | 3
21 | RN-349
9 | RN-282 | NW & Sec | Vignesh
13 | RN-427 | MBRSG FireWall Reconfiguration | Completed
15 | RN-3 | Voltas - VAPT | Completed
26 | RN-356 | Theodor Wille Intertrade FZE | 4
#REF! | #REF! | #REF! | #REF!
18 | RN-357 | LM Exchange-Security Awareness trg | On Track
#REF! | #REF! | #REF! | #REF!
46 | RN-286 | NAFFCO | 4
12 | RN-104 | NW & Sec | Tanaya
8 | RN-288 | IntelliStrike | Tanaya
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
22 | RN-289 | EMPOWER-VAPT_2023 | Completed
56
22 | RN-16 | Empower | 2
23 | RN-89 | AJMAN BANK - DLP & FP | On Track
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
2 | RN-122 | ADCB - SailPoint Phase 2
45 | RN-289 | EMPOWER | 3
57
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
15 | RN-294 | NW & Sec | Vignesh
31 | RN-279 | Damas - Cybereason | 2
30 | RN-331 | Tawazun Industrial Park
#REF! | #REF! | #REF! | #REF!
28 | RN-279 | Damas - Cybereason | Completed
27 | RN-102 | ALDAR | 5
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | RN-409 | Gulf Marines Services Company LLC
#REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
40 | RN-341 | Waha Health - CyberReason PS - 4 Days | #REF!
#REF! | #REF! | #REF! | Completed
31 | RN-304 | Deem Finance_Zscaler | #REF!
33 | RN-309 | Mall Of Qatar_Akamai_19062023 | On Track
39 | #REF! | #REF! | On Track
#REF! | RN-375 | ADEK - CyberArc | 4
#REF! | RN-89 | AJMAN BANK | Completed
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
35 | RN-312 | ES_F5 Networks | #REF!
#REF! | #REF! | #REF! | On Track
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
35 | RN-342 | MAF Bot Manager | #REF!
13 | RN-270 | LM Exchange | Completed
#REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
6 | RN-27 |  | #REF!
49 | RN-292 | SKM AirConditioning | Pallavi Nair
17 | RN-119 | Transco | 4
28 |  | 0 | 4
43 | RN-331 | Tawajun Industrial Park - Checkmarx solution | 0
#REF! | #REF! | #REF! | On Track
49 | RN-305 | ENI_Emirates National Investments - VAPT | #REF!
32 | RN-379 | DLD | Delayed
58 | RN-278 | Vendor | 2
41 | RN-353 | ES_Forcepoint Proxy - Licenses; Professional Services_ZTNA | Task based AMC - tasks will be supported by vendor
54 | RN416 | DamasJewellery | Delayed

## Financial Data
FINANCIAL DATA
PROJECT DATA |  |  | FINANCIAL DATA
NO. | PROJECT ID | PROJECT NAME | PO Ref # | PO DATE | PO Description | PAYMENT TERMS | COST OF PROJECT | APPROVED ADD'L COSTS | TOTAL APPROVED BUDGET | Approved Internal SO Cost | Actual Cost | COST VARIANCE | COST VS. BUDGET
1 | RN-82 | CUBE - VAPT - 2022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | RN-3 | Voltas |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RN-78 | DLD SAILPOINT |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | RN-309 | Mall of Qatar |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | RN-37 | FNG - VAPT |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | RN-101 | TIP - Forcepoint, BJ and DLP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | RN-25 | NW & Sec |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | RN--23 | NW & Sec |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | RN-228/337 | RTS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | RN-37 | Fujairah National Group |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | RN-242 | LM Exchange |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | RN-237 | INTERPLAST - VAPT 2023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | RN-252 | EPC-VAPT_2023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | RN-318 | IntelliStrike |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | RN-112 | MASHREQ - FireEye |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | RN-238 | Seddiqi Holding |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | RN-298 | Nextcare - FP DLP & Data classification |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | RN-353 | Emirates Steel |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | RN-416 | DAMAAC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | RN-301 | Nextcare_Akamai_AAP & DSA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | RN-380 | OQ Trading |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | RN-320 | Nextcare_Managed_APM_&_IT_Incidents |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | RN-314 | IntelliStrike |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | RN-425 | NI UAE -Sailpoint FAM Upgrade |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | RN-397 | DIB - Forcepoint RBI |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | RN-329 | DP World |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | RN-237 | INTERPLAST |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | RN-349 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | RN-282 | NW & Sec |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | RN-427 | MBRSG FireWall Reconfiguration |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | RN-3 | Voltas - VAPT |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | RN-356 | Theodor Wille Intertrade FZE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | RN-357 | LM Exchange-Security Awareness trg |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | RN-286 | NAFFCO |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | RN-104 | NW & Sec |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | RN-288 | IntelliStrike |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | SAAL-000813-1 | 2023-05-30 | Consultation Services for Implementation of SDLC | DELIVERY DATE - 12 JUN 23 | 23153.33 | 0 | 23153.33 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | RN-289 | EMPOWER-VAPT_2023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | RN-16 | Empower |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | RN-89 | AJMAN BANK - DLP & FP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RN-122 | ADCB - SailPoint Phase 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | RN-294 | NW & Sec |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | RN-279 | Damas - Cybereason |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | RN-331 | Tawazun Industrial Park |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | RN-279 | Damas - Cybereason |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | RN-102 | ALDAR |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | RN-409 | Gulf Marines Services Company LLC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | RN-341 | Waha Health - CyberReason PS - 4 Days |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | RN-304 | Deem Finance_Zscaler |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | RN-309 | Mall Of Qatar_Akamai_19062023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | RN-375 | ADEK - CyberArc |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | RN-89 | AJMAN BANK |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | RN-312 | ES_F5 Networks |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | RN-342 | MAF Bot Manager |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | RN-270 | LM Exchange |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | RN-27 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | RN-292 | SKM AirConditioning |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | RN-119 | Transco |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | RN-331 | Tawajun Industrial Park - Checkmarx solution |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | RN-305 | ENI_Emirates National Investments - VAPT |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | RN-379 | DLD |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | RN-278 | Vendor |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | RN-353 | ES_Forcepoint Proxy - Licenses; Professional Services_ZTNA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | RN416 | DamasJewellery |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | RN-359 | #REF! |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Deliverables and Performance (hidden)
DELIVERABLES AND PERFORMANCE
CONTRACT DATA |  |  | DELIVERABLES |  |  | PERFORMANCE
NO. | CONTRACT ID | CONTRACT NAME | MILESTONE | DATE | APPROVED VARIATIONS | DATE OF REVIEW | TYPE OF REVIEW | REVIEW SUMMARY
1 | RN-82 | CUBE - VAPT - 2022
42 | RN-3 | Voltas
2 | RN-78 | DLD SAILPOINT
34 | RN-309 | Mall of Qatar
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
3 | RN-37 | FNG - VAPT
3 | RN-101 | TIP - Forcepoint, BJ and DLP
11 | RN-25 | NW & Sec
10 | RN--23 | NW & Sec
25 | RN-228/337 | RTS
36 | RN-37 | Fujairah National Group
43 | RN-242 | LM Exchange
4 | RN-237 | INTERPLAST - VAPT 2023
4 | RN-252 | EPC-VAPT_2023
7 | RN-318 | IntelliStrike
6 | RN-112 | MASHREQ - FireEye
29 | RN-238 | Seddiqi Holding
7 | RN-298 | Nextcare - FP DLP & Data classification
37 | RN-353 | Emirates Steel
40 | RN-416 | DAMAAC
8 | RN-301 | Nextcare_Akamai_AAP & DSA
35 | RN-380 | OQ Trading
11 | RN-320 | Nextcare_Managed_APM_&_IT_Incidents
14 | RN-314 | IntelliStrike
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
34 | RN-425 | NI UAE -Sailpoint FAM Upgrade
12 | RN-397 | DIB - Forcepoint RBI
#REF! | #REF! | #REF!
55 | RN-329 | DP World
53 | RN-237 | INTERPLAST
21 | RN-349
9 | RN-282 | NW & Sec
13 | RN-427 | MBRSG FireWall Reconfiguration
15 | RN-3 | Voltas - VAPT
26 | RN-356 | Theodor Wille Intertrade FZE
#REF! | #REF! | #REF!
18 | RN-357 | LM Exchange-Security Awareness trg
#REF! | #REF! | #REF!
46 | RN-286 | NAFFCO
12 | RN-104 | NW & Sec
8 | RN-288 | IntelliStrike
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
22 | RN-289 | EMPOWER-VAPT_2023
56
22 | RN-16 | Empower
23 | RN-89 | AJMAN BANK - DLP & FP
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
2 | RN-122 | ADCB - SailPoint Phase 2
57
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
15 | RN-294 | NW & Sec
31 | RN-279 | Damas - Cybereason
30 | RN-331 | Tawazun Industrial Park
#REF! | #REF! | #REF!
28 | RN-279 | Damas - Cybereason
27 | RN-102 | ALDAR
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | RN-409 | Gulf Marines Services Company LLC
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
40 | RN-341 | Waha Health - CyberReason PS - 4 Days
#REF! | #REF! | #REF!
31 | RN-304 | Deem Finance_Zscaler
33 | RN-309 | Mall Of Qatar_Akamai_19062023
39 | #REF! | #REF!
#REF! | RN-375 | ADEK - CyberArc
#REF! | RN-89 | AJMAN BANK
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
35 | RN-312 | ES_F5 Networks
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
35 | RN-342 | MAF Bot Manager
13 | RN-270 | LM Exchange
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
6 | RN-27
49 | RN-292 | SKM AirConditioning
17 | RN-119 | Transco
28 |  | 0
43 | RN-331 | Tawajun Industrial Park - Checkmarx solution
#REF! | #REF! | #REF!
49 | RN-305 | ENI_Emirates National Investments - VAPT
32 | RN-379 | DLD
58 | RN-278 | Vendor
41 | RN-353 | ES_Forcepoint Proxy - Licenses; Professional Services_ZTNA
54 | RN416 | DamasJewellery
47 | RN-359 | #REF!

## Risk Register (hidden)
RISK REGISTER
PROJECT DATA |  |  | KEY RISKS / ISSUES
NO. | CONTRACT ID | CONTRACT NAME | RISK / ISSUE ONE | LIKELIHOOD RATING | IMPACT RATING | OVERALL RISK SCORE | MITIGATION ACTION | PROPOSED RESOLUTION | RISK / ISSUE TWO | LIKELIHOOD RATING | IMPACT RATING | OVERALL RISK SCORE | MITIGATION ACTION | PROPOSED RESOLUTION | RISK / ISSUE THREE | LIKELIHOOD RATING | IMPACT RATING | OVERALL RISK SCORE | MITIGATION ACTION | PROPOSED RESOLUTION
1 | RN-82 | CUBE - VAPT - 2022 |  |  |  | – | [5 empty] | – | [5 empty] | –
42 | RN-3 | Voltas |  |  |  | – | [5 empty] | – | [5 empty] | –
2 | RN-78 | DLD SAILPOINT |  |  |  | – | [5 empty] | – | [5 empty] | –
34 | RN-309 | Mall of Qatar |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
3 | RN-37 | FNG - VAPT |  |  |  | – | [5 empty] | – | [5 empty] | –
3 | RN-101 | TIP - Forcepoint, BJ and DLP |  |  |  | – | [5 empty] | – | [5 empty] | –
11 | RN-25 | NW & Sec |  |  |  | – | [5 empty] | – | [5 empty] | –
10 | RN--23 | NW & Sec |  |  |  | – | [5 empty] | – | [5 empty] | –
25 | RN-228/337 | RTS |  |  |  | – | [5 empty] | – | [5 empty] | –
36 | RN-37 | Fujairah National Group |  |  |  | – | [5 empty] | – | [5 empty] | –
43 | RN-242 | LM Exchange |  |  |  | – | [5 empty] | – | [5 empty] | –
4 | RN-237 | INTERPLAST - VAPT 2023 |  |  |  | – | [5 empty] | – | [5 empty] | –
4 | RN-252 | EPC-VAPT_2023 |  |  |  | – | [5 empty] | – | [5 empty] | –
7 | RN-318 | IntelliStrike |  |  |  | – | [5 empty] | – | [5 empty] | –
6 | RN-112 | MASHREQ - FireEye |  |  |  | – | [5 empty] | – | [5 empty] | –
29 | RN-238 | Seddiqi Holding |  |  |  | – | [5 empty] | – | [5 empty] | –
7 | RN-298 | Nextcare - FP DLP & Data classification |  |  |  | – | [5 empty] | – | [5 empty] | –
37 | RN-353 | Emirates Steel |  |  |  | – | [5 empty] | – | [5 empty] | –
40 | RN-416 | DAMAAC |  |  |  | – | [5 empty] | – | [5 empty] | –
8 | RN-301 | Nextcare_Akamai_AAP & DSA |  |  |  | – | [5 empty] | – | [5 empty] | –
35 | RN-380 | OQ Trading |  |  |  | – | [5 empty] | – | [5 empty] | –
11 | RN-320 | Nextcare_Managed_APM_&_IT_Incidents |  |  |  | – | [5 empty] | – | [5 empty] | –
14 | RN-314 | IntelliStrike |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
34 | RN-425 | NI UAE -Sailpoint FAM Upgrade |  |  |  | – | [5 empty] | – | [5 empty] | –
12 | RN-397 | DIB - Forcepoint RBI |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
55 | RN-329 | DP World |  |  |  | – | [5 empty] | – | [5 empty] | –
53 | RN-237 | INTERPLAST |  |  |  | – | [5 empty] | – | [5 empty] | –
21 | RN-349 |  |  |  |  | – | [5 empty] | – | [5 empty] | –
9 | RN-282 | NW & Sec |  |  |  | – | [5 empty] | – | [5 empty] | –
13 | RN-427 | MBRSG FireWall Reconfiguration |  |  |  | – | [5 empty] | – | [5 empty] | –
15 | RN-3 | Voltas - VAPT |  |  |  | – | [5 empty] | – | [5 empty] | –
26 | RN-356 | Theodor Wille Intertrade FZE |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
18 | RN-357 | LM Exchange-Security Awareness trg |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
46 | RN-286 | NAFFCO |  |  |  | – | [5 empty] | – | [5 empty] | –
12 | RN-104 | NW & Sec |  |  |  | – | [5 empty] | – | [5 empty] | –
8 | RN-288 | IntelliStrike |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
22 | RN-289 | EMPOWER-VAPT_2023 |  |  |  | – | [5 empty] | – | [5 empty] | –
56 | [5 empty] | – | [5 empty] | – | [5 empty] | –
22 | RN-16 | Empower |  |  |  | – | [5 empty] | – | [5 empty] | –
23 | RN-89 | AJMAN BANK - DLP & FP |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
2 | RN-122 | ADCB - SailPoint Phase 2 |  |  |  | – | [5 empty] | – | [5 empty] | –
57 | [5 empty] | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
15 | RN-294 | NW & Sec |  |  |  | – | [5 empty] | – | [5 empty] | –
31 | RN-279 | Damas - Cybereason |  |  |  | – | [5 empty] | – | [5 empty] | –
30 | RN-331 | Tawazun Industrial Park |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
28 | RN-279 | Damas - Cybereason |  |  |  | – | [5 empty] | – | [5 empty] | –
27 | RN-102 | ALDAR |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | RN-409 | Gulf Marines Services Company LLC |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
40 | RN-341 | Waha Health - CyberReason PS - 4 Days |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
31 | RN-304 | Deem Finance_Zscaler |  |  |  | – | [5 empty] | – | [5 empty] | –
33 | RN-309 | Mall Of Qatar_Akamai_19062023 |  |  |  | – | [5 empty] | – | [5 empty] | –
39 | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | RN-375 | ADEK - CyberArc |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | RN-89 | AJMAN BANK |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
35 | RN-312 | ES_F5 Networks |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
35 | RN-342 | MAF Bot Manager |  |  |  | – | [5 empty] | – | [5 empty] | –
13 | RN-270 | LM Exchange |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
6 | RN-27 |  |  |  |  | – | [5 empty] | – | [5 empty] | –
49 | RN-292 | SKM AirConditioning |  |  |  | – | [5 empty] | – | [5 empty] | –
17 | RN-119 | Transco |  |  |  | – | [5 empty] | – | [5 empty] | –
28 |  | 0 |  |  |  | – | [5 empty] | – | [5 empty] | –
43 | RN-331 | Tawajun Industrial Park - Checkmarx solution |  |  |  | – | [5 empty] | – | [5 empty] | –
#REF! | #REF! | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –
49 | RN-305 | ENI_Emirates National Investments - VAPT |  |  |  | – | [5 empty] | – | [5 empty] | –
32 | RN-379 | DLD |  |  |  | – | [5 empty] | – | [5 empty] | –
58 | RN-278 | Vendor |  |  |  | – | [5 empty] | – | [5 empty] | –
41 | RN-353 | ES_Forcepoint Proxy - Licenses; Professional Services_ZTNA |  |  |  | – | [5 empty] | – | [5 empty] | –
54 | RN416 | DamasJewellery |  |  |  | – | [5 empty] | – | [5 empty] | –
47 | RN-359 | #REF! |  |  |  | – | [5 empty] | – | [5 empty] | –

## Data Values
|  | Prpojects | Milestones |  |  | Prpojects | Milestones
| May | 5 | 13 |  | July | 3 | 13
| Jun | 6 | 12 |  | August | 8 | 22
| July | 2 | 5 |  | September | 4 | 15
`
|  |  |  | ps | amc | ms
|  |  |  | 291375 | 7728
|  |  |  | 197559 | 3333.75
|  |  |  | 496283.29 | 3333.75 | 62662.04
|  |  |  | 11592 | 4856.25 | 157500
|  |  |  | 6182 | 43097.71
|  |  |  | 126163.8 | 30912
|  |  |  | 22687.7 | 1932
Mashreq & Deem Finance
2649803.07

## KEY Data – do not delete –
CONTRACT MANAGEMENT LOG TEMPLATE
KEY DATA
Status | ONE-OFF / ONGOING | Project Type | LIKELIHOOD RATING |  | Complexity |  | OVERALL RISK SCORE | ACCOUNT HEALTH
On Track | One-Off |  | 1 | Highly Unlikely |  |  | LOW
On Hold | Ongoing | Barracuda | 2 | Unlikely | 1 | Low | MED | GREEN
Completed |  | Checkpoint | 3 | Possible | 2 | Medium | HIGH | AMBER
Delayed |  | CrowdStrike | 4 | Probable | 3 | High |  | RED
Not Started |  | CyberArc | 5 | Highly Likely | 5 | Severe
Ready for Closure |  | cybereason
Darktrace
Forcepoint, DLP
Fortigate
Fortinet
FP, ForcePoint
IAM
IAM, Sailpoint
ISMS
ivanti
Pulsesecure
Sailpoint
Sailpoint, IAM
SOC
Trend Micro
Tripwire
VAPT
VAPT, SOC

## Closed Merged
PROJECT DATA | [6 empty] | CUSTOMER DATA |  |  | ACCOUNT DATA |  | PROJECT MANAGEMENT | [5 empty] | TERMS
NO. | PROJECT ID | Project Type | Tower | Led By | PROJECT NAME | Project Scope | CUSTOMER NAME | CUSTOMER SPOC NAME | CUSTOMER SPOC EMAIL | ACCOUNT MANAGER NAME | ACCOUNT HEALTH | INTERNAL PROJECT MANAGER | PROJECT COMPLEXITY | Status | Total Milestones | Milestones Open | Milestones Closed | START DATE | END DATE | Revised End Date | Actual End Date | % Completion | REMARKS | Rekha comments
| RN-20 | VAPT | IntelliStrike |  | Sentinal - VAPT |  | Sentinel Capital | Faheem | Faheem.Kausar@sencap.com | Rohit Save | GREEN | Tanaya | Low | Completed | 3 | 1 | 2 | 2021-08-16 | 2023-08-31 |  | 2023-08-31 | 100% | Delayed due to unresponsive customer
| RN-274 | Sailpoint | Sailpoint |  | NI External Client Build - IIQ |  | NI | Fuard | Fuard.Saban@network.global | Ishan Arora | GREEN | Rubeena | Low | Completed | 1 | 0 | 1 | 2023-04-03 | 2023-06-19 |  | 2023-06-19 | 100% | Sign-off received on 19th Jun. Invoicing complete. Check with Manasi
| RN-105 | Sailpoint | Sailpoint |  | PHCC(Phase1)Sailpoint |  | PHCC | Sahil | sbhugra@phcc.gov.qa | Brejesh | GREEN | Rubeena | Low | Completed | 5 | 1 | 4 | 2023-06-23 | 2023-07-14 |  | 2023-03-01 | 100% | Project signoff Received, Testing pending for outsourced employee. External dependancy for the testing (customer to give the schedule)
| RN-253 | Checkpoint | NW & Sec |  | AL ZAHRA - Checkpoint (Vendor) |  | AL ZAHRA | Iftequar Hussain | iftequar.h@azhd.ae | Rohit Save | GREEN | Sean Faizal | Low | Completed | 1 | 0 | 1 | 2023-05-26 | 2023-06-05 |  | 2023-07-10 | 100% | Invoicing is done. Will check with Rekha to close it
| RN-6 | VAPT | IntelliStrike |  | Al Jazeira Services - VAPT |  | Aljazeira Services | Murugesan Pugazhendi | Murugesan.Pugazhendi@glserve.com | Bibinu Ajith | GREEN | Pallavi Nair | Low | Completed | 3 | 0 | 3 | 2022-08-26 | 2023-06-19 |  | 2023-07-14 | 100% | Sign-off received on 10 July 23
| RN-27 | IA ITSM |  |  | Albatha - ISO 20K |  | Albatha | Anirudh Tulsidas Shetty | Anirudh@albatha.com | Rohit Suresh Save | GREEN | Pallavi Nair | Low | Completed | 3 | 0 | 3 | 2023-05-09 | 2023-06-21 |  | 2023-07-17 | 100% | Delvierables are complete and payment received.
| RN-318 | VAPT | IntelliStrike |  | ECCSC_VAPT_Web & Sec Assessement_Load Testing |  | Emirates Centrol Cooling System Corp |  | Emirates Small Scope - VAPT |  | GREEN | Rubeena | Low | Completed | [6 empty] | 2023-08-07 | 100%
| RN-288 | VAPT | IntelliStrike |  | Damas API Testing - VAPT |  | Damas | Amit Pradhan | apradhan@damasjewellery.com | Rohit Save | GREEN | Tanaya | Low | Completed | 2 | 1 | 1 | 2023-06-01 | 2023-07-14 |  | 2023-08-09 | 100% | Retesting is pending
| RN-282 | FW - Fortigate | NW & Sec | RNS | Dubai Sports Council-Fortigate |  | Dubai Sports Council | Mohammed Ashhar | armohammed@dubaisc.ae | Faizan Javed | GREEN | Vignesh | Medium | Completed | 3 | 3 |  | 2023-05-26 | 2023-08-01 |  | 2023-08-14 | 100% | Configuration of the FW is in progress
| RN-23 | ForcePoint, FP | NW & Sec |  | DLD- Bolden James & Forcepoint |  | DLD | Rambhul | rambhul.singh@dubailand.gov.ae | KD | AMBER | Rubeena | Low | Completed | 2 | 1 | 1 |  | NA |  | 2021-03-11 | 100% | Client dependancy. Product is discarded. Written confirmation is accorded from customer
| RN-25 | Rapid 7 | NW & Sec |  | Gulf Drug - SIM, SOC, VAPT |  | Gulf Drug | Vijay | Vijay@gulfdrug.com | Ayushmann | AMBER | Tanaya | Medium | Cancelled | 4 | 4 | 0 |  | 2023-08-31 |  | 2022-08-05 | 61% | Client to give go-ahead to start the project
| RN-104 | Rapid 7 | NW & Sec |  | AD Aviation - Rapid7 |  | Abu Dhabi Aviation | Sibtain | m.ali@abudhabiaviation.com | Ishan Arora | AMBER | Tanaya | Low | Completed | 2 | 1 | 0 |  | 2023-07-14 |  | 2022-06-28 | 100% | Abhinav to share the Insight VM documentation
| RN-270 | Cyclops | NW & Sec | Vendor | LM Exchange-Cyclops (Vendor) |  | LM Exchange | Hareesh R S | hareesh.rs@lm-exchange.com | Ranjith Goerge | AMBER | Vignesh | Medium | Completed |  | 2 | 2 |  | 2023-06-26 |  | 2023-08-07 | 100% | Project sign off shared to client
| RN-314 | VAPT | IntelliStrike | RNS | Damas - API Testing |  | Damas Jewellery LLC |  | Amit Pradhan | Rohit | GREEN | Vignesh | Low | Completed |  |  |  | 2023-08-01 | 2023-08-23 |  | 2023-08-23 | 100%
| RN-294 | Invicti | NW & Sec |  | Airtel Africa - Invicti |  | Airtel Africa | Arun Menon | arun.menon@africa.airtel.com | Ishan Arora | AMBER | Vignesh | Medium | Completed | 3 |  | 3 | 2023-05-23 | 2023-07-14 |  | 2023-08-24 | 100% | Dependency with customer. Left over sessions to be planned.
| RN-260 | Rapid 7 - IVM | NW & Sec |  | Damac - Rapid 7 |  | Damac Properties | Rajesh Narayanan | Rajesh.Narayanan@damacgroup.com | Bibinu Ajith | GREEN | Pallavi Nair | Medium | Completed | 4 | 1 | 3 | 2023-04-10 | 2023-06-30 |  | 2023-08-28 | 100% | Final documentation to be shared and get the sign off to close the project
| RN-119 | ISO Audit BCP | IntelliAssure |  | Transco - BCP |  | Transco | Khaled Omer Al Tamimi | Khaled.altamimi@transco.ae | Ayushman | GREEN | Pallavi Nair | Low | Completed | 4 | 3 | 1 |  | 2023-01-31 |  | 2023-08-31 | 100% | Two drills are done, one reporting is pending for second one. Next drill is scheduled for Sept 23
| RN-322 | ISO Audit | IntelliAssure | RNS | SAAL_ Maintenance of ISO _ August_2023 |  | SAAL | Mehboob Merchant |  | Haytham | GREEN | Pallavi Nair | Low | Completed |  |  |  |  | 2023-09-01 |  | 2023-08-29 | 100%
| RN-197 | VAPT | IntelliStrike | RNS | ES - 2023 - RAPID 7 & VAPT (4 Qtrs) |  | Emirates Steel |  |  |  | GREEN | Tanaya | Medium | Completed | [6 empty] | 2023-08-01 | 100% | Rapid 7 is closed. VAPT is ongiong. So the project is open in Zoho
| RN-258 | Network Sec | NW & Sec | RNS | Arcadia School - Peplink | Arcadia School | Uma Sankar |  | uma.sanker@alshirawi.ae | Ishan Arora Sagar Chopra | GREEN | Pallavi Nair | Medium | Completed | 2 | 0 | 2 | 0 | 2023-04-12 | 2023-10-11 | 2023-10-11 | 100% | 1% |  | Awaiitng client side readiness to start project implementation
| RN-259 | Network Sec | NW & Sec | RNS | Arcadia School - Checkpoint (RNS) | Arcadia School | Uma Sankar |  | uma.sanker@alshirawi.ae | Ishan Arora Sagar Chopra | GREEN | Pallavi Nair | Medium | Completed | 2 | 0 | 2 | 0 | 2023-04-12 | 2023-10-11 | 2023-10-11 | 100% | 1% |  | Awaiitng client side readiness to start project implementation
| RN-313 | Network Sec | NW & Sec | Vendor + RNS | Al Dhafra Checkpoint Firewall Upgrade | Al Dhafra Insurance Co PSC | Alaa Saad |  |  | Ranjit George Mathew | GREEN | Pallavi Nair | Low | On Track |  |  |  |  | 2024-07-31 | 2024-10-25 | 2024-10-25 | 100%
| RN-349 | ISO | IntelliAssure |  | Al Mana Retail - Maintenance of ISO/IEC 27001:2013 (ISMS) |  | Al Mana |  |  |  |  | NA |  | Completed | [6 empty] | 2023-05-31 | 100%
| RN-16 | VAPT | IntelliStrike | RNS | Empower - VAPT 1 |  | Empower | Zaher | Zaher.ElAli@nextcarehealth.com | Ishan | AMBER | Rubeena | Low | Completed | 2 | 1 | 1 | 2023-11-11 | 2023-07-17 |  | 2023-09-20 | 100%
| RN-191 | ForcePoint, FP | NW & Sec | RNS | ALDAR - Forcepoint, DLP |  | ALDAR | Rakesh Narang | rnarang@aldar.com | Bibinu Ajith | RED | Sean Faizal | High | Completed | 3 | 0 | 3 | 2023-01-17 | 2023-06-16 |  | 2024-01-15 | 100% | Email is being excluded from the scope. Rest implementation is complete, wtg for sign-off
| RN-228/337 | Proofpoint | NW & Sec | Vendor | RTS-Proofpoint |  | RTS | Balamurugan Singaram |  | Rohit Save | GREEN | Pallavi Nair |  | Completed |  |  |  | TBD | 2023-12-15 |  | 2024-01-23 | 100% | fine tuning in progress. Sign off planned in the last week of Dec
| RN-356 | Fortinet | NW & Sec | RNS | Theodor Wille Intertrade FZE_Fortinet Q2 |  | Theodor Wille Intertrade FZE | Shrung Vachhrajani | Shrung.Vachhrajani@twipv.com | Ranjit George | GREEN | Sean Faizal | Low | Completed | 4 | 1 | 3 |  |  |  | 2024-01-26 | 100% | DUBAI SITE IS COMPLETE. Germany is completed. HO and Doc is in progress
| RN-102 | VAPT | IntelliStrike | RNS | ALDAR ACADAMICS / ADNOC SCHOOLS - VAPT |  | ALDAR | Sheik Mohaideen | sheik.mohaideen@aldareducation.com | Rohit Save | AMBER | Sean Faizal | Low | Completed | 5 | 0 | 5 | 2022-09-07 | 2023-07-27 |  | 2024-01-29 | 100% | Invoicing completed - M1, M2, M3 & M4 COMPLETED; Final Sign-off pending
| RN-238 | VAPT | IntelliStrike | RNS | Seddiqi Holding - VAPT |  | Seddiqi Holding | Prince Rana | prince.rana@seddiqiholding.com | Rohit Save | AMBER | Pallavi Nair | Medium | Completed | 4 | 4 | 0 | 2023-03-06 | 2023-11-15 |  | 2024-01-11 | 100% | Awaiting for the sign-off
| RN-331 | Checkmarx | NW & Sec | Vendor | Tawajun Industrial Park - Checkmarx solution |  | Tawazun Industrial Park | Hassan | drmhasan@watheqlab.ae | Ishan Arora | GREEN | Sean Faizal | Medium | Completed | [6 empty] | 2024-02-22 | 100% | Sign-off received on 21st Feb
| RN-279 | cybereason | NW & Sec | Vendor | Damas - Cybereason |  | Damas - Cybereason | Amit Pradhan | apradhan@damasjewellery.com | Rohit Save | AMBER | Pallavi Nair | Medium | Completed | 2 | 2 | 0 | 2023-04-29 | 2023-07-14 |  | 2024-02-26 | 100% | Close the reported issues and then ask for the sign-off
| RN-409 | Barracuda WAF | NW & Sec | Vendor | Gulf Marine Services_Barracuda WAF |  | Gulf Marines Services Company LLC | Mushtafik Hanif |  | Unnikrishnan | GREEN | Divya | Low | Completed |  |  |  |  | 2024-03-15 |  | 2024-03-08 | 100% | Sign off received on 08 March 24
| RN-309 | Akamai | NW & Sec | RNS | Mall Of Qatar_Akamai_19062023 |  | Mall of Qatar | Deepak Pradhan |  | Brejesh Bisht | GREEN | Pallavi Nair | Low | Completed | 12 | 4 | 8 | 2023-07-01 | 2024-06-01 |  | 2024-03-11 | 100% | Need not to be tracked as it is a subscription based project and ops team take care of the monthly billing
| RN-380 | ISO Consulting | IntelliAssure | RNS | OQ Trading_iso27K_aasmt_Q42023 |  | OQ Trading | Abhilash Radhadevi | abhilash.radhadevi@oq.com | Rohit Save | GREEN | Divya | Low | Completed |  |  |  | 2024-01-15 | 2024-03-22 |  | 2024-04-02 | 100% | Sign off recieved
| RN-37 | VAPT | IntelliStrike | RNS | FNG - VAPT |  | Fujairah National Group | Lalu Vijayn | lalu.v@fng.ae | Ishan Arora | AMBER | Vignesh | Low | Completed | 2 | 1 | 0 | 2021-08-16 | 2023-07-31 |  | 2024-04-16 | 100% | Awaiting for sign-off.
| RN-353 | Forcepoint | NW & Sec | RNS | ES_Forcepoint Proxy - Licenses; Professional Services_ZTNA |  | Emirates Steel | Abdelghafour | Abdelghafour.AlAli@emiratessteel.com | Bibinu Ajith | AMBER | Vignesh | Medium | Completed | 1 |  | 1 |  |  |  | 2024-04-22 | 100% | ZTNA implementation is complete. Issue fixing in progress. Sign off will be complete next week
| RN-304 | Zscaler | NW & Sec | Vendor + RNS | Deem Finance_Zscaler |  | Deem Finance | Parthasardhi | parthasarathy@deem.io | Rohit Save | AMBER | Divya | Low | Completed | 4 | 2 | 2 | 2023-09-30 | 2024-04-19 |  | 2024-04-22 | 100% | Conditional Sign-off received on 22nd with an exception that, the KT will be conducted in May and close the project fully
| RN-89 | ForcePoint-DLP | NW & Sec | RNS | AJMAN BANK - DLP & FP |  | AJMAN BANK | Thanveer Sadiq | T.Sadiq@AjmanBank.ae | Ishan Arora | GREEN | Sean Faizal | High | Completed | 4 | 2 | 2 | 2023-01-27 | 2023-08-21 |  | 2024-04-25 | 100% | sign off received on 25 Apr. Sent it for invoicing
| RN-416 | VAPT | NW & Sec | RNS | DAMAS - 4 APIs VAPT |  | Damas | Vijay | VijayM@damasjewellery.com | Rohit Save | GREEN | Vignesh | Low | Completed | 1 | 0 | 1 | 2024-03-13 | 2024-03-31 |  | 2024-04-24 | 100% | Retesting is not required. Sign off is is complete
| RN-342 | Akamai | NW & Sec | Vendor | MAF Bot Manager |  | MAF Carrefour | Jafar, Bayan (vendor) | bjafar@akamai.com | Bibinu Ajith | AMBER | Vignesh | Medium | Completed | 1 | 0 | 1 |  |  |  | 2024-05-01 | 100% | CS to check with Bibinu on the status -- payment received and project closed
| RN-3 | VAPT | IntelliStrike | RNS | Voltas - VAPT |  | Voltas | Amjad | akhan@voltas.com | Unnikrishnan | GREEN | Vignesh | Low | Completed | 1 | 0 | 1 | 2022-01-17 | 2023-07-05 |  | 2024-05-01 | 100% | Re-testing is pending. Sign off and payments are complete. NO response from customer
| RN-242 | Mimecast | Data Center | Vendor | LM Exchange-Mimecast(Vendor) |  | LM Exchange | Hareesh R S | hareesh.rs@lm-exchange.com | Rohit Save | GREEN | Vignesh | Medium | Completed | 16 | 0 | 16 | 2022-11-28 | 2023-06-26 |  | 2024-05-17 | 100% | Awaiting for sign-off
| RN-357 | Mimecast | NW & Sec | RNS | LM Exchange-Security Awareness trg |  | LM Exchange | Hareesh R S | hareesh.rs@lm-exchange.com | Rohit Save | GREEN | Vignesh | Medium | Completed | 1 |  | 1 |  |  |  | 2024-05-17 | 100% | Firewall presentation is only pending. Awaiting for customer response on the schedule for Trg
| RN-289 | VAPT | IntelliStrike | RNS | EMPOWER-VAPT_2023 |  | EMPOWER | Rajesh Rajarathnam | rajesh.rajarathnam@empower.ae | Ishan Arora | GREEN | Sean Faizal | Low | Completed | 3 | 0 | 3 | 2023-06-07 | 2023-09-06 |  | 2024-04-26 | 100% | Formal sign-off done for project closure- Invoicing has been complete
| RN-286 | VAPT | IntelliStrike | RNS | NAFFCO - VAPT |  | NAFFCO | Mankandan | manikandan.t@naffco.com | Unnikrishnan | GREEN | Vignesh | Low | Completed | 4 | 0 | 4 | 2023-04-27 | 2023-09-04 |  | 2024-05-21 | 100% | Signoff receieved on 21st May 2024.
| RN-410 | Zscaler | NW & Sec | Vendor | Seddiqui Holding - zScaler |  | Seddiqui Holding | Prince | prince.rana@seddiqiholding.com | Rohit Save | GREEN | Divya | Low | Completed | 2 | 0 | 2 | 2024-02-02 | 2024-05-16 |  | 2024-05-16 | 100% | PS completed; Awaiting sign off
| RN-239 | Sailpoint | Sailpoint | RNS | Aldar - SailPoint - CR (4 enhancements) |  | Aldar | Sunil Sharma | ssharma@aldar.com | Bibinu Ajith | GREEN | Laxmi | Medium | Completed | 2 | 1 | 1 | 2024-03-06 |  |  | 2024-05-30 | 100% | Received Sign Off
| RN-292 | VAPT | IntelliStrike | RNS | SKM - VAPT |  | SKM AirConditioning | Tayyab Haider | tayyab.haider@skmaircon.com | Faizan Javed | GREEN | Vignesh | Low | Completed | 4 | 0 | 4 | 2023-01-06 | 2023-08-14 |  | 2024-05-27 | 100% | 24/5 - out of 3 milestones, 2 milestones has been closed, payment recieved.
| RN-231 | VAPT | IntelliStrike | RNS | DWTC VAPT 2022 |  | DWTC | Faisal | Faisal.Khan@dwtc.com | Ishan Arora | GREEN | Vignesh | Medium | completed | 3 | 2 | 1 | ###### | 2023-07-31 |  | 2024-05-30 | 100% | 30may - Signoff recieved
| RN-237 | VAPT | IntelliStrike | RNS | INTERPLAST - VAPT 2023 |  | INTERPLAST | Sabu John Bosco | Sabu@interplast-uae.com | Ranjit George | GREEN | Sean Faizal | Medium | Completed | 3 | 0 | 3 | 2023-03-27 | 2023-08-04 |  | 2024-05-31 | 100% | Sign off Acknowledgement pending
| RN416 | VAPT | IntelliStrike | RNS | DAMAS Jewelery |  | DamasJewellery | Amit Pradhan | apradhan@damasjewellery.com | Rohit Save | GREEN | Vignesh | Low | Completed | 3 |  | 3 |  |  |  | 2024-06-06 | 100% | Sign off initiated of 28th May; Awaiting for sign off
| RN-329 | ISO Consulting | IntelliAssure | RNS | DPW_ISO 27001_Consulting_Q3_2023 |  | DP World | Mariam Mazrouqui |  |  | GREEN | Divya | Low | Completed |  |  |  | 2023-10-10 | 2024-06-24 |  | 2024-04-26 | 100% | Sign off recieved
|  | PICUS | NW & Sec | RNS | RAK Bank - Picus |  | Rak Bank |  |  |  | GREEN | Vignesh | Low | Completed |  |  |  |  | 2024-05-25 |  | 2024-05-25 | 100% | License renewal has been done
|  | Opswat | NW & Sec |  | Mashreq Bank - Opswat |  | Mashreq Bank |  |  | Sagar | GREEN | Vignesh | Low | Completed | [6 empty] | 2024-06-27 | 100% | License delivery, need to confirm with Sean on whether it is a renewal
| RN-277 | ForcePoint, DLP | NW & Sec | RNS | Emrill - ForcePoint DLP |  | Emrill | Atif Riaz | Atif.Riaz@emrill.com | Rohit Save | AMBER | Vignesh | Medium | Completed | 6 | 6 | 0 | 2023-01-02 | 2023-07-10 |  | 2024-07-08 | 100% | Identified gaps are being fixed. Sign-off is expected on may 3rd tentatively. 2/7 - Signoff of email has been recieved. Waiting for Divya/JP to confirm on the closure
| RN-359 | Fortinet | NW & Sec | Vendor | Fortinet NAC & FortiSIEM |  | Property Finder | Sameh | sam@propertyfinder.ae | Abu Hasna | GREEN | Pallavi Nair | Medium | Completed | [6 empty] | 2024-07-05 | 100% | Project re-opened on 02 Apr 24. All open issues are closed. Handover completed.
| RN-369 | Logrythm | NW & Sec | Vendor | ADJD LogRhythm Licenses Renewal & appliance & PS |  | ADJD | Belal Abdullah | b.salmeen@adjd.gov.ae | Haytham | GREEN | Vignesh | Medium | Completed | 1 | 1 | 0 |  | 2024-03-31 |  | 2024-07-31 | 100% | 26/07 - Closed
| RN-381 | Sailpoint | Sailpoint | RNS | EDC_Sailpoint Implementation |  | Emirates Driving Company | Sachin | Sachin@edcad.ae | Komal | GREEN | Laxmi | Medium | Completed | 3 | 1 | 2 | ###### | 2024-02-28 |  | 2024-07-30 | 100% | RBAC in progress,6 apps live
| RN-405 | Palo Alto | NW & Sec | RNS | Intigral - Palo Alto Only PS |  | Intigral ME | Anup Nellippily/Abdul Rahman | Anup.Nellippily@intigral.net | Ishan Arora | GREEN | Divya | Medium | Completed | 2 | 2 |  | 2024-02-14 | 2024-04-08 |  | 2024-08-20 | 100% | Sign off recieved
| RN-276 | PAM | Sailpoint | Vendor | Damas Arcon |  | Damas Arcon | Amit Pradhan | apradhan@damasjewellery.com | Faizan | GREEN | Pallavi Nair | Medium | Completed | 4 | 1 | 3 | 2023-04-10 | 2024-05-28 |  | 2024-05-28 | 100% | Signoff received, only DR activity is remaining, awaiting confirmation from Damas team regarding DR readiness to complete the same.
| RN-462 | VAPT | VAPT | RNS | DAMAS - VAPT July24 |  | Damas | Amit Pradhan | apradhan@damasjewellery.com | Komal | GREEN | Vignesh |  | Completed |  |  |  | 2024-07-30 | 2024-08-21 |  | 2024-08-21 | 100% | Signoff recieved on 21st Aug 24.
| RN-435 | CheckPoint | NW & Sec | RNS | CWT-SML LOGISTICS LLC | Firewall replacement | CWT Logistics | Rajesh |  | Unnikrishnan | AMBER | Sean Faizal | Medium | Completed |  |  |  | 2024-06-20 | 2024-07-11 |  | 2024-08-18 | 100% | project complete, signoff recieved
| RN-427 | Fortinet | NW & Sec | RNS | MBRSG FireWall Reconfiguration | 501E - Reconfig 601F - Reconfig & relocation VPN Config - 4 sites | MBRSG | Anthony Bartolo | anthony.bartolo@mbrsg.ac.ae | Ishan Arora | GREEN | Sean Faizal | Low | Completed | 3 | 3 | 0 | ###### | 2024-06-10 |  | 2024-08-18 | 100% | Signoff Sign-off recieved
| NEW | Crowdstrike | NW & Sec | RNS | Gulf Cryo Crowdstrike | Gulf Cryo |  |  |  | Ishan Arora | GREEN | Vignesh | Low | Completed | [8 empty] | Roll out is done by customer, can be closed
| RN-436 | Tenable | NW & Sec | RNS | ADDOF Tenable.sc | Tenable .se Migration |  |  |  | Bibinu Ajith | GREEN | Sean Faizal |  | Completed |  |  |  | 2024-06-20 | 2024-07-28 |  | 2024-08-30 | 100% | Project tasks complete, signoff to be initiated
| RN-341 | Cybereason | NW & Sec | RNS | Waha Health - CyberReason PS - 4 Days | Waha Health | Asam |  | asam.m@wahahealth.com | Ayushman | GREEN | Pallavi Nair | Low | Completed |  |  |  | 2023-09-08 | 2023-10-03 | 2023-11-15 | 2023-12-27 | 100% | Awaiting for sign-off
| RN-296 | VAPT | IntelliStrike | RNS | Gulf Cryo - VAPT | Gulf Cryo | Zain Javed |  | zjaved@gulfcryo.com | Ishan Arora | GREEN | Vignesh | Low | Completed | 3 | 1 | 2 | 2023-07-03 |  |  | 2023-01-12 | 90% | Two web apps are pending under retesting. Conditional sign-off received.
| RN-239 | Sailpoint | Sailpoint | RNS | Aldar_Sailpoint_PS_CR_Nov_2023 (Enhancements CR), Manage Engine CR (Aug 23) & HCM API Integration CR (Sep 23) | Aldar | Sunil Sharma |  | ssharma@aldar.com | Bibinu Ajith | GREEN | Vignesh | Medium | Completed | 2 | 2 |  |  | 2023-12-15 |  | 2023-12-29 | 100% | Sign-off has been asked - Enghancements CR (CR 3) Manage Engine CR - Closed (CR 1) HCM API Integration - Closed (CR 2)
| RN-78 | Sailpoint | Sailpoint | RNS | DLD SAILPOINT | Dubai Land Department | Khalid |  | khalidmk@dubailand.gov.ae | Sagar Chopra | GREEN | Tanaya | Low | Completed | 4 |  | 4 | 2021-12-06 | 2023-07-31 |  | 2024-01-05 | 100% | Project sign-off complete Compliance Manager Reports demo is pending, which is impacting the Go-Live
| RN-122 | Sailpoint | Sailpoint | RNS | ADCB - SailPoint Phase 1 | ADCB | Jeny |  | JenyAnniePhilip.ext@adcb.com | Sagar Chopra | RED | Tanaya | Medium | On Hold | 12 | 10 | 2 | 2021-05-24 | 2023-09-29 |  | 2023-09-29 | 66% | 3 App sign-off received. ECAMS is pending for sign-off. Mover UAT testing is pending with ADCB. Project is on hold. Phase 2 to be discussed and agreed
| RN-254 | Sailpoint | Sailpoint | RNS | Digital 14 - SailPoint | Digital 14 (Katim) | Maddi Siva |  | Maddi.Prasad@katim.com | Ishan Arora | GREEN | Tanaya | Low | Completed | 3 | 2 | 1 | 2023-04-03 | 2023-09-29 |  | 2024-01-15 | 100% | Dec will be last month. Sign off will be received in first week of Jan 24 New PO received on 11 Dec from 03 OCT TO 31 DEC. Contract is getting renewed for one year
| RN-401 | Sailpoint | Sailpoint | RNS | Mashreq Sailpoint CR - Dec 23 | MASHREQ BANK | Rajesh Gurikar |  |  | Ishan Arora | GREEN | Sean Faizal | Low | Completed | 1 | 1 |  |  | 2024-01-24 |  | 2024-02-10 | 100%
| RN-379 | Tenable | NW & Sec | Vendor | DLD - Tenable VM | DLD | Abdulla Yalooq |  | alyalooq@dubailand.gov.ae | Ishan Arora | GREEN | Tanaya | Medium | Completed | 2 | 2 |  | 2023-12-11 | 2024-01-05 | 2024-01-15 | 2024-01-28 | 100% | Implementation in progress
| RN-239 | SailPoint | Sailpoint | RNS | Aldar - SailPoint - Phase 1 | Aldar | Sunil Sharma |  | ssharma@aldar.com | Bibinu Ajith | GREEN | Laxmi | Medium | Completed | 5 | 3 | 2 | 2023-01-20 | 2023-11-10 |  | 2023-11-10 | 100% | Phase 1 is complete and sign off received. Phase 2 will resume from Apr 24
| RN-185 | Sailpoint | Sailpoint |  | Intigral - Sailpoint (Phase 1 & 2) |  | Intigral | Anup | Anup.Nellippily@intigral.net | Ishan Arora | GREEN | Laxmi | Low | Completed | 5 | 2 | 3 | 2022-11-15 | 2023-08-07 |  | 2023-08-07 | 90% | Conditional Sign-off received for Phase 1. 2 Apps were moved to Phase 2 (10 apps in the scope). Reqmt gathering for 2 apps is complete.
| RN-411 | Barracuda Email Sec | NW & Sec | RNS | Providence - Barracuda Email Security | Providence | Mujahed Khan |  |  | Komal | GREEN | Vignesh | Low | Completed | 1 | 1 |  | 2024-02-21 | 2024-03-08 |  | 2024-03-08 | 90% | As Build doc is being developed. Sign off will be complete by 8th March
| RN-370 | FireEye | NW & Sec | Vendor | ADJD FireEye WEB MPS Licenses & Appliance | ADJD | Belal Abdullah |  | b.salmeen@adjd.gov.ae | Haytham | GREEN | Vignesh | Medium | Completed | 1 | 1 |  |  | 2024-01-31 |  | 2024-03-15 | 100% | Upgrade is complete. Sign-off will be initiated in the WE 15 Mar 24
| RN-377 | Rapid 7 | NW & Sec | RNS | WIG - Nesto - RAPID7_INSIGHT IDR_SEPT_2023 | Western International Group - Nesto | Raveesh P |  | raveesh.p@westernint.com | Ranjit George | GREEN | Vignesh | Medium | Completed | 1 | 1 |  | 2023-11-14 | 2024-01-31 |  | 2024-03-15 | 90% | Conditional sign-off submitted with SOAR pending. Wtg for customer response.
| RN-378 | Managed Services | NW & Sec | RNS | MBRSG_Securonix | MBRSG | Anthony |  | anthony.bartolo@mbrsg.ac.ae | Rohit Save | GREEN | Pallavi Nair | Medium | Completed | 6 | 6 |  | 2023-11-10 | 2024-01-15 |  | 2024-03-15 | 100% | Documentation review is pending. Ready for sign-off.
| RN-312 | FW - F5 WAF | NW & Sec | Vendor + RNS | ES_F5 Networks | Emirates Steel | Abdelghafour |  | Abdelghafour.AlAli@emiratessteel.com | Bibinu Ajith | GREEN | Tanaya | Low | Completed | 1 |  | 1 |  | 2023-10-02 |  | 2024-03-22 | 90% | As-Build is pending. Post as-bild, sign-off will be asked
| RN-19 | CyberArK | CyberArK | RNS/Vendor | DOH - Cyberark | DOH | Nahas |  | Bibinu Ajith | nnizar@doh.gov.ae | AMBER | Pallavi Nair | High | Completed | 15 | 4 | 11 | 2021-08-31 | 2024-05-31 | 2024-09-12 | 2024-09-12 | 100% | Received project signoff
| RN-371 | Sailpoint | Sailpoint | RNS | AXA_Gulf Insurance Group – SailPoint + CR (7 CRs) |  | Axa(Formely GIG) | Rahul Banga | rahul.banga@gig-gulf.com | Ishan Arora | GREEN | Laxmi | Medium | Completed | 2 | 2 | 0 | 2023-10-01 | 2024-03-31 | 2024-06-30 | 2024-09-20 | 100% | Conditional sign-off mail received. 7 CRs were raised during implementation. 4 are done and 3 in progress. Can be closed once the three CRs are complete. Customer to confirm their readiness to execute these 3 CRs. Invoicing is complete.
| RN-371 | Sailpoint | Sailpoint | RNS | AXA_Gulf Insurance Group – SailPoint Upgrade 8.1 to 8.3p3(Now) & 8.4(Once it is stabilized) |  | AXA_Gulf Insurance Group | Rahul Banga | rahul.banga@gig-gulf.com | Ishan Arora | GREEN | Laxmi | Medium | Completed | 2 | 0 | 2 | 2023-12-21 | 2024-01-19 |  | 2024-09-20 | 100% | Upgrade is complete. Mail Conditional Sign off received for UAT. Prod is also complete. Testing is going on. Document sign-off is pending
| RN-428 | Forcepoint | NW & Sec | RNS | Deem Finance_Forcepoint |  | Deem Finance | Parthasardhi M | parthasarathy@deem.io | Bibinu | GREEN | Divya | High | Completed | 3 | 2 | 1 | 2024-04-04 | 2024-06-28 |  | 2024-06-28 | 100%
| RN-283 | Manage Engine | NW & Sec |  | RAK Customs Manage Engine | Rak Customs | RAK Customs anage Engine | Khulood Jumah Al Keebali |  | k.alkeebali@customs.rak.ae | AMBER | Pallavi Nair | Medium | Completed | 5 | 0 | 0 | 2023-05-15 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 100%
| RN-291 | ISO SDLC | IntelliAssure | RNS | Saal-SDLC (Consultation Services for Implementation of SDLC) |  | Saal | Mehboob Merchant | mehboob@saal.ai | Haytham | GREEN | Divya | Medium | Completed | 2 | 1 | 1 | 2023-06-16 | 2023-08-30 | 2024-07-15 | 2024-10-13 | 100% | SIgn off recieved
|  | PulseSecure | NetSec | Vendor | NextCare-PulseSecure | NAC Deployement | Nextcare | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Ishan | GREEN | Sean Faizal | Low | Completed | 3 | 0 | 3 | NA | 20-09-24 |  | 2024-09-20 | 100%
| RN-252 | VAPT | IntelliStrike | RNS | EPC-VAPT_2023 |  | EMIRATES POLICY CENTER | Jinson Pappachan | jinson@epc.ae | Ranjit George | GREEN | Sean Faizal | Low | Completed | 2 | 0 | 2 | 2023-04-06 | 2024-02-07 | 2024-08-30 | 2024-10-29 | 100% | Conditional sign-off recieved | delay from Customer
| RN-18 | Sailpoint | Sailpoint | RNS | DOH - Sailpoint |  | DOH | Prashant, Ashwaq | paley@doh.gov.ae, asalameri@doh.gov.ae | Bibinu Ajith | AMBER | Pallavi Nair | High | Completed | 10 | 9 | 1 | 2019-08-15 | 2023-07-20 |  | 2023-07-20 | 83% | On hold due to their infra getting migrated to G42 cloud. Invoicing is complete. 12 Apps. Customer dependancies for full closure. UAT is done. JML UAT sign-off is pending. Customer in principle, agreed for full sign-off. JPto go onsite with Bibinu to talk to customer and get the sign-off.
| RN-366 | Sailpoint | Sailpoint | RNS | NISailPoint_SouthAfrica_Sept_2023 |  | Network International | Fuard Saban | Fuard.Saban@network.global | Ishan Arora | GREEN | Pallavi Nair | Medium | Completed | 8 | 0 | 8 | 2023-10-25 | 2024-07-29 |  | 2024-12-02 | 100%
| RN-308 | CyberArk | Sailpoint | Vendor + RNS | ADNEC CyberArk |  | ADNEC |  | Mohamed Al Hosani | Mohamed.alhosani@adnec.ae | AMBER | Pallavi Nair | Medium | Completed | 17 | 3 | 14 | 2023-09-18 | 2024-07-31 |  | 2024-12-05 |  | EPM Pending, awaiting customer confirmation
| RN-459 | CyberArk | Sailpoint | RNS and CyberArk | ZMI CyberArk |  | ZMI | Ahmed Hossam | Hossam.ahmed@zmiglobal.com | Sanjay | GREEN | Pallavi Nair | Medium | Completed | 11 | 0 | 11 | 2024-07-17 | 2024-09-10 |  | 2024-11-12 | 100%
| RN-478 | Audit | Network Security | RNS | Intigral - GRC | Audit - GRC | Intigral | SaiKumar Kodam | saikumar.kodam@intigral.net | Ishan Arora | GREEN | Ajinkya | Low | Completed | 3 | 0 | 3 | 2024-09-18 | 2024-11-19 |  | 2024-11-19 | 100% | Project is complete.
41 | RN-405 | Palo Alto | NW & Sec | RNS | INTIGRAL - PaloAlto_Renewal_PS/AMC_Jan_2024 |  | Intigral ME | Binu Mathew | Binu.Mathew@intigral.net | Ishan Arora | GREEN | Divya | Low | Completed | 2 | 0 | 2 | 2024-02-13 | 2024-11-25 |  | 2024-11-25 | 100% | Completed
56 | RN-395 | VAPT | IntelliStrike | RNS | Gulf Cement_GCC_VAPT_RAK |  | Gulf Cement Company | Ajeet Ahire | Ajeet@gulfcement.ae | Manish Narayanan | GREEN | Vignesh | Low | Completed | 3 | 1 | 2 | 2023-12-19 | 2024-03-31 |  | 2024-11-25 | 100% | 25/11 - Completed | Delay from Customer
94 | RN- 22 | Sailpoint | Sailpoint | RNS | DIB |  | DIB | Shinu | Shinu C George (IT Dept) <Shinu.George@dib.ae> | Sagar Chopra | GREEN | Laxmi | Medium | Completed | 4 | 1 | 3 | 2021-07-05 | 2022-02-12 |  | 2024-11-15 | 96% | sign off pending for Sharepoint , Jira |  |  | project commpleted, signoff pending
44 | RN-421 | Darktrace | NW & Sec | Vendor | Seddiqui Holding - Darktrace |  | Seddiqui Holding | Prince | prince.rana@seddiqiholding.com | Ashida | AMBER | Divya | Medium | Delayed | 1 | 1 | 0 | 2024-03-25 | 2024-05-30 |  | 2024-05-30 | 90% | Deployment & configuration completed; Awaiting sign off
54 | RN-368 | Solarwinds | NW & Sec | RNS | Beema Insurance - Solarwinds NMC |  | Beema Insurance | Wasif Khan | mohammed.wasif@beema.com.qa | Deepinder Singh | GREEN | Vignesh | Medium | Completed | 3 | 1 | 2 | 2023-11-01 | 2023-11-30 |  | 2024-01-04 | 86% | NCM issues reported and are being fixed(Product limitation issue). Conditional sign-off received. 10/5 - Wilard is working with Solarwinds to get issue sorted; Meeting to be scheduled with customer by Wilard Customer needs to get a demo license for Fortinet Devices so we can simulate the issue again in SolarWinds NCM 27/06 - Customer waiting for VM license. 28/8 - Solarwinds and Beema Insurance working together to solve the issue | Delay from Customer & Vendor
50 | RN-317 | VAPT | IntelliStrike | RNS | Ajman Chamber of Commerce & Industry |  | Ajman Chamber of Commerce & Industry | Shams | shams@ajmanchamber.ae | Haytham | GREEN | Vignesh | Low | Completed | 0 | 0 | 0 | 2023-08-10 |  |  | 2024-07-08 | 99% | Re-testing in completed for Internal NW& Ext Web App. Conditional sign-off received; Internal network report has to be shared with customer 13/05 - Had spoke with customer, he will check with his team and revert. 21/05 - SIgnoff initiated; Awaiting for sign off 27/06 - Following up with customer for a month to get signoff. 3/07 - Signoff email have sent to customer | Delay from Customer
| RN - 383 | Sailpoint | Sailpoint | RNS | NI Egypt |  |  | Karim Arafa | karim.arafa@network.global> | Sagar Chopra | GREEN | Pallavi Nair | Medium | Completed | 9 | 7 | 2 | 2023-01-15 | 2024-07-26 |  | 2024-12-11 | 58% | 3 Apps UAT is complete. 7 Enhancemnets are complete. Remaining scope has been descoped.
109 | RN - 481 | Sailpoint | SailPoint | RNS | ZAND - SailPoint Enhancement |  | ZAND Bank | Abiodun Afolabi | Abiodun.Afolabi@zand.ae | Sagar Chopra | GREEN | Ajinkya | Medium | Completed | 4 | 0 | 4 | 2024-09-30 | 2024-10-23 |  | 2024-12-11 | 100% | Received signoff on 11th Dec
| RN-485 | CyberArk | CyberArK | RNS | Presidential Flights |  | PF | Malik |  | Haythem | GREEN | Laxmi | Low | Completed | 2 | 1 | 1 | 2024-10-15 | 2024-11-30 |  | 2024-11-30 | 99% | sign off pending
|  | Sailpoint | SailPoint | RNS | Airtel Ph-2 | Ashok | Airtel |  | ashok1.muthu@africa.airtel.com | Sagar Chopra | GREEN | Laxmi | High | Completed | 5 | 5 | 0 | 2024-06-02 | 2024-09-03 |  | 2024-09-03
| RN -375 | CyberArK | CyberArK | RNS | ADEK - CyberArk |  |  |  |  | Haytham | AMBER | Pallavi Nair | Medium | Completed | 6 | 1 | 5 | 2023-11-02 | 2024-07-19 |  | 2024-12-13 | 100 | Signoff pending
81 | RN-447 | VAPT | IntelliStrike | RNS | Gulf Cryo - VAPT 2024 |  | Gulf Cyro | Zain Javed | zjaved@gulfcryo.com | Ishan Arora | GREEN | Vignesh | Medium | Completed |  |  | 0 | 2024-07-10 |  | TBD | 2024-12-23 | 100% | Web application assessment in progress. 28/08 - Two Web app assessment completed. Customer to share one web app and Internal APIs details to perform assessment 19/09 - Customer doesn't want to perform Internal APIs assessments. One more web assessment to be initiated 9/10 - Phase 1 signoff recieved
| RN-307 | Cybereason | NW & Sec | Vendor | DWTC - Cybereason |  | DWTC |  |  |  | GREEN | Pallavi Nair | Low | Completed | 4 | 0 | 4 | 2023-01-18 | 2024-11-07 |  | 2024-11-07 | 100%
| RN-375 | CyberArk | Sailpoint | RNS | ADEK - CyberArc |  | ADEK | Steve Simpson | steve.simpson@adek.gov.ae | Haytham | AMBER | Pallavi Nair | Medium | Completed | 6 | 0 | 6 | 2023-11-02 | 2024-07-19 | 2024-12-13 | 2024-12-31 | 100%
| RN-254 | Sailpoint | IntelliDeploy | RNS | Digital 14 (Katim) - SailPoint |  | Digital 14 (Katim) | Maddi | Maddi.Prasad@katim.com | Ishan Arora | GREEN | Pallavi Nair | Low | Completed |  |  |  | 2024-01-01 | 2024-12-31 |  |  | NA
RN-460 | VAPT | VAPT | IntelliStrike | RNS | SWSC - VAPT |  | Sharjah Womens Sports council | Faizan | benon.kurian@sws.gov.ae | Benon | GREEN | Vignesh | Medium | Completed |  |  | 0 | 2024-07-29 | 2024-11-21 |  | 2024-12-27 | 100% | kickoff done on 29th July Phase 1 assessments in progress 28/08 - Web app assessment to be initiated, waiting for customer to share creds to commence 20/09 - Web app assessment was completed. Phase 1 signoff has been shared 07/10 - Phase 1 of received. Remediation support to be provided
31 | RN-398 | Data Center | Data Center | Vendor + RNS | DAMAAC_OT& IT_Saudi |  | DAMAAC | Dileep/Mahantesh |  | Bibinu Ajith | GREEN | Divya | Medium | On Track |  |  | 0 | 2024-07-01 | 2024-11-08 |  |  | 100% | sign off recieved
87 | RN-458 | Blackberry | NW & Sec | Vendor | Tawazun Council - Blackberry workspace upgrade |  | Tawazun Council | Ishan |  |  | GREEN | Vignesh | Low | Completed |  |  | 0 | 2024-07-17 | 2024-10-30 |  | 2025-01-16 | 100% | 16/Jan - Signoff recieved
115 | RN-490 | Barracuda | NW & Sec | RNS | Gulf Cement - Barracuda |  | Gulf Cement |  |  | Manish | GREEN | Vignesh | Medium | completed | 3 | 3 |  | 2024-11-22 | 2024-12-05 | 2025-01-16 | 2025-01-29 | 100% | 29/1/25 - Project signoff reicved
| RN - 470 | Sailpoint | Sailpoint | RNS | ADCB - SAP SuccessFactor and IAM Enhancement |  | ADCB | Abhishek Tripathi | Abhishek.Tripathi@adcb.com | Sagar Chopra | GREEN | Ajinkya | High | Completed | 3 | 0 | 3 | 2024-09-04 | 2024-10-31 | 2025-02-06 |  | 100% | Completed, signoff received on 6th Feb
5 | RN-236 | Zscaler | NW & Sec | Vendor | MASHREQ - zScalar | MASHREQ BANK | Prashant | prashantd@mashreq.com | Ishan Arora |  | GREEN | Sean Faizal | Medium | Completed | 3 | 1 | 2 | 2022-06-20 | 2023-06-30 | TBD | 80% | USA cinfiguration on hold due to internal dependency at mashreq - project to resume upon implmemntation of VSE from the ZT project
6 | RN-112 | FireEye | NW & Sec | Vendor | MASHREQ - FireEye |  | MASHREQ BANK | Satish Kumar | SatishKumarK@mashreq.com | Ishan Arora | GREEN | Sean Faizal | Medium | On Hold | 8 | 1 | 7 | 2022-06-20 | 2023-05-31 | TBD |  | 95% | Project in closure stage, customer to provide availability to prepre documentations | Delay from Customer
12 | RN-397 | Forcepoint RBI | NW & Sec | RNS | DIB - Forcepoint RBI |  | Dubai Islamic Bank DIB | Mohammed Abdullah |  | Ishan Arora | GREEN | Sean Faizal | Low | Completed | 4 | 0 | 4 | 2024-01-30 | 2024-04-30 | 2024-07-27 |  | 100% | awaiting signoff acknowledment
9 | RN-384 | MS Automation | NW & Sec | Vendor | Microsoft Automation - MAAN |  | Authority of Social Contribution - MAAN | Mohamed Ramadan | mohamed.ramadan@maan.gov.ae | Haytham | GREEN | Sean Faizal | High | Completed | 3 | 0 | 3 | 2024-01-16 | 2024-07-12 | 2025-01-30 | 2025-01-30 | 100% | Phase 1 complete, sign-off recieved | Delay from Vendor and Customer
71 | RN-440 | Nazomi | NW & Sec | Vendor | AD Louvre - Nazomi | Nazomi gaurdian platform implementation | Abu Dhabi Louvre | Nazem Yahia | NElArjah@Louvreabudhabi.ae | Haytham | GREEN | Sean Faizal | Low | Completed | 4 | 1 | 3 | 2024-06-12 | 2024-10-15 | 2024-11-15 | 2024-12-17 | 100% | Sign-off received, Project clossure meeting planned
101 | RN-464 | Checkmarx | AppSec | Vendor | ESA-Checkmarx | CXOne deployment | Emirates Steek Arkan | Mohamad Hamdan |  | Bibinu Ajith | GREEN | Sean Faizal | Low | Completed | 3 | 0 | 3 | 2024-08-19 | 2024-09-30 | 2025-01-30 | 2025-01-30 | 100% | Sign-off initiated
57 | RN-402 | VAPT | IntelliStrike | RNS | Balmer Lawrie - VAPT | VAPT | Balmer Lawrie | Pradeep Kotagar | pradeep.k@balmerlawrie.ae | Manish Narayanan | GREEN | Vignesh | Low | Completed | 3 | 1 | 2 | 2024-01-04 | 2024-04-15 | TBD | 2025-02-20 | 100% | Signoff recieved on 20th Feb | Delay from Customer
97 | RN-472 | VAPT | IntelliStrike | RNS | DNIR - VAPT | DNI | DNI | Saju | saju.pv@dni.ae | Faizan | GREEN | Vignesh | Medium | Completed | 1 | 0 | 1 | 2024-08-28 | 2024-09-28 | 2025-02-28 | 2025-02-26 | 100% | 26/2 - Signoff recieved
10 | RN-362 | VAPT | NW & Sec | RNS | Nextcare VAPT |  | Nextcare | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Haytham | GREEN | Sean Faizal | Low | Completed | 1 | 1 | 0 | 2024-01-01 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 100% | Consumed 50 days out of 50, 10 Apps tested | Assessment will be performed based on the customer requirement
| RN-446 | Sailpoint | Sailpoint | RNS | Mashreq Bank sailpoint- phase 3 |  | Mashreq Bank | Nagesh | NageshD@mashreq.com | Sagar Chopra | GREEN | Pallavi Nair | Medium | Completed | 2 | 0 | 2 | 2024-11-25 | 2024-12-09 | 2025-01-22 | 2025-01-22 | 100%
| RN - 499 | Palo Alto | Nw & Sec | RNS | Nextcare Palo Alto_ Oman |  | Nextcare | Zaher El Ali | Zaher.ElAli@nextcarehealth.com | Ishan Arora | GREEN | Ajinkya | Medium | Completed | 1 | 0 | 1 | 2024-12-10 | 2025-02-28 | 2025-03-03 | 2025-04-07 | 100% | Project completed. Signoff received on 7 April
| RN-371 | Sailpoint | Sailpoint | RNS | AXA Sailpoint 8.4 upgrade |  | AXA | Rahul Banga | rahul.banga@gig-gulf.com | Ishan Arora | GREEN | Ajinkya | low | Completed | 2 | 0 | 2 | 2025-02-03 | 2025-03-28 | 2025-04-11 |  | 100% | Go live completed. Signoff shared on 2 April
76 | RN - 444 | Zscaler | NW & Sec | RNS | Amico Group - Zscaler |  | Amico | Jurageswaran | jshetty@amicogroup.com | Manish Narayanan | GREEN | Vignesh | Medium | Completed | 8 | 8 | 0 | 2024-07-01 | 2024-07-19 | TBD | 2025-04-09 | 99% | Payment milestones are completed. Waiting for the signoff
| RN-307 | Cybereason | NW & Sec | Vendor | DWTC - Cybereason | DWTC | DWTC | Faisal Khan |  | Ishan Arora | Ishan | Pallavi Nair | Pallavi Nair | Completed | 4 | 0 | 4 | 2023-01-18 | 2024-11-07 |  | 2024-11-07 | 100%

## Closed PS Projects (hidden)
PROJECT MANAGEMENT LOG TEMPLATE
PROJECT REGISTER
The PROJECT Identification portion of this table will automatically populate to the Financial Data, Deliverables and Performance, and Risk Register tabs within this workbook.
| PROJECT DATA |  |  |  | CUSTOMER DATA |  |  | ACCOUNT DATA |  | PROJECT MANAGEMENT | [5 empty] | TERMS
| NO. | PROJECT ID | Project Type | Tower | Led By | PROJECT NAME | CUSTOMER NAME | CUSTOMER SPOC NAME | CUSTOMER SPOC EMAIL | ACCOUNT MANAGER NAME | ACCOUNT HEALTH | INTERNAL | PROJECT COMPLEXITY | Status | Completed Date | Total Milestones | Milestones Open | Milestones Closed | START | END | Revised End Date | Actual End Date | % Completion | REMARKS | Rekha comments
[12 empty] | PROJECT MANAGER | [6 empty] | DATE | DATE
| 1 | RN-20 | VAPT | IntelliStrike |  | Sentinal - VAPT | Sentinel Capital | Faheem | Faheem.Kausar@sencap.com | Rohit Save | GREEN | Tanaya | Low | Completed |  | 3 | 1 | 2 | 2021-08-16 | 2023-08-31 |  |  | 54% | Delayed due to unresponsive customer
| 2 | RN-274 | Sailpoint | Sailpoint |  | NI External Client Build - IIQ | NI | Fuard | Fuard.Saban@network.global | Ishan Arora | GREEN | Rubeena | Low | Completed |  | 1 | 0 | 1 | 2023-04-03 | 2023-06-19 |  | 2023-06-19 | 100% | Sign-off received on 19th Jun. Invoicing complete. Check with Manasi
| 3 | RN-105 | Sailpoint | Sailpoint |  | PHCC(Phase1)Sailpoint | PHCC | Sahil | sbhugra@phcc.gov.qa | Brejesh | GREEN | Rubeena | Low | Completed |  | 5 | 1 | 4 | 2023-06-23 | 2023-07-14 |  | 2023-03-01 | 96% | Project signoff Received, Testing pending for outsourced employee. External dependancy for the testing (customer to give the schedule)
| 4 | RN-253 | Checkpoint | NW & Sec |  | AL ZAHRA - Checkpoint (Vendor) | AL ZAHRA | Iftequar Hussain | iftequar.h@azhd.ae | Rohit Save | GREEN | Sean Faizal | Low | Completed |  | 1 | 0 | 1 | 2023-05-26 | 2023-06-05 | 2023-07-14 | 2023-07-10 | 100% | Invoicing is done. Will check with Rekha to close it
| 5 | RN-6 | VAPT | IntelliStrike |  | Al Jazeira Services - VAPT | Aljazeira Services | Murugesan Pugazhendi | Murugesan.Pugazhendi@glserve.com | Bibinu Ajith | GREEN | Pallavi Nair | Low | Completed |  | 3 | 0 | 3 | 2022-08-26 | 2023-06-19 | 2023-07-14 |  | 99% | Sign-off received on 10 July 23
| 6 | RN-27 | IA ITSM |  |  | Albatha - ISO 20K | Albatha | Anirudh Tulsidas Shetty | Anirudh@albatha.com | Rohit Suresh Save | GREEN | Pallavi Nair | Low | Completed |  | 3 | 0 | 3 | 2023-05-09 | 2023-06-21 | 2023-07-17 |  | 99% | Delvierables are complete and payment received.
| 7 | RN-318 | VAPT | IntelliStrike |  | ECCSC_VAPT_Web & Sec Assessement_Load Testing | Emirates Centrol Cooling System Corp |  | Emirates Small Scope - VAPT |  | GREEN | Rubeena | Low | Completed | [6 empty] | 2023-08-07
| 8 | RN-288 | VAPT | IntelliStrike |  | Damas API Testing - VAPT | Damas | Amit Pradhan | apradhan@damasjewellery.com | Rohit Save | GREEN | Tanaya | Low | Completed |  | 2 | 1 | 1 | 2023-06-01 | 2023-07-14 | 2023-08-09 |  | 50% | Retesting is pending
| 9 | RN-282 | FW - Fortigate | NW & Sec |  | Dubai Sports Council-Fortigate | Dubai Sports Council | Mohammed Ashhar | armohammed@dubaisc.ae | Faizan Javed | GREEN | Vignesh | Medium | Completed |  | 3 | 3 |  | 2023-05-26 | 2023-08-01 | 2023-08-14 |  | 15% | Configuration of the FW is in progress
| 10 | RN--23 | ForcePoint, FP | NW & Sec |  | DLD- Bolden James & Forcepoint | DLD | Rambhul | rambhul.singh@dubailand.gov.ae | KD | AMBER | Rubeena | Low | Completed |  | 2 | 1 | 1 | 2021-03-11 | NA |  |  | 61% | Client dependancy. Product is discarded. Written confirmation is accorded from customer
| 11 | RN-25 | Rapid 7 | NW & Sec |  | Gulf Drug - SIM, SOC, VAPT | Gulf Drug | Vijay | Vijay@gulfdrug.com | Ayushmann | AMBER | Tanaya | Medium | Cancelled |  | 4 | 4 | 0 | 2022-08-05 | 2023-08-31 |  |  | 70% | Client to give go-ahead to start the project
| 12 | RN-104 | Rapid 7 | NW & Sec |  | AD Aviation - Rapid7 | Abu Dhabi Aviation | Sibtain | m.ali@abudhabiaviation.com | Ishan Arora | AMBER | Tanaya | Low | Completed |  | 2 | 1 | 0 | 2022-06-28 | 2023-07-14 |  |  | 90% | Abhinav to share the Insight VM documentation
| 13 | RN-270 | Cyclops | NW & Sec |  | LM Exchange-Cyclops (Vendor) | LM Exchange | Hareesh R S | hareesh.rs@lm-exchange.com | Ranjith Goerge | AMBER | Vignesh | Medium | On Track |  |  | 2 | 2 | 2023-04-25 | 2023-06-26 | 2023-08-07 |  | 100% | Project sign off shared to client
| 14 | RN-314 | VAPT | IntelliStrike |  | Damas - API Testing | Damas Jewellery LLC |  | Amit Pradhan | Rohit | GREEN | Vignesh | Low | Completed |  |  |  |  | 2023-08-01 | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  |  |  | Dependency with customer. Left over sessions to be planned.
| 15 | RN-294 | Invicti | NW & Sec |  | Airtel Africa - Invicti | Airtel Africa | Arun Menon | arun.menon@africa.airtel.com | Ishan Arora | AMBER | Vignesh | Medium | Completed |  | 3 |  | 3 | 2023-05-23 | 2023-07-14 |  | 2023-08-24 |  | Dependency with customer. Left over sessions to be planned. |  |  | Final documentation to be shared and get the sign off to close the project
| 16 | RN-260 | Rapid 7 - IVM | NW & Sec |  | Damac - Rapid 7 | Damac Properties | Rajesh Narayanan | Rajesh.Narayanan@damacgroup.com | Bibinu Ajith | GREEN | Pallavi Nair | Medium | Completed |  | 4 | 1 | 3 | 2023-04-10 | 2023-06-30 | 2023-07-07 | 2023-08-28 | 95% | Final documentation to be shared and get the sign off to close the project
| 17 | RN-119 | ISO Audit BCP | IntelliAssure |  | Transco - BCP | Transco | Khaled Omer Al Tamimi | Khaled.altamimi@transco.ae | Ayushman | GREEN | Pallavi Nair | Low | Completed |  | 4 | 3 | 1 |  | 2023-01-31 | 2023-12-30 | 2023-08-31 |  | Two drills are done, one reporting is pending for second one. Next drill is scheduled for Sept 23
| 18 | RN-322 | ISO Audit | IntelliAssure | RNS | SAAL_ Maintenance of ISO _ August_2023 | SAAL | Mehboob Merchant |  | Haytham | GREEN | Pallavi Nair | Low | Completed | [5 empty] | 2023-09-01 | 2023-08-29 | 2023-08-29
| 19 | RN-197 | VAPT | IntelliStrike | RNS | ES - 2023 - RAPID 7 & VAPT (4 Qtrs) | Emirates Steel |  |  |  | GREEN | Tanaya | Medium | Completed | [7 empty] | 2023-08-01 |  | Rapid 7 is closed. VAPT is ongiong. So the project is open in Zoho |  |  | Two drills are done, one reporting is pending for second one. Next drill is scheduled for Sept 23
| 20 | RN-119 | ISO Audit BCP | IntelliAssure | RNS | Transco - BCP | Transco | Khaled Omer Al Tamimi | Khaled.altamimi@transco.ae | Ayushman | GREEN | Pallavi Nair | Low | Completed |  | 4 | 3 | 1 | 2023-01-31 | 2023-12-30 |  | 2023-08-31 | 25% | Two drills are done, one reporting is pending for second one. Next drill is scheduled for Sept 23
| 21 | RN-349 | ISO | IntelliAssure - |  | Al Mana Retail - Maintenance of ISO/IEC 27001:2013 (ISMS)
| 22 | RN-16 | VAPT | IntelliStrike | RNS | Empower - VAPT 1 | Empower | Zaher | Zaher.ElAli@nextcarehealth.com | Ishan | AMBER | Rubeena | Low | Completed |  | 2 | 1 | 1 | 2023-11-11 | 2023-07-17 |  | 2023-09-20 | 81% |  |  |  | Email is being excluded from the scope. Rest implementation is complete, wtg for sign-off
| 23 | RN-191 | ForcePoint, FP | NW & Sec | RNS | ALDAR - Forcepoint, DLP | ALDAR | Rakesh Narang | rnarang@aldar.com | Bibinu Ajith | RED | Sean Faizal | High | Completed |  | 3 | 0 | 3 | 2023-01-17 | 2023-06-16 | 2023-12-31 | 2024-01-15 | 100% | Email is being excluded from the scope. Rest implementation is complete, wtg for sign-off
| 24 | RN-119 | ISO Audit BCP | IntelliAssure | RNS | Transco - BCP | Transco | Khaled Omer Al Tamimi | Khaled.altamimi@transco.ae | Ayushman | GREEN | Pallavi Nair | Low | Completed |  | 4 | 3 | 1 | 2023-01-31 | 2023-12-30 |  | 2023-08-31 | 25% | Two drills are done, one reporting is pending for second one. Next drill is scheduled for Sept 23 |  |  | Two drills are done, one reporting is pending for second one. Next drill is scheduled for Sept 23
| 25 | RN-228/337 | Proofpoint | NW & Sec | Vendor | RTS-Proofpoint | RTS | Balamurugan Singaram |  | Rohit Save | GREEN | Pallavi Nair | Medium | Completed |  |  |  |  | TBD | 2023-12-15 | 2023-12-29 | 2024-01-23 | 100% | fine tuning in progress. Sign off planned in the last week of Dec
| 26 | RN-356 | Fortinet | NW & Sec | RNS | Theodor Wille Intertrade FZE_Fortinet Q2 | Theodor Wille Intertrade FZE | Shrung Vachhrajani | Shrung.Vachhrajani@twipv.com | Ranjit George | GREEN | Sean Faizal | Low | Completed |  | 4 | 1 | 3 |  |  | 2023-12-31 | 2024-01-26 | 100% | DUBAI SITE IS COMPLETE. Germany is completed. HO and Doc is in progress |  |  | Sign off has been shared with client on 15th june. Waiting for approval.
| 27 | RN-102 | VAPT | IntelliStrike | RNS | ALDAR ACADAMICS / ADNOC SCHOOLS - VAPT | ALDAR | Sheik Mohaideen | sheik.mohaideen@aldareducation.com | Rohit Save | AMBER | Sean Faizal | Low | Completed |  | 5 | 0 | 5 | 2022-09-07 | 2023-07-27 | 2024-01-31 | 2024-01-29 | 100% | Invoicing completed - M1, M2, M3 & M4 COMPLETED |  |  | Vendor PS. Customer dependancy. Awaiting prerequisite readiness in client side to start the project
| 28 | [22 empty] | Final Sign-off pending
| 29 | RN-238 | VAPT | IntelliStrike | RNS | Seddiqi Holding - VAPT | Seddiqi Holding | Prince Rana | prince.rana@seddiqiholding.com | Rohit Save | AMBER | Pallavi Nair | Medium | Completed |  | 4 | 4 | 0 | 2023-03-06 | 2023-11-15 | 2023-12-29 | 2024-01-11 | 100% | Awaiting for the sign-off |  |  | Internal dependency. Abhinav need to work on AWS guideline document. CS assessment and SE is pending. Re-testing to be initiated for internal assessment & config review.
| 30 | RN-331 | Checkmarx | NW & Sec | Vendor | Tawajun Industrial Park - Checkmarx solution | Tawazun Industrial Park | Hassan | drmhasan@watheqlab.ae | Ishan Arora | GREEN | Sean Faizal | Medium | On Track | [6 empty] | 2024-02-28 | 2024-02-22 | 100% | Sign-off received on 21st Feb |  |  | Fine Tuning is pending
| 31 | RN-279 | cybereason | NW & Sec | Vendor | Damas - Cybereason | Damas - Cybereason | Amit Pradhan | apradhan@damasjewellery.com | Rohit Save | AMBER | Pallavi Nair | Medium | Completed |  | 2 | 2 | 0 | 2023-04-29 | 2023-07-14 | 2024-02-09 | 2024-02-26 | 90% | Close the reported issues and then ask for the sign-off |  |  | Fine Tuning is pending
| 32 | RN-379 | Tenable | NW & Sec | Vendor | DLD - Tenable VM | DLD | Abdulla Yalooq | alyalooq@dubailand.gov.ae | Ishan Arora | GREEN | Tanaya | Medium | On Track |  | 2 | 2 |  | 2023-12-11 | 2024-01-05 | 2024-01-15 | 2024-02-28 | 50% | Implementation in progress |  |  | Varun engaged to complete the last site on 18th Sep
| 33 | RN-409 | Barracuda WAF | NW & Sec | Vendor | Gulf Marine Services_Barracuda WAF | Gulf Marines Services Company LLC | Mushtafik Hanif |  | Unnikrishnan | GREEN | Divya | Low | On Track | [5 empty] | 2024-03-15 |  | 2024-03-08 | 100% | Sign off received on 08 March 24
| 34 | RN-309 | Akamai | NW & Sec | RNS | Mall Of Qatar_Akamai_19062023 | Mall of Qatar | Deepak Pradhan | Project can be created, as there are payment milestones | Brejesh Bisht | GREEN | Pallavi Nair | Low | On Track |  | 12 | 4 | 8 | 2023-07-01 | 2024-06-01 | 2024-06-30 | 2024-03-11 | 60% | Need not to be tracked as it is a subscription based project and ops team take care of the monthly billing |  |  | Delayed due to Config review (WiFi) assessment to be concluded by Suresh.
| 35 | RN-380 | ISO Consulting | IntelliAssure | RNS | OQ Trading_iso27K_aasmt_Q42023 | OQ Trading | Abhilash Radhadevi | abhilash.radhadevi@oq.com | Rohit Save | GREEN | Divya | Low | On Track |  |  |  |  | 2024-01-15 | 2024-03-22 |  | 2024-04-02 | 95%
| 36 | RN-37 | VAPT | IntelliStrike | RNS | FNG - VAPT | Fujairah National Group | Lalu Vijayn | lalu.v@fng.ae | Ishan Arora | AMBER | Vignesh | Low | On Track |  | 2 | 1 | 0 | 2021-08-16 | 2023-07-31 | 2024-04-19 | 2024-04-16 | 84% | Awaiting for sign-off.
| 37 | RN-353 | Forcepoint | NW & Sec | RNS | ES_Forcepoint Proxy - Licenses; Professional Services_ZTNA | Emirates Steel | Abdelghafour | Abdelghafour.AlAli@emiratessteel.com | Bibinu Ajith | AMBER | Vignesh | Medium | Delayed | 2024-04-22 | 1 |  | 1 |  |  | 2024-04-29 | 2024-04-22 | 90% | ZTNA implementation is complete. Issue fixing in progress. Sign off will be complete next week |  |  | Signed off
31 | 38 | RN-304 | Zscaler | NW & Sec | Vendor + RNS | Deem Finance_Zscaler | Deem Finance | Parthasardhi | parthasarathy@deem.io | Rohit Save | AMBER | Divya | Low | On Track |  | 4 | 2 | 2 | 2023-09-30 | 2024-04-19 | 2024-04-22 | 2024-04-22 | 98% | Conditional Sign-off received on 22nd with an exception that, the KT will be conducted in May and close the project fully |  |  | COMPLETE
23 | 39 | RN-89 | ForcePoint-DLP | NW & Sec | RNS | AJMAN BANK - DLP & FP | AJMAN BANK | Thanveer Sadiq | T.Sadiq@AjmanBank.ae | Ishan Arora | GREEN | Sean Faizal | High | On Track | 2024-04-25 | 4 | 2 | 2 | 2023-01-27 | 2023-08-21 | 2024-04-26 | 2024-04-25 | 100% | sign off received on 25 Apr. Sent it for invoicing
71 | 40 | RN-416 | VAPT | NW & Sec | RNS | DAMAS - 4 APIs VAPT | DAMAAC | Vijay | VijayM@damasjewellery.com | Rohit Save | GREEN | Vignesh | Low | On Track | 2024-04-24 | 1 | 0 | 1 | 2024-03-13 | 2024-03-31 | 2024-04-29 | 2024-04-24 | 100% | Retesting is not required. Sign off is is complete |  |  | Signed off on 10 Nov 23
35 | 41 | RN-342 | Akamai | NW & Sec | Vendor | MAF Bot Manager | MAF Carrefour | Jafar, Bayan (vendor) | bjafar@akamai.com | Bibinu Ajith | AMBER | Vignesh | Medium | Completed | 2024-05-01 | 1 | 0 | 1 |  |  | TBD | TBD |  | CS to check with Bibinu on the status -- payment received and project closed |  |  | Phase 1 is complete and waiting for Phase 2 kick off
15 | 42 | RN-3 | VAPT | IntelliStrike | RNS | Voltas - VAPT | Voltas | Amjad | akhan@voltas.com | Unnikrishnan | GREEN | Vignesh | Low | Completed | 2024-05-01 | 1 | 0 | 1 | 2022-01-17 | 2023-07-05 | 2024-04-29 |  | 80% | Re-testing is pending. Sign off and payments are complete. NO response from customer |  |  | Project will be closed by 17 Nov 23
17 | 43 | RN-242 | Mimecast | Data Center | Vendor | LM Exchange-Mimecast(Vendor) | LM Exchange | Hareesh R S | hareesh.rs@lm-exchange.com | Rohit Save | GREEN | Vignesh | Medium | On Track | 2024-05-17 | 16 | 0 | 16 | 2022-11-28 | 2023-06-26 | 2024-04-29 |  | 100% | Awaiting for sign-off
18 | 44 | RN-357 | Mimecast | NW & Sec | RNS | LM Exchange-Security Awareness trg | LM Exchange | Hareesh R S | hareesh.rs@lm-exchange.com | Rohit Save | GREEN | Vignesh | Medium | On Track | 2024-05-17 | 1 |  | 1 |  |  | 2024-04-29 |  | 75% | Firewall presentation is only pending. Awaiting for customer response on the schedule for Trg |  |  | Awaited for Signoff
22 | 45 | RN-289 | VAPT | IntelliStrike | RNS | EMPOWER-VAPT_2023 | EMPOWER | Rajesh Rajarathnam | rajesh.rajarathnam@empower.ae | Ishan Arora | GREEN | Sean Faizal | Low | Completed | 2024-04-26 | 3 | 0 | 3 | 2023-06-07 | 2023-09-06 | 2024-04-26 |  | 100% | Formal sign-off done for project closure- Invoicing has been complete |  |  | Faizan confirmed that project is closed. Being closed on 11th Dec
48 | 46 | RN-286 | VAPT | IntelliStrike | RNS | NAFFCO - VAPT | NAFFCO | Mankandan | manikandan.t@naffco.com | Unnikrishnan | GREEN | Vignesh | Low | Completed | 2024-05-21 | 4 | 0 | 4 | 2023-04-27 | 2023-09-04 | 2024-05-17 |  |  | Signoff receieved on 21st May 2024. | On Track |  | CR#1 - 3 tasks (12 man days), completed on task (7 days), 2 activites wtg for customer pre-reqs. Conditional sign-off for CR#1 CR#2 - 5 tasks (17 man days). Pending 5 days from CFR # 1 will be clubbed with CR#2
42 | 47 | RN-410 | Zscaler | NW & Sec | Vendor | Seddiqui Holding - zScaler | Seddiqui Holding | Prince | prince.rana@seddiqiholding.com | Rohit Save | GREEN | Divya | Low | Completed |  | 2 | 0 | 2 | 2024-02-02 | ###### |  |  | 100% | PS completed |  |  | Niraj was withdrawn from 12th Dec
32 | 48 | RN-239 | Sailpoint | Sailpoint | RNS | Aldar - SailPoint - CR (4 enhancements) | Aldar | Sunil Sharma | ssharma@aldar.com | Bibinu Ajith | GREEN | Laxmi | Medium | Completed |  | 2 | 1 | 1 | 2024-03-06 | ###### | 2024-05-30 |  | 100% | Received Sign Off
33 | 49 | RN-292 | VAPT | IntelliStrike | RNS | SKM - VAPT | SKM AirConditioning | Tayyab Haider | tayyab.haider@skmaircon.com | Faizan Javed | GREEN | Vignesh | Low | Completed |  | 4 | 0 | 4 | 2023-01-06 | 2023-08-14 | 2024-05-27 | 0 | 95% | Awaiting for sign-off. | On Track |  | Engagement will be complete by 21 Nov
50 | 52 | RN-231 | VAPT | IntelliStrike | RNS | DWTC VAPT 2022 | DWTC | Faisal | Faisal.Khan@dwtc.com | Ishan Arora | GREEN | Vignesh | Medium | completed | 2024-05-30 | 3 | 2 | 1 | 2023-12-26 | 2023-07-31 | 2024-05-27 |  | 100% | 30may - Signoff recieved | On Track |  | Phase 1 is complete, Waiting for sign-off. Phase 2 to start. Small query from customer in the phase 1 sign-off, which is being addressed by Nitesh (to work with Srikanth (who is on leave))
4 | 53 | RN-237 | VAPT | IntelliStrike | RNS | INTERPLAST - VAPT 2023 | INTERPLAST | Sabu John Bosco | Sabu@interplast-uae.com | Ranjit George | GREEN | Sean Faizal | Medium | Completed |  | 3 | 0 | 3 | 2023-03-27 | 2023-08-04 | 2024-05-09 | 2024-05-31 | 100% | Sign off Acknowledgement pending |  |  | fine tuning in progress. Sign off planned in the last week of Dec
59 | 54 | RN416 | VAPT | IntelliStrike | RNS | DAMAS Jewelery | DamasJewellery | Amit Pradhan | apradhan@damasjewellery.com | Rohit Save | GREEN | Vignesh | Low | Completed | 2024-06-06 | 3 |  | 3 |  |  | 2024-05-14 | 2024-06-06 | 100% | Sign off initiated of 28th May; Awaiting for sign off |  |  | DUBAI SITE IS COMPLETE. Germany is completed. HO and Doc is in progress
38 | 55 | RN-329 | ISO Consulting | IntelliAssure | RNS | DPW_ISO 27001_Consulting_Q3_2023 | DP World | Mariam Mazrouqui |  |  | GREEN | Divya | Low | Completed |  |  |  |  | 2023-10-10 | 24-06-2024 | 2024-04-26 |  | 100% |  |  |  | 2 more FWs to be purchased in the place of re-purposed HW (two sites are not ready). Soft closure. Once customer comes back, then this will be supported. Sean to check with Rubeena & Suresh on the pending tasks.
63 | 56 |  | PICUS | NW & Sec | RNS | RAK Bank |  |  |  |  | GREEN | Vignesh | Low | Completed | [8 empty] | 100% | License renewal has been done |  |  | Invoicing completed - M1, M2, M3 & M4 COMPLETED Final Sign-off pending
72 | 57 |  | Opswat | NW & Sec |  | Mashreq Opswat |  |  |  | Sagar | GREEN | Vignesh | Low | Completed | 2024-06-27 | [7 empty] | 100% | License delivery, need to confirm with Sean on whether it is a renewal |  |  | Awaiting for the sign-off
| 40 | RN-341 | Cybereason | NW & Sec | 2023-09-04 | RNS | Waha Health - CyberReason PS - 4 Days | Waha Health | Asam |  | asam.m@wahahealth.com | Ayushman | GREEN | Pallavi Nair | Low | Completed |  |  |  |  | 2023-09-08 | 2023-10-03 | 2023-11-15 | 2023-12-27 | 100% |  | Awaiting for sign-off
| 13 | RN-296 | VAPT | IntelliStrike | 2023-07-01 | RNS | Gulf Cryo - VAPT | Gulf Cryo | Zain Javed |  | zjaved@gulfcryo.com | Ishan Arora | GREEN | Vignesh | Low | Completed |  | 3 | 1 | 2 | 2023-07-03 |  | 2023-01-12 |  | 90% |  | Two web apps are pending under retesting. Conditional sign-off received.
| 62 | RN-239 | Sailpoint | Sailpoint | 2023-11-10 | RNS | Aldar_Sailpoint_PS_CR_Nov_2023 (Enhancements CR), Manage Engine CR (Aug 23) & HCM API Integration CR (Sep 23) | Aldar | Sunil Sharma |  | ssharma@aldar.com | Bibinu Ajith | GREEN | Vignesh | Medium | Completed |  | 2 | 2 |  |  | 2023-12-15 | 2023-12-29 |  | 100% |  | Sign-off has been asked - Enghancements CR (CR 3) Manage Engine CR - Closed (CR 1) HCM API Integration - Closed (CR 2)
| 2 | RN-78 | Sailpoint | Sailpoint | 2021-12-01 | RNS | DLD SAILPOINT | Dubai Land Department | Khalid |  | khalidmk@dubailand.gov.ae | Sagar Chopra | GREEN | Tanaya | Low | Completed |  | 4 |  | 4 | 2021-12-06 | 2023-07-31 | 2024-01-05 |  | 100% |  | Project sign-off complete Compliance Manager Reports demo is pending, which is impacting the Go-Live
| 47 | RN-359 | Fortinet | NW & Sec | 2023-09-26 | Vendor | Fortinet NAC & FortiSIEM | Property Finder | Sameh |  | sam@propertyfinder.ae | Haytham | GREEN | Samruddhi | Medium | On Track | [10 empty] | Samruddhi to plan a meeting with vendor
| 2 | RN-122 | Sailpoint | Sailpoint | 2021-05-01 | RNS | ADCB - SailPoint Phase 1 | ADCB | Jeny |  | JenyAnniePhilip.ext@adcb.com | Sagar Chopra | RED | Tanaya | Medium | On Hold |  | 12 | 10 | 2 | 2021-05-24 | 2023-09-29 | TBD |  | 66% |  | 3 App sign-off received. ECAMS is pending for sign-off. Mover UAT testing is pending with ADCB. Project is on hold. Phase 2 to be discussed and agreed
| 6 | RN-254 | Sailpoint | IntelliDeploy | 2023-04-03 | RNS | Digital 14 - SailPoint | Digital 14 (Katim) | Maddi Siva |  | Maddi.Prasad@katim.com | Ishan Arora | GREEN | Tanaya | Low | On Track |  | 3 | 2 | 1 | 2023-04-03 | 2023-09-29 | 2024-01-15 |  | 100% |  | Dec will be last month. Sign off will be received in first week of Jan 24 New PO received on 11 Dec from 03 OCT TO 31 DEC. Contract is getting renewed for one year
| 76 | RN-401 | Sailpoint | Sailpoint | 2023-12-13 | RNS | Mashreq Sailpoint CR - Dec 23 | MASHREQ BANK | Rajesh Gurikar |  |  | Ishan Arora | GREEN | Sean Faizal | Low | Completed |  | 1 | 1 |  |  | 2024-01-24 | 2024-02-10 |  | 100%
| 43 | RN-331 | Checkmarx | NW & Sec | 2023-05-01 | Vendor | Tawajun Industrial Park - Checkmarx solution | Tawazun Industrial Park | Hassan |  | drmhasan@watheqlab.ae | Ishan Arora | GREEN | Sean Faizal | Medium | On Track | [6 empty] | 2024-02-28 | 2024-02-22 | 100% |  | Sign-off received on 21st Feb
| 28 | RN-279 | cybereason | NW & Sec |  | Vendor | Damas - Cybereason | Damas - Cybereason | Amit Pradhan |  | apradhan@damasjewellery.com | Rohit Save | AMBER | Pallavi Nair | Medium | Completed |  | 2 | 2 | 0 | 2023-04-29 | 2023-07-14 | 2024-02-09 | 2024-02-26 | 90% |  | Close the reported issues and then ask for the sign-off
| 58 | RN-379 | Tenable | NW & Sec | 2023-11-22 | Vendor | DLD - Tenable VM | DLD | Abdulla Yalooq |  | alyalooq@dubailand.gov.ae | Ishan Arora | GREEN | Tanaya | Medium | On Track |  | 2 | 2 |  | 2023-12-11 | 2024-01-05 | 2024-01-15 | 2024-02-28 | 50% |  | Implementation in progress
| 9 | RN-239 | SailPoint | Sailpoint | 2023-01-01 | RNS | Aldar - SailPoint - Phase 1 | Aldar | Sunil Sharma |  | ssharma@aldar.com | Bibinu Ajith | GREEN | Laxmi | Medium | On Track |  | 5 | 3 | 2 | TBD | TBD |  |  | 100% |  | Phase 1 is complete and sign off received. Phase 2 will resume from Apr 24
| 14 | RN-185 | Sailpoint | Sailpoint | 01/11/2022 (Ph 1) & Dec 23 (Phase 2) | Intigral - Sailpoint (Phase 1 & 2) | Intigral | Anup |  | Anup.Nellippily@intigral.net | Ishan Arora | GREEN | Laxmi | Low | On Track |  | 5 | 2 | 3 | 2022-11-15 | 2023-08-07 | TBD |  | 90% |  | Conditional Sign-off received for Phase 1. 2 Apps were moved to Phase 2 (10 apps in the scope). Reqmt gathering for 2 apps is complete.
| 76 | RN-409 | Barracuda WAF | NW & Sec | 2024-02-10 | Vendor | Gulf Marine Services_Barracuda WAF | Gulf Marines Services Company LLC | Mushtafik Hanif |  |  | Unnikrishnan | GREEN | Divya | Low | On Track | [5 empty] | 2024-03-15 |  | 2024-03-08 | 100% |  | Sign off received on 08 March 24
| 77 | RN-411 | Barracuda Email Sec | NW & Sec | 2024-02-20 | RNS | Providence - Barracuda Email Security | Providence | Mujahed Khan |  |  | Komal | GREEN | Vignesh | Low | On Track |  | 1 | 1 |  | 2024-02-21 | 2024-03-08 | 2024-03-08 |  | 90% |  | As Build doc is being developed. Sign off will be complete by 8th March
| 33 | RN-309 | Akamai | NW & Sec | 2023-06-01 | RNS | Mall Of Qatar_Akamai_19062023 | Mall of Qatar | Deepak Pradhan |  | Project can be created, as there are payment milestones | Brejesh Bisht | GREEN | Pallavi Nair | Low | On Track |  | 12 | 4 | 8 | 2023-07-01 | 2024-06-01 | 2024-06-30 | 2024-03-11 | 60% |  | Need not to be tracked as it is a subscription based project and ops team take care of the monthly billing
| 49 | RN-370 | FireEye | NW & Sec | 2023-10-11 | Vendor | ADJD FireEye WEB MPS Licenses & Appliance | ADJD | Belal Abdullah |  | b.salmeen@adjd.gov.ae | Haytham | GREEN | Vignesh | Medium | Completed | 2024-03-14 | 1 | 1 |  |  | 2024-01-31 | 2024-03-15 |  | 100% |  | Upgrade is complete. Sign-off will be initiated in the WE 15 Mar 24
| 53 | RN-377 | Rapid 7 | NW & Sec | 2023-10-31 | RNS | WIG - Nesto - RAPID7_INSIGHT IDR_SEPT_2023 | Western International Group - Nesto | Raveesh P |  | raveesh.p@westernint.com | Ranjit George | GREEN | Vignesh | Medium | Completed | 2024-03-14 | 1 | 1 |  | 2023-11-14 | 2024-01-31 | 2024-03-15 |  | 90% |  | Conditional sign-off submitted with SOAR pending. Wtg for customer response.
| 65 | RN-378 | Managed Services | NW & Sec | 2023-11-10 | RNS | MBRSG_Securonix | MBRSG | Anthony |  | anthony.bartolo@mbrsg.ac.ae | Rohit Save | GREEN | Pallavi Nair | Medium | On Track | 2024-03-18 | 6 | 6 |  | 2023-11-10 | 2024-01-15 | 2024-03-15 |  | 100% |  | Documentation review is pending. Ready for sign-off.
| 58 | RN-380 | ISO Consulting | IntelliAssure | 2023-12-05 | RNS | OQ Trading_iso27K_aasmt_Q42023 | OQ Trading | Abhilash Radhadevi |  | abhilash.radhadevi@oq.com | Rohit Save | GREEN | Divya | Low | On Track |  |  |  |  | 2024-01-15 | 2024-03-22 |  | 2024-04-02 | 95%
| 35 | RN-312 | FW - F5 WAF | NW & Sec | 2023-07-01 | Vendor + RNS | ES_F5 Networks | Emirates Steel | Abdelghafour |  | Abdelghafour.AlAli@emiratessteel.com | Bibinu Ajith | GREEN | Tanaya | Low | On Track |  | 1 |  | 1 |  | 2023-10-02 | 2024-03-22 |  | 90% | As-Build is pending. Post as-bild, sign-off will be asked
| 3 | RN-37 | VAPT | IntelliStrike |  | RNS | FNG - VAPT | Fujairah National Group | Lalu Vijayn |  | lalu.v@fng.ae | Ishan Arora | AMBER | Vignesh | Low | On Track |  | 2 | 1 | 0 | 2021-08-16 | 2023-07-31 | 2024-04-19 | 2024-04-16 | 84% | Awaiting for sign-off.
|  | NEW | Crowdstrike | NW & Sec | 2024-04-03 | RNS | Gulf Cryo Crowdstrike | Gulf Cryo |  |  |  | Ishan Arora | GREEN | Vignesh | Low | On Track | [9 empty] | Roll out is done by customer, can be closed
| 41 | RN-353 | Forcepoint | NW & Sec | 2023-09-13 | RNS | ES_Forcepoint Proxy - Licenses; Professional Services_ZTNA | Emirates Steel | Abdelghafour |  | Abdelghafour.AlAli@emiratessteel.com | Bibinu Ajith | AMBER | Vignesh | Medium | Delayed |  | 1 |  | 1 |  |  | 2024-04-29 | 2024-04-22 | 90% | 2024-04-22 | ZTNA implementation is complete. Issue fixing in progress. Sign off will be complete next week
| 31 | RN-304 | Zscaler | NW & Sec | 2023-07-07 | Vendor + RNS | Deem Finance_Zscaler | Deem Finance | Parthasardhi |  | parthasarathy@deem.io | Rohit Save | AMBER | Divya | Low | On Track |  | 4 | 2 | 2 |  | 2023-09-30 | 2024-04-19 | 2024-04-22 | 98% | 2024-04-22 | Conditional Sign-off received on 22nd with an exception that, the KT will be conducted in May and close the project fully
| 23 | RN-89 | ForcePoint-DLP | NW & Sec |  | RNS | AJMAN BANK - DLP & FP |  | AJMAN BANK | Thanveer Sadiq |  | T.Sadiq@AjmanBank.ae | Ishan Arora | GREEN | Sean Faizal | High | On Track |  | 4 | 2 | 2 | 2023-01-27 | 2023-08-21 | 2024-04-26 | 2024-04-25 | 100% | sign off received on 25 Apr. Sent it for invoicing
| 71 | RN-416 | VAPT | NW & Sec | 2024-03-12 | RNS | DAMAS - 4 APIs VAPT |  | DAMAAC | Vijay |  | VijayM@damasjewellery.com | Rohit Save | GREEN | Vignesh | Low | On Track |  | 1 | 1 |  | 2024-03-13 | 2024-03-31 | 2024-04-29 | 2024-04-24 | 100% | Retesting is not required. Sign off is is complete
| 35 | RN-342 | Akamai | NW & Sec | 2023-08-02 | Vendor | MAF Bot Manager |  | MAF Carrefour | Jafar, Bayan (vendor) |  | bjafar@akamai.com | Bibinu Ajith | AMBER | Vignesh | Medium | Completed |  | 1 | 1 |  |  |  | TBD |  | TBD | CS to check with Bibinu on the status -- payment received and project closed
| 15 | RN-3 | VAPT | IntelliStrike |  | RNS | Voltas - VAPT |  | Voltas | Amjad |  | akhan@voltas.com | Unnikrishnan | GREEN | Vignesh | Low | Completed |  | 1 | 1 | 0 | 2022-01-17 | 2023-07-05 | 2024-04-29 |  | 80% | Re-testing is pending. Sign off and payments are complete. NO response from customer
| 17 | RN-242 | Mimecast | Data Center | 2022-11-01 | Vendor | LM Exchange-Mimecast(Vendor) |  | LM Exchange | Hareesh R S |  | hareesh.rs@lm-exchange.com | Rohit Save | GREEN | Vignesh | Medium | On Track |  | 16 | 0 | 16 | 2022-11-28 | 2023-06-26 | 2024-04-29 |  | 100% | Awaiting for sign-off
| 18 | RN-357 | Mimecast | NW & Sec | 2023-08-01 | RNS | LM Exchange-Security Awareness trg |  | LM Exchange | Hareesh R S |  | hareesh.rs@lm-exchange.com | Rohit Save | GREEN | Vignesh | Medium | On Track |  | 1 | 1 |  |  |  | 2024-04-29 |  | 75% | Firewall presentation is only pending. Awaiting for customer response on the schedule for Trg
| 22 | RN-289 | VAPT | IntelliStrike | 2023-06-01 | RNS | EMPOWER-VAPT_2023 |  | EMPOWER | Rajesh Rajarathnam |  | rajesh.rajarathnam@empower.ae | Ishan Arora | GREEN | Sean Faizal | Low | Completed |  | 3 | 0 | 3 | 2023-06-07 | 2023-09-06 | 2024-04-26 |  | 100% | Formal sign-off done for project closure- Invoicing has been complete
| #REF! | RN-286 | VAPT | IntelliStrike | 2024-04-23 | RNS | NAFFCO - VAPT |  | NAFFCO | Mankandan |  | manikandan.t@naffco.com | Unnikrishnan | GREEN | Vignesh | Low | Completed |  | 4 | 0 | 4 | 2023-04-27 | 2023-09-04 | 2024-05-17 |  | 98% | Signoff receieved on 21st May 2024. | On Track
| #REF! | RN-410 | Zscaler | NW & Sec | 2024-02-09 | Vendor | Seddiqui Holding - zScaler | Seddiqui Holding |  | Prince |  | prince.rana@seddiqiholding.com | Rohit Save | GREEN | Divya | Low | Completed |  | 2 | 0 | 2 | 2024-02-02 | 2024-05-18 |  |  | 100% | PS completed
| #REF! | RN-239 | Sailpoint | Sailpoint | 2024-03-06 | RNS | Aldar - SailPoint - CR (4 enhancements) | Aldar |  | Sunil Sharma |  | ssharma@aldar.com | Bibinu Ajith | GREEN | Laxmi | Medium | Completed |  | 2 | 1 | 1 | 2024-03-06 | 2024-05-15 | 2024-05-30 |  | 100% | Received Sign Off
| #REF! | RN-292 | VAPT | IntelliStrike | 2024-06-23 | RNS | SKM - VAPT | SKM AirConditioning |  | Tayyab Haider |  | tayyab.haider@skmaircon.com | Faizan Javed | GREEN | Vignesh | Low | Completed |  | 4 | 1 | 3 | 2023-01-06 | 2023-08-14 | 2024-05-27 |  | 95% | Awaiting for sign-off. 10/5 - JP and Faizan has planned to meet customer by next week to obtain conditional signoff 24/5 - out of 3 milestones, 2 milestones has been closed, payment recieved. | On Track
| 50 | RN-231 | VAPT | IntelliStrike | 2024-12-26 | RNS | DWTC VAPT 2022 | DWTC |  | Faisal |  | Faisal.Khan@dwtc.com | Ishan Arora | GREEN | Vignesh | Medium | completed |  | 3 | 2 | 1 | 2023-12-26 | 2023-07-31 | 2024-05-27 |  | 100% | 30may - Signoff recieved | On Track
| 4 | RN-237 | VAPT | IntelliStrike | 2023-03-01 | RNS | INTERPLAST - VAPT 2023 | INTERPLAST |  | Sabu John Bosco |  | Sabu@interplast-uae.com | Ranjit George | GREEN | Sean Faizal | Medium | Completed |  | 3 | 0 | 3 | 2023-03-27 | 2023-08-04 | 2024-05-09 | 2024-05-31 | 100% | Sign off Acknowledgement pending
| 59 | RN416 | VAPT | IntelliStrike | 2024-05-14 | RNS | DAMAS Jewelery | DamasJewellery |  | Amit Pradhan |  | apradhan@damasjewellery.com | Rohit Save | GREEN | Vignesh | Low | Completed |  | 3 |  | 3 | 2024-05-14 | 2024-06-06 |  |  | 100% | Sign off initiated of 28th May; Awaiting for sign off 19/5 - Signoff recieved
| 38 | RN-329 | ISO Consulting | IntelliAssure | RNS | DPW_ISO 27001_Consulting_Q3_2023 | DP World | Mariam Mazrouqui |  | Faizan Javed | GREEN | Divya | Low | Completed |  | 2 | 2 |  | 2023-10-10 | 24-6-2024 | 2024-04-26 |  | 100% | Sign off recieved
| 63 |  | PICUS | NW & Sec |  | RNS | RAK Bank | [5 empty] | GREEN | Vignesh | Low | Completed | [9 empty] | License renewal has been done
| 72 |  | Opswat | NW & Sec | 2024-06-24 |  | Mashreq Opswat | License renewal |  |  |  |  | GREEN | Vignesh | Low | Completed | [5 empty] | 2024-06-27 |  |  |  | License delivery, need to confirm with Sean on whether it is a renewal License delivered to customer on 28th Jun
| 60 | RN-435 | you | NW & Sec | TBD | RNS | CWT-SML LOGISTICS LLC | Firewall replacement | CWT Logistics | Rajesh |  | Unnikrishnan | AMBER | Sean Faizal | Medium | Completed |  |  |  |  | 2024-06-20 | 2024-07-11 | 2024-08-18 |  | 100% | project complete, signoff recieved
| 13 | RN-427 | Fortinet | NW & Sec | 45432 | RNS | MBRSG FireWall Reconfiguration | 501E - Reconfig 601F - Reconfig & relocation VPN Config - 4 sites | MBRSG | Anthony Bartolo | anthony.bartolo@mbrsg.ac.ae | Ishan Arora | GREEN | Sean Faizal | Low | Completed |  | 3 | 3 | 0 | 2024-05-20 | 2024-06-10 | 2024-08-18 |  | 100% | Signoff Sign-off recieved
| 17 | RN-19 | CyberArK | CyberArK | RNS/Vendor | DOH - Cyberark | DOH | Nahas |  | Bibinu Ajith | nnizar@doh.gov.ae | AMBER | High | Pallavi Nair | 2024-09-12 | 15 | 4 | 11 | 2021-08-31 | 2024-05-31 | 2024-09-12 | 2024-09-12 | 75% | Received project signoff
| 54 | RN-368 | Solarwinds | NW & Sec | RNS | Beema Insurance - Solarwinds NMC |  | Beema Insurance | Wasif Khan | mohammed.wasif@beema.com.qa | Deepinder Singh | GREEN | Vignesh | Medium | Completed | 3 | 1 | 2 | 2023-11-01 | 2023-11-30 | TBD |  | 86% | NCM issues reported and are being fixed(Product limitation issue). Conditional sign-off received. 10/5 - Wilard is working with Solarwinds to get issue sorted; Meeting to be scheduled with customer by Wilard Customer needs to get a demo license for Fortinet Devices so we can simulate the issue again in SolarWinds NCM 27/06 - Customer waiting for VM license. 28/8 - Solarwinds and Beema Insurance working together to solve the issue | Delay from Customer & Vendor
| 50 | RN-317 | VAPT | IntelliStrike | RNS | Ajman Chamber of Commerce & Industry |  | Ajman Chamber of Commerce & Industry | Shams | shams@ajmanchamber.ae | Haytham | GREEN | Vignesh | Low | Completed |  |  | #VALUE! | 2023-08-10 |  | 2024-07-08 |  | 99% | Re-testing in completed for Internal NW& Ext Web App. Conditional sign-off received; Internal network report has to be shared with customer 13/05 - Had spoke with customer, he will check with his team and revert. 21/05 - SIgnoff initiated; Awaiting for sign off 27/06 - Following up with customer for a month to get signoff. 3/07 - Signoff email have sent to customer | Delay from Customer

## Closed AMC Projects (hidden)
PROJECT MANAGEMENT LOG TEMPLATE
PROJECT REGISTER
The PROJECT Identification portion of this table will automatically populate to the Financial Data, Deliverables and Performance, and Risk Register tabs within this workbook.
| PROJECT DATA |  |  |  |  | CUSTOMER DATA |  |  |  | ACCOUNT DATA |  | PROJECT MANAGEMENT
| NO. | PROJECT ID | Project Type | PROJECT NAME | Start Date | CUSTOMER ID | CUSTOMER NAME | CUSTOMER SPOC NAME | CUSTOMER SPOC EMAIL | ACCOUNT MANAGER NAME | ACCOUNT HEALTH | INTERNAL PROJECT MANAGER | Status | Scope | Total Health Checks | HC Completed | HC Due | Open Health Checks | Closed Health Checks | No. Incident Tickets | Open Incident Tickets | Closed Incident Tickets | START DATE | END DATE | Payment for | Term | Billing Forecast Month | Biling Status | Invoice Date | Billing Amount | Payment Satus | Forecast Revenue | Paid Date
| 31 | RN-245 | ForcePoint, FP | Al Hilal - Forcepoint |  |  | Al Hilal Bank | Amjad Alnajjar | aalnajjar@alhilalbank.ae | Bibinu | GREEN | Pallavi Nair | Completed |  | 1 |  |  | 4 | 1 | Remote incident support | 0 | 3 | 2022-08-03 | 2023-08-02 |  |  |  | Complete | 2023-08-07 | 11040 |  | 2023-09-06
|  | RN-302 | Sailpoint | DIB - Sailpoint |  |  | DIB | NA | NA | Sagar Chopra | AMBER | Pallavi Nair | Completed | [9 empty] | 2023-05-28 | 2023-06-28 |  |  | 2023-07-01 | Complete |  | 30912 | Not Received | 2023-08-13
|  | RN-302 | Sailpoint | DIB - Sailpoint |  |  | DIB | NA | NA | Sagar Chopra | AMBER | Pallavi Nair | Completed | [9 empty] | 2023-06-28 | 2023-07-28 |  |  | 2023-08-01 |  |  | 30912
| 43 | RN-222 | THALES | ADJD - THALES |  |  | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Bibnu Ajith | GREEN | Sean Faizal | Completed
| 44 | RN-132 | ForcePoint | ADJD - ForcePoint |  |  | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Bibnu Ajith | GREEN | Sean Faizal | Completed |  | 4 |  |  | 3 | 1 |  |  |  | 2020-04-25 | 2023-04-24
| 53 | RN-123 | ForcePoint-DLP | Tawazun economic Council ForcePoint-DLP |  |  | Tawazun economic Council | Mansoor Nuruddin | mundare@tawazun.gov.ae | Sagar Chopra | GREEN | Sean Faizal | Completed |  | 4 |  |  | 2 | 2 |  |  |  | 2022-06-19 | 2023-06-18
| 53 | RN-123 | ForcePoint-DLP | Tawazun economic Council ForcePoint-DLP |  |  | Tawazun economic Council | Mansoor Nuruddin | mundare@tawazun.gov.ae | Sagar Chopra | GREEN | Sean Faizal | Completed |  | 4 |  |  | 2 | 2 |  |  |  | 2022-06-19 | 2023-06-18
| 54 | RN-120 | Sailpoint | Tawazun Economic Council |  |  | Tawazun Economic Council | Mansoor Nuruddin | mundare@tawazun.gov.ae | Sagar Chopra | AMBER | Sean Faizal | On Track |  | 2 |  |  | 1 | 1 |  |  |  | 2022-04-14 | 2025-04-13
| 31 | RN-245 | ForcePoint, FP | Al Hilal - Forcepoint |  |  | Al Hilal Bank | Amjad Alnajjar | aalnajjar@alhilalbank.ae | Bibinu | GREEN | Pallavi Nair | Completed |  | 1 |  |  | 4 | 1 | Remote incident support | 0 | 3 | 2022-08-03 | 2023-08-02 |  |  |  | Complete | 2023-08-07 | 11040 |  | 2023-09-06
| 32 | RN-162 | Checkpoint | Al Shirawi / Global Shipping and Logistics - Checkpoint |  |  | Al Shirawi / Global Shipping and Logistics | Uma Sanker | uma.sanker@alshirawi.ae | Sagar Chopra | GREEN | Pallavi Nair | Not Started | Can be closed, as we have renewal | 1 |  |  | 0 | 1 | 3 | 0 | 0 | 2022-12-28 | 2023-12-27 |  |  |  | Complete
| 40 | RN-128 / 202 | McAfee | ADJD - McAfee |  |  | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Bibnu Ajith | GREEN | Sean Faizal | On Track |  | 4 |  |  | 2 | 2 |  |  |  | 2022-08-10 | 2023-08-09 |  |  | 2023-09-01 | Complete | 2023-09-19 | 46748.09
| 41 | RN-128 / 202 | LogRythm | ADJD - LogRythm |  |  | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Bibnu Ajith | GREEN | Sean Faizal | On Track |  | 4 |  |  | 3 | 1 |  |  |  | 2022-08-10 | 2023-08-09
| 42 | RN-128 / 202 | FireEye | ADJD - FireEye |  |  | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Bibnu Ajith | GREEN | Sean Faizal | On Track |  | 4 |  |  | 3 | 1 |  |  |  | 2022-08-10 | 2023-08-09
| 43 | RN-222 | THALES | ADJD - THALES/ Trellix |  |  | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Bibnu Ajith | GREEN | Sean Faizal | Completed
| 44 | RN-132 | ForcePoint | ADJD - ForcePoint |  |  | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Bibnu Ajith | GREEN | Sean Faizal | Completed |  | 4 |  |  | 3 | 1 |  |  |  | 2020-04-25 | 2023-04-24 |  |  | 2023-09-01 | Complete | 2023-09-18 | 2625
| 46 | RN-128 / 202 | Tenable | ADJD - Tenable |  |  | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Sagar Chopra | AMBER | Sean Faizal | On Track |  | 4 |  |  | 3 | 1 |  |  |  | 2022-08-10 | 2023-08-09
| 53 | RN-290 | Cybereason | Support-Amlak Finance-Cybereason | There is no AMC | [6 empty] | Vignesh | Not Started
| 59 | RN-170 | Checkpoint | Support-Al Shirawi / Global Shipping and Logistics- CheckPoint FW | RNS | [6 empty] | Pallavi Nair | Completed |  | 1 |  |  |  |  | 3 |  |  | 2022-06-14 | 2023-06-13
| 2 | RN-126 | Fortigate | Commercial Bank of Dubai - Fortigate | RNS |  | Commercial Bank Dubai | Shihab | shihab.packer@cbd.ae | Ishan Arora | GREEN | Pallavi Nair | On Track |  | 4 |  |  | 3 | 1 | 4 | 0 | 0 | 2022-08-10 | 2023-08-09 |  |  |  | Complete |  |  | Paid
| 3 | RN-127 | Trendmicro | Commercial Bank of Dubai-Trendmicro | RNS |  | Commercial Bank Dubai | Shihab | shihab.packer@cbd.ae | Ishan Arora | GREEN | Pallavi Nair | On Track |  | 4 |  |  | 3 | 1 | 4 | 0 | 0 | 2022-08-10 | 2023-08-09 |  |  |  | Complete |  |  | Paid
| 28 | RN-173 |  | Exclaimer E-mail Signature System and Auto Responder | Human Resource Authority-Exclaimer E-mail Signature System and Auto Responder | To be checked | HRA | Anas | Anas.Shahi@hra.gov.ae | Haythem | RED | Pallavi Nair | Delayed | 4 HCs | 2 |  |  | 2 | 0 | NA |  |  | 2020-09-20 | 2023-09-02
|  | RN-223 |  | Gemalto / Thales | DPP - Gemalto |  | Dubai Police Procecution |  |  | Ishan |  | Vignesh | On Track |  | 1 |  |  |  |  | 3 |  |  | 2023-08-12 | 2023-08-11 |  |  |  | Complete | 2023-08-01 | 13248
| 34 | RN-212 |  | CyberArc | ADJD - CyberArc | RNS | ADJD | Belal Salmeen | b.salmeen@adjd.gov.ae | Sagar Chopra | GREEN | Vignesh | On Track |  | 4 |  |  | 1 | 3 |  |  |  | 2022-12-26 | 2023-12-25 |  |  |  | Complete
| 48 | RN-267 |  | Sailpoint | DOH-Sailpoint | RNS | DOH |  |  | Bibinu |  | Pallavi Nair | Completed | 1 HC and 7 Incidents per year | [8 empty] | 2022-01-01 | 2023-06-28 |  | Y1 | Complete
|  | RN-267 |  | Sailpoint | DOH-Sailpoint |  | DOH |  |  | Bibinu |  | Pallavi Nair | Not Started | 1 HC and 7 Incidents per year | [8 empty] | 2024-01-01 | 2025-06-28 |  | Y3 | 2024-06-01 |  |  | 321309.91
| 45 | RN-223 | Can be closed | Gemalto / Thales | DPP - Gemalto | RNS |  | Dubai Police Procecution |  |  | Ishan | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  | 1 | 0 |  | 2022-08-12 | 2023-08-11 |  |  |  | Complete |  | 13248 | Paid
| 43 | RN-144 |  | Tripwire | Emirates Airlines - Tripwire | RNS |  | Emirates Airlines | Durgesh Kumar | durgeshkumar.saraswat@dnata.com | Ishan Arora | GREEN | Sean Faizal | On Track | 2 HCs and 4 Incidents |  | 2 |  |  |  |  | 4 | 2022-11-14 | 2023-11-13 |  |  |  | Complete
| 9 | RN-224 | Can be closed, as 8 incidents were resolved | Sailpoint | ADCB-Sailpoint | RNS | 2023-01-01 | ADCB |  |  | Sagar Chopra |  | Pallavi Nair | On Track | 8 Incidents | [7 empty] | 2023-01-01 | 2023-12-31 |  |  |  | Complete |  | 36800 | Paid
| 28 | RN-143 | Proposal to be checked | CARBON BLACK | Tawazun Economic Council | RNS |  | Tawazun Economic Council | Mansoor Nuruddin | mundare@tawazun.gov.ae | Sagar Chopra | Sean Faizal | RED | Missed | 4 HCs and 4 Incident per Year |  | 4 |  |  |  |  | 4 | 2023-01-27 | 2024-01-26 |  |  |  | Complete |  |  | Paid
| 30 | RN-193 |  |  | Tripwire | DIB - Tripwire |  | RNS |  | DIB | Mohammed Jibran Afzal | mohammed.jibran@dib.ae | Sagar Chopra | GREEN | Sean Faizal | On Track | 8 Incidents only, no preventive HCs | [6 empty] | 8 |  |  | 2023-01-01 | 2023-12-31 |  |  |  | Complete |  | 29440 | Paid | Paid
| 32 | RN-200 |  |  | ALL PRODUCTS | DLD CONSOLIDATED (Barracuda-WAF&LB, ARCON, PALO-ALTO,IBM,NETCRUNCH,FORTINET) |  | RNS |  | DLD | Rambhul Singh | rambhul.singh@dubailand.gov.ae | Sagar Chopra | GREEN | Sean Faizal | Delayed |  |  | 24 |  |  | 11 | 9 |  |  |  | 2022-12-26 | 2023-12-26 |  |  | 2023-03-01 | Complete |  |  | Paid | Paid
| 18 | RN-159 |  |  | Desktops,Printers and Firewall | Apex Fund Services Dubai |  | RNS |  | Apex Fund Services Dubai | Sadashiv Chavan | sadashiv.chavan@apexgroup.com | Rohit Suresh Save | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  | 1 | 0 | 18 | 0 | 5 | 2022-12-13 | 2023-12-12 |  |  | 2023-10-01 |  |  | 3333.75
| 19 | RN-160 |  |  | Desktops,Printers and Firewall | Apex Fund Services Abu Dhabi |  | RNS |  | Apex Fund Services Abu Dhabi | Sadashiv Chavan | sadashiv.chavan@apexgroup.com | Rohit Suresh Save | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  | 1 | 0 | 18 | 0 | 9 | 2022-12-13 | 2023-12-12 |  |  | 2023-10-01 |  |  | 3333.75
| 4 | RN-183 |  | check count of HC, inc | Solarwinds | PIH - Solarwinds |  | RNS |  | Power International Holding | Ahmad Nabeel | a.nabeel@powerholding-intl.com | Brejesh | GREEN | Pallavi Nair | On Track | HC and Inc ticket info to be checked |  | 4 |  |  | 2 | 2 | 10 | 0 | 6 | 2022-12-28 | 2023-12-27 |  |  |  | Complete |  | 10000 | Not Paid | Not Paid
| 23 | RN-201 |  |  | McAfee | ADAA - Mcafee |  | RNS |  | ADAA | Mariam Mohamed | Mariam.Alhammadi@adaa.gov.ae | Haythem | GREEN | Pallavi Nair | On Track |  |  | 4 |  |  | 3 | 1 | 6 | 1 | 0 | 2023-01-01 | 2023-12-31 |  |  |  | Complete |  | 12492.5 | Paid | Paid
| 8 | RN-224 |  |  | Sailpoint | ADCB-Sailpoint |  | RNS | 2023-08-04 | ADCB |  |  | Sagar Chopra |  | Pallavi Nair | On Track | 8 Incidents | [9 empty] | 2023-08-04 | 2024-12-31 | [5 empty] | 36800
| 22 | RN-196 |  |  | Solarwinds | Dukhan Bank -Solarwinds |  | RNS |  | Dukhan Bank | Imran Ansari | imran@dukhanbank.com | Brejesh | GREEN | Pallavi Nair | On Track |  |  | 4 |  |  | 3 | 1 | 2 | 0 | 2 | 2022-11-12 | 2023-11-12 |  |  |  | Complete |  | 11500 | Paid | Paid
| 75 | RN-335 |  | Will start after PS is complete | Checkpoint | Support-Arcadia-Checkpoint (13 Dec 22 - 12 Dec 23) |  | RNS |  | Arcadia School |  |  |  |  | Pallavi Nair | On Track | 1 HC and 3 Incidents | [9 empty] | 2022-12-13 | 2023-12-12
| 57 | RN-216 |  |  | Cybereason | MOFAIC Cybereason |  | RNS |  | MOFAIC |  |  | Bibinu |  | Pallavi Nair | On Track | 1HC per Qtr, 2 Incidents per Qtr |  | 4 |  |  |  |  | 8 |  |  | 2022-12-15 | 2023-12-14
| 42 | RN-280 |  |  | Tenable | DMT - Tenable |  | RNS |  | DMT | Reshma Bharathan | Reshma.Bharathan@dmt.gov.ae | Bibinu | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  | 1 | 0 | 8 | 0 | 2 | 2022-12-22 | 2023-12-22 |  |  |  | Complete |  | 20000 | Paid | Paid
| 58 | RN-199 |  |  | Checkpoint | Support-Al Shirawi (Oasis Investment) - Checkpoint |  | RNS |  |  | Uma Sanker | uma.sanker@alshirawi.ae | Sagar Chopra | GREEN | Pallavi Nair | On Track |  |  | 1 |  |  |  |  | 3 |  |  | 2022-11-28 | 2023-11-27
| 9 | RN-265 |  | Not Started (PS in active) |  | Forcepoint Cloud Migration | Aldar-Forcepoint Cloud Migration |  | RNS | Linked with RN-191 | Aldar |  |  | Bibinu |  | Pallavi Nair | Not Started | 6 Break Down Calls / Incident Support (Every Year) • 2 Preventive Maintenance Support (Every Year) |  | 2 |  |  |  |  | 6 | [7 empty] | No seprate invoice needed. Part of Services
| 15 | RN-149 |  |  |  | Fortigate | MOFAIC Fortigate |  | RNS |  | MOFAIC |  |  | Bibinu | GREEN | Pallavi Nair | Completed |  |  | 2 | Y1 - H1 & H2 |  | 1 | 1 | 4 |  |  | 2021-12-13 | 2022-12-12 |  |  | 2022-12-01 | Complete |  | 8227.44 | Paid
| 46 | RN-221 |  |  |  | Lepide | Human Resource Authority-Lepide |  | Vendor |  | HRA | Anas | Anas.Shahi@hra.gov.ae | Haythem | RED | Pallavi Nair | Delayed |  |  | 4 |  |  | 4 | 0 | NA |  |  | 2020-10-26 | 2023-10-21 |  |  |  | Complete |  | 16560 | Paid
|  | RN-280 |  | Expiring on 22 Dec 23 |  | Tenable | DMT Tenalble |  | RNS |  | DMT |  |  | Bibinu |  | Pallavi Nair | On Track | 8 Incidents, 1 HC | [10 empty] | 2023-12-22
| 49 | RN-256 |  |  |  | Sailpoint | SIB-100 HR Support |  | RNS |  | SIB | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | Completed | [10 empty] | 2022-10-13 | 2023-01-13 |  |  | 2022-10-01 | COMPLETE |  | 4856.25 | Paid
| 58 | RN-278 | Check | 30 man days AMC (task based) |  | Logrythm | Nextcare - Logrhythm |  | Vendor |  | Nextcare | Zaher from Nextcare Vendor - Hady Madkour | Zaher.ElAli@nextcarehealth.com hady.madkour@logrhythm.com | Ishan Arora |  | Pallavi Nair |  | Task based AMC - tasks will be supported by vendor
| 37 | RN-205 / 332 | Completed |  |  | Sailpoint | QAPCO-Sailpoint |  | RNS |  | QAPCO |  |  | Brejesh |  | Vignesh | Completed | 6 incidents and 1 HC in a year | Incidents are consumed. | 1 |  |  |  |  | 6 |  |  | 2023-08-21 | 2024-08-20
| 45 | RN-241 | Completed | Will expire on 13 Feb 24 |  | Sailpoint | MAF Carrefour-Sailpoint |  | RNS |  | MAF Carrefour |  |  | Bibinu |  | Vignesh | On Track | 10 Incidents per Yr, 1 HC for Qtr |  | 1 |  |  |  |  | 2.5 |  |  | 2023-02-15 | 2024-02-14 | Q1 23 |  | 2023-02-01 | Complete |  | 76114.49
| 58 | New | Completed | Premium Support, No AMC |  | Checkpoint | AlShirawi - Checkpoint DIC & AlQuoz |  | RNS |  | Al Shirawi Eqpt Co |  |  |  |  | Pallavi Nair | Completed | Premium support for 1800 applicance - Qty 2 | [9 empty] | 2023-10-03 | 2024-10-02 |  |  | 2023-11-01 |  |  | 83300 |  |  | Hardware has been delivered and no AMC. So project is closed
Closed in March
| 3 | RN-169 | Completed | Will expire on 31 Mar 24 | EDR | Solarwinds | MBRHE Solarwinds |  | RNS |  | MBRHE | Mohammad Amjad | mamjad@mbrhe.ae | Ishan Arora | GREEN | Pallavi Nair | On Track | 4 HCs and 6 Incidnets |  | 4 |  |  |  |  | 6 | 0 |  | 2023-03-31 | 2024-03-31 |  |  |  | Complete |  |  | Paid
| 4 | RN-187 | Completed | will expire on 24 Mar 24 | N&S | Palo Alto | MBRHE-PaloAlto |  | RNS |  | MBRHE | Mohammad Amjad | mamjad@mbrhe.ae | Ishan Arora | GREEN | Pallavi Nair | On Track | 12 PM HCs and 8 Incidnets for 3 yrs |  | 2 |  |  | 1 | 1 | 4 | 1 | 1 | 2021-03-25 | 2024-03-24 |  |  |  | Complete |  | 36245.65 | Paid
| 11 | RN-164 | Completed | will end on 21 Mar 24 | Data Sec | ForcePoint, FP | UBL - Forcepoint Web Security |  | RNS |  | UBL - UAE, Bahrain & Qatar | Talha Ahmed Seddiqi | talha.siddiqui@ubl.com.pk | Ishan Arora | GREEN | Pallavi Nair | On Track |  |  | 4 |  |  | 3 | 1 | 4 | 0 | 4 | 2023-03-22 | 2024-03-21 |  |  |  | Complete |  |  | Paid
| 70 | RN-394 | Completed | Will expire on 27 Mar 24 | N&S | Checkpoint | Brandfolio Checkpoint Email |  | RNS |  | Brandfolio |  |  | Ranjit |  | Pallavi Nair | On Track | 2 HCs and 4 Incidents |  | 2 |  |  |  |  | 4 |  |  |  | 2024-03-27
| 38 | RN-327 | Ongoing | Expiring on 19th Apr 24 | EDR | Tenable | Tawajun Economic Counsil - Tenable HC | 4 HCs | RNS |  | Tawajun Economic Counsil |  |  | Sagar Chopra | GREEN | Sean Faizal | Completed | 1HC - 1 Man day to be delivered by 19 Jul 23 |  | 1 | [7 empty] | 2023-04-20 | 2023-07-19 |  |  | 2023-07-01 | Complete | 2023-07-19 | 1840 |  |  | check with Ishan for the renewal of the contract
|  | RN-327 | Ongoing | Expiring on 19th Apr 24 |  | Tenable | Tawajun Economic Counsil - Tenable HC | 4 HCs | RNS |  | Tawajun Economic Counsil |  |  | Sagar Chopra | GREEN | Sean Faizal | Completed | 1HC - 1 Man day to be delivered by 19 Oct 23 |  | 1 | [8 empty] | 2023-10-19 |  |  | 2023-10-01 | Complete |  | 1840
|  | RN-327 | Completed | Expiring on 19th Apr 24 |  | Tenable | Tawajun Economic Counsil - Tenable HC | 4 HCs | RNS |  | Tawajun Economic Counsil |  |  | Sagar Chopra | GREEN | Sean Faizal | Completed | 1HC - 1 Man day to be delivered by 19 Jan 24 |  | 1 | [8 empty] | 2024-01-19 |  |  | 2024-01-01 | Complete |  | 1840
|  | RN-327 | Completed | Expiring on 19th Apr 24 |  | Tenable | Tawajun Economic Counsil - Tenable HC | 4 HCs | RNS |  | Tawajun Economic Counsil |  |  | Sagar Chopra | GREEN | Sean Faizal | On Track | 1HC - 1 Man day to be delivered by 19 Apr 24 |  | 1 | [8 empty] | 2024-04-19 |  |  | 2024-04-01 | Complete |  | 1840
| 12 | RN-243 | Completed | Renewed from 16 Mar 24 |  | Ivanti SD | Tawajun Industrial Park - Mindware | Vendor (Support by Mindware) | Mindware | 2024-03-16 |  |  |  | Ishan | GREEN | Sean Faizal | On Track | RNS-AMC : Local Support - Professional Service (5 Man Days/40 hours excluding quarterly health Check-up) and 4 Quarterly Health Checks |  | 2 (Mindware - 3 man days) and 2 (RNS - 5 man days) | [7 empty] | 2024-03-16 | 2024-06-15 | Q1 |  | 2024-05-01 |  |  | 6700
|  | RN-243 | Completed | Renewed from 16 Mar 24 |  | Ivanti SD | Tawajun Industrial Park - Mindware | [6 empty] | Ishan | GREEN | Sean Faizal | On Track | RNS-AMC : Local Support - Professional Service (5 Man Days/40 hours excluding quarterly health Check-up) and 4 Quarterly Health Checks |  | 2 (Mindware - 3 man days) and 2 (RNS - 5 man days) | [7 empty] | 2023-06-16 | 2024-09-15 | Q2 |  | 2024-08-01 |  |  | 6700
|  | RN-243 | Completed | Renewed from 16 Mar 24 |  | Ivanti SD | Tawajun Industrial Park - Mindware | [6 empty] | Ishan | GREEN | Sean Faizal | On Track | RNS-AMC : Local Support - Professional Service (5 Man Days/40 hours excluding quarterly health Check-up) and 4 Quarterly Health Checks |  | 2 (Mindware - 3 man days) and 2 (RNS - 5 man days) | [7 empty] | 2023-09-16 | 2024-12-15 | Q3 |  | 2024-11-01 |  |  | 6700
|  | RN-243 | Ongoing | Renewed from 16 Mar 24 |  | Ivanti SD | Tawajun Industrial Park - Mindware | [6 empty] | Ishan | GREEN | Sean Faizal | On Track | RNS-AMC : Local Support - Professional Service (5 Man Days/40 hours excluding quarterly health Check-up) and 4 Quarterly Health Checks |  | 2 (Mindware - 3 man days) and 2 (RNS - 5 man days) | [7 empty] | 2023-12-16 | 2025-03-15 | Q4 |  | 2024-03-01 |  |  | 6700
| 22 | RN-120 | Completed | Will end on 15 May 24 | Identity | Sailpoint | Tawazun Economic Council Sailpoint |  | RNS | 2023-05-16 | Tawazun economic Council | Mathew Rajesh |  | Ishan Arora | GREEN | Sean Faizal | On Track | AMC including 4 onsite visits | [6 empty] | 4 |  |  | 2023-05-16 | 2024-05-15 |  |  | 2023-12-01 | Complete |  | 15546
| 23 | RN-211 | Completed | Will end on 29 Feb 24 | EDR | Tripwire | Ajman Bank Tripwire |  | RNS |  | Ajman Bank | Ruwayah Ali AlKetbi | R.AlKetbi@AjmanBank.ae | Ishan Arora | GREEN | Sean Faizal | On Track | 4 HCs and unlimited incidents |  | 4 |  |  | 3 | 1 | Unlimited |  |  | 2023-03-01 | 2024-02-29 |  |  | 2023-03-01 | Complete |  |  | Paid |  | Check with Ishan for the renewal of the contract
|  | RN-162 | Completed | Will end in 14 Jun 24 | N&S | Checkpoint | Al Shirawi / Global Shipping and Logistics - Checkpoint |  | RNS |  | Al Shirawi / Global Shipping and Logistics | Uma Sanker | uma.sanker@alshirawi.ae | Sagar Chopra | GREEN | Pallavi Nair | On Track | 6 annual tickets including 4 Incident Response tickets (9 by 6 support hours – excluding Fridays) and 2 General health check/preventive maintenance tickets, unlimited telephonic and email support, unlimited remote support 1 Total |  | 2 |  |  |  |  | 4 |  |  | 2023-06-15 | 2024-06-14 |  |  | 2023-08-01 | Complete | 2023-08-21 | 82950 |  | 2023-09-20
| 4 | RN-220 | Completed | Ex[pire in june | EDR | Solarwinds | Qterminals-Solarwinds |  | RNS |  | Qterminals | Akbar Puzhakkalakath | apuzhakkalakth@QTerminals.com | Brejesh | GREEN | Pallavi Nair | On Track | 4 HCs and 8 Incidents |  | 4 |  |  | 2 | 2 | 8 | 0 | 1 | 2021-06-29 | 2024-06-28 |  |  | TBD | 3rd Yr - Unbilled |  | 39000 |  |  | Invoicing is pending. Last year invoicing is pending. Check with customer on the continuity of services
| 33 | RN-311 | Ongoing | Will end in Jun 24 | Identity | Sailpoint | SIB new 100 hr support | RNS |  |  |  | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | completed | Q1 (July) | [9 empty] | 2023-07-01 | 2023-09-01 |  |  | 2023-07-01 | COMPLETE | 2023-07-12 | 4856.25 | 2023-08-11
|  | RN-311 | Ongoing | Will end in Jun 24 |  | Sailpoint | SIB new 100 hr support | RNS |  |  |  | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | completed | Q2 | [9 empty] | 2023-10-01 | 2023-12-01 |  |  | 2023-10-01 | COMPLETE |  | 4856.25
| 11 | RN-311 | Completed | Will end in Jun 24 |  | Sailpoint | SIB new 100 hr support | RNS |  |  |  | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | completed | Q3 | [9 empty] | 2024-01-01 | 2024-03-01 |  |  | 2024-01-01 | COMPLETE |  | 4856.25
|  | RN-311 | Completed | Will end in Jun 24 |  | Sailpoint | SIB new 100 hr support | RNS |  |  |  | Mubashir Hafiz | mubashir.hafeez@sib.ae | Bibinu Ajith | GREEN | Vignesh | completed | Q4 | [9 empty] | 2024-04-01 | 2024-06-01 |  |  | 2024-04-01 | COMPLETE |  | 4856.25
| 42 | RN-343 | Ongoing | Will end on 11 Sep 24 | EDR | McAfee | ADJD_ MacAfee renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 | 3 |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  | Check withh Rekha on the invoicing plan
|  | RN-343 | Ongoing | Will end on 11 Sep 24 |  | McAfee | ADJD_ MacAfee renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-343 | Ongoing | Will end on 11 Sep 24 |  | McAfee | ADJD_ MacAfee renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
| 43 | RN-344 | Ongoing | Will end on 11 Sep 24 | PAM | CyberArc | ADJD_ CyberArk renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  | Check withh Rekha on the invoicing plan
|  | RN-344 | Ongoing | Will end on 11 Sep 24 |  | CyberArc | ADJD_ CyberArk renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-344 | Ongoing | Will end on 11 Sep 24 |  | CyberArc | ADJD_ CyberArk renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
| 44 | RN-345 | Ongoing | Will end on 11 Sep 24 | Data Sec | ForcePoint, FP | ADJD_ ForcePoint renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  | Check withh Rekha on the invoicing plan
|  | RN-345 | Ongoing | Will end on 11 Sep 24 |  | ForcePoint, FP | ADJD_ ForcePoint renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-345 | Ongoing | Will end on 11 Sep 24 |  | ForcePoint, FP | ADJD_ ForcePoint renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
| 45 | RN-347 | Ongoing | Will end on 11 Sep 24 | N&S | LogRhythm | ADJD_ LogRhythm renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  | Check withh Rekha on the invoicing plan
F |  | RN-347 | Ongoing | Will end on 11 Sep 24 |  | LogRhythm | ADJD_ LogRhythm renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-347 | Ongoing | Will end on 11 Sep 24 |  | LogRhythm | ADJD_ LogRhythm renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
| 46 | RN-346 | Ongoing | Will end on 11 Sep 24 | N&S | FireEye | ADJD_ FireEye renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  | Check withh Rekha on the invoicing plan
|  | RN-346 | Ongoing | Will end on 11 Sep 24 |  | FireEye | ADJD_ FireEye renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-346 | Ongoing | Will end on 11 Sep 24 |  | FireEye | ADJD_ FireEye renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
| 47 | RN-348 | Ongoing | Will end on 11 Sep 24 | EDR | Tenable | ADJD_ Tenable renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q1 : 12 Sep 23 | Q1 : 11 Dec 23 |  |  | 2023-12-01 |  |  | 2625 each Qtr |  |  | Check withh Rekha on the invoicing plan
|  | RN-348 | Ongoing | Will end on 11 Sep 24 |  | Tenable | ADJD_ Tenable renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q2 : 12 Dec 23 | Q2 : 11 Mar 24 |  |  | 2024-03-01 |  |  | 2625 each Qtr
|  | RN-348 | Ongoing | Will end on 11 Sep 24 |  | Tenable | ADJD_ Tenable renewal_August 2023 |  | RNS | 2023-09-11 | ADJD - Abu Dhabi Judicial Dept | Hamad Al Hassani | hs.alhassani@adjd.gov.ae | Haytham | GREEN | Vignesh | Completed | 18 Incidents & 4 HC per year |  | 4 |  |  | 1 | 3 | 18 | 1 | 17 | Q3 : 12 Mar 24 | Q3 : 11 Jun 24 |  |  | 2024-06-01 |  |  | 2625 each Qtr
| 12 | RN-166 | Completed |  | N&S | Fortigate | Al Dhaffra - Fortigate Firewall + FortiAnalyzer |  | RNS |  | Al Dhaffra Insurance | Alaa Saad | alaa.saad@aldhafrainsurance.ae | Bibinu | GREEN | Pallavi Nair | On Track |  |  | 2 |  |  | 1 | 1 | 4 | 0 | 0 | 2023-02-24 | 2024-02-23 |  |  | COMPLETE | Complete |  | 18500 | Paid
|  |  | S.No. | Customer Name | Product Name | Start Date | End Date
|  |  | 1 | Apex Fund Services - Abu Dhabi | Desktops,Printers and Firewall | 2022-12-13 | 2023-12-12
|  |  | 2 | Apex Fund Services - Dubai | Desktops,Printers and Firewall | 2023-12-18 | 2023-12-19
|  |  | 3 | ADAA | McAfee | 2023-01-01 | 2023-12-31
|  |  | 4 | Al Shirawi / Global Shipping and Logistics | CheckPoint 6200 (in HA) Firewall + Smart-1 405 Appliance | 2022-12-28 | 2023-12-27
|  |  | 5 | ADCB | Sailpoint | 2023-01-01 | 2023-12-31
|  |  | 6 | Arcadia | Checkpoint | 2022-12-13 | 2023-12-12 | Renewed
|  |  | 7 | Mofaic | Cybereason | 2022-12-14 | 2023-12-14
|  |  | 10 | Al shirawi -Leminar AC | Checkpoint | 2023-01-01 | 2023-12-01
|  |  | 11 | Al Shirawi Oasis - Metal | Checkpoint | 2022-12-11 | 2023-12-10
|  |  | 12 | Al Shirawi Oasis - Rental | Checkpoint | 2022-12-11 | 2023-12-10
|  |  |  | DLD | Barracuda Load Balancer-641 | 2022-12-26 | 2023-12-26
|  |  |  | DLD | Barracuda WAF-340 | 2023-12-26 | 2023-12-26
|  |  |  | DLD | Arcon | 2022-12-29 | 2023-12-28
|  |  |  | DLD | Palo Alto | 2022-03-07 | 2023-12-31
|  |  |  | DLD | Fortinet | 2022-12-31 | 2023-12-30
|  |  |  | DLD | IBM | 2022-12-31 | 2023-12-30
|  |  |  | DLD | Netcrunch | 2022-12-31 | 2023-12-30
|  |  | 8 | Al shirawi - Electrical and Mechanical (RAK Office) - Contracting | Checkpoint | 2023-02-01 | 2024-01-31
|  |  | 9 | Al Shirawi - Enterprice LLC Shekh Zayed Road | Checkpoint | 2023-02-01 | 2024-01-31
|  |  |  | MAF Carrefour | Sailpoint | Start Date: 15-Feb-23 End date: 14-Feb-24
|  |  | 2 | Emirates Airlines | Tripwire | 2022-11-14 | 2023-11-13 | Renewed
Note on C10: CS Rao: Rekha to check and confirm
Note on C11: CS Rao: CS to check with KD
Note on C14: CS Rao: Manasi to check and confirm the start and end dates
Note on C16: CS Rao: Can be closed
Note on C17: CS Rao: CS to check with KD for McAfee, LogRythm and FireEye, CyberArc and Teanable
Note on C18: CS Rao: CS to check with KD for McAfee, LogRythm and FireEye, CyberArc and Teanable
Note on C19: CS Rao: CS to check with KD for McAfee, LogRythm and FireEye, CyberArc and Teanable
Note on C20: CS Rao: Rekha to check and confirm
Note on C21: CS Rao: CS to check with KD
Note on C22: CS Rao: CS to check with KD for McAfee, LogRythm and FireEye, CyberArc and Teanable
Note on C23: CS Rao: not started
Note on C24: CS Rao: Get the details from Pallavi
Note on C27: CS Rao: Rekha to check with Manasi / Gracy on the support documentation

## Projects needed attention
# | Project Name | Project coordinator | Account Mgr | Update on date
1 | Emrill - | Vignesh | Rohit | Invoiced but payment not received - Junaid have to speak with customer -- 02 milestones or open out of 03)
2 | Gargash - Invoiced but payment not received | Divya | Rohit | Invoicing is completed and payment is not received, need to finish fortimgr activity, customer is not availble.. Will check to day to get it one
3 | DPW - Documentation completed and awaiting for sign-off | Divya | Rohit | 02 milestone are pending out of 03, this week we are going to meet the clientd
4 | Emirates policy centre.. Test enviornment is not ready | Sean | Rohit | 04th iteration is pening
5 | Emirates national Investments - Change in the Point of contact | Vignesh | Rohit | Need to check with Rohit
6 | SKM - Invoice is done awaiting for payment release | Vignesh | Faizen | Doing follow-up
8 | DWTC- VAPT | Vignesh | Ishaan | Expecting to close this pojetct my dod
9 | Interplast | Sean
10 | ADCB sailpoint | laxmi |  | Project not started yet-- customer PO is awaited
11 | Tawazun industrial park - FP | Sean | Ishaan | There is a data dependency with client and sean is working to close this eod June
13 | Damas Arcon | Pallavi | Rohit | 50%. Payment pending,, sign-off is pending
15 | NAFFCO - | Vignesh | Unni | Awaiting for sign-off,, one sign-of is pending (01 milestone is pending out of 03)